## Sheet1
Step |  | Description | Artifact | Activity | Description
1 | Updating the master design plan | Updating the master design plan should occur after the stage is planned, to record the estimated time and resources required in stage 4. The master design plan will also be updated at the end of stage 4 to record the actual time and effort expended in stage 4 |  |  | - The QPE should explain the evaluation process to the attendees and their role in the evaluation workshop: + Role of the attendees + No dumb questions + Yield to the facilitator + Avoid side conversations + Stay focused + Find issues, do not fix them + Go easy on the architect
2 | Evaluation preparation | These are the activities associated with preparing for the architecture design evaluation workshop. This may differ depending upon whether the evaluation is internal or external | Click here |  | - The CA will lead the evaluation and trace through the architecture design artifacts, beginning with the review of the business context and the business constraints - The business constraints:
3 | Evaluation workshop | This is the amount of time spent in the actual design evaluation. Typically ACDM evaluation lasts a day or less; however, in industry trials a few evaluations span two days for large systems with large external stakeholder groups | Click here | 1.Introduction 2.Review Business Context and Business Constraints 3.Review the Technical Requirements and Constraints 4.Architecture Overview Presentation 5.Functional Analysis 6.Structural Analysis: Analyze the Systemic Structures Using the Quality Attribute Scenarios 7.Summary: Review Recorded Issues
4 | Post-evaluation activities | After the evaluation, the issues uncovered during the evaluation must be recorded in the issues action document, and the resolution action determined by the chief architect
Note on G3: QPE: Quality Process Engineer Reference: Table 11.5 page 274 Page 296
Note on G4: CA: Chief Architect