## Revision history
Document Reviewer Information
Reviewer Name | Review Attendance (R/S) | Comments
R/S: Required or Suggested participants or functions for the document review meeting
Document Approver Information
Approver Name | Approver Function | Comments
Document Revision History
Date | Revision | Status | Change Summary | Revised by | Version
25/11/2013 | design template | on going |  | Ngo Quang Huy | 1
2013-02-12 | update plan | on going |  | Ngo Quang Huy | 2

## Master design plan
MASTER DESIGN PLAN
CATEGORIES |  |  | ASSIGN | MAIN RESPONSIBLE | TIME
[5 empty] | week 3 | week 4 | week 5 | week 6 | week 7 | week 8 | week 9
[5 empty] | 2013-11-18 | 2013-11-25 | 2013-12-02 | 2013-12-09 | 2013-12-16 | 2013-12-23 | 2013-12-30
STAGE 1 | Activities | Discover Architectural Drivers. | Team | Huynh Trong Khang
|  | meeting with customer #1 | Team
|  | Review with mentor #1 | Team
|  | Meeting with customer #2. | Team
|  | Meeting with mentor #2. | Team
|  | Review with customer #3. | Team
Team
| Documents | Operation Requirement Document | Huynh Trong Khang
|  | Review Operation Requirement Document. | Team
STAGE 2 | Activities | Establish Project Scope.
Define entities Draw use-case model Create use-case description Create quality attribute scenario.
Review with mentor #1
Meeting with customer #1
Review with mentor #2
Review customer, mentor & closed architecture drivers specification & product backlog document.
| Documents | Architecture Drivers Specification
Product Backlog Document.
STAGE 3 | Activities
Documents
STAGE 4 | Activities
Documents
STAGE 5 | Activities
Documents
STAGE 6 | Activities
Documents
STAGE 7 | Activities
Documents
Formulas:
week 4 = [TIME]+7

## main filter
Member
Lê Ngọc Châu
Khấu Thành Đạo
Ngô Quang Huy
Nguyễn Phan Xuân Huy
Huỳnh Trọng Khang
Tạ Ngọc Thiên Phú