## Team member
Chau Le
Dao Khau
Huy Ngo
Huy Nguyen
Khang Huynh
Phu Ta

## Chau Le
Admission System Project
Report date: 14/5/2014 |  |  | Phase: Daily report sprint 4
Reporter: Chau Le
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Test - Create question | Low | 14/5/2014 | 14/5/2014 | Done |  | Chau Le
2 | [6 empty] | Chau Le
3
4
Plan for next days
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Dao Khau
Admission System Project
Report date: 14/5/2014 |  |  | Phase: Daily report sprint 4
Reporter: Dao Khau
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Deploy-Android's DDS | Medium | 2014-12-05 | 2014-12-05 | On-going |  | Dao Khau
2 | Deploy-Android's DMS | Medium | 2014-12-05 | 2014-12-05 | On-going |  | Dao Khau
3 | Implement - Send mail on android | High | 2014-12-05 | 2014-12-05 | Done
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Huy Ngo
Admission System Project
Report date: 14/5/2014 |  |  | Phase: Daily report sprint 4
Reporter: Huy Ngo
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Prototype Android DMS application | High | 2014-12-05 | 2014-12-05 | Done |  | Huy Ngo
2 | Test - Login/log out on android | Low | 14/5/2014 | 14/5/2014 | Done
3 | Test - Show Q/A on android | Low | 14/5/2014 | 14/5/2014 | Done
4 | Test - Search Q/A on Android | Low | 2014-12-05 | 2014-12-05 | Done
6
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
2
3

## Huy Nguyen
Admission System Project
Report date: 14/5/2014 |  |  | Phase: Daily report sprint 4
Reporter: Huy Nguyen
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Web service - Save Q/A on android | Medium | 2014-12-05 | 2014-12-05 | Done |  | Huy Nguyen
2
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Khang Huynh
Admission System Project
Report date: 14/5/2014 |  |  | Phase: Daily report sprint 4
Reporter: Khang Huynh
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Implement - Save Q/A on android | High | 2014-12-05 | 2014-12-05 | Done |  | Khang Huynh
2 | Implement -Delete Q/A | High | 2014-12-05 | 2014-12-05 | Done |  | Khang Huynh
3 | Implement - Create question | High | 14/5/2014 | 14/5/2014 | Done |  | Khang Huynh
4 | Web service - send mail on android | Medim | 13/5/2014 | 13/5/2014 | Done |  | Khang Huynh
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1 | Android virtual sometime being crash
The most significance knowledge gained last week
# | Description
1
2
3

## Phu Ta
Admission System Project
Report date: 14/5/2014 |  |  | Phase: Daily report sprint 4
Reporter: Phu Ta
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Implement - Search Q/A on Android | High | 2014-12-05 | 2014-12-05 | On-going |  | Phu Ta
2
3
4
Plan for next days
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3