## Team member
Chau Le
Dao Khau
Huy Ngo
Huy Nguyen
Khang Huynh
Phu Ta

## Chau Le
Admission System Project
Report date: 07/5/2014 |  |  | Phase: Daily report sprint 4
Reporter: Chau Le
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Implement - Tạo câu hỏi trên android hiển thị bộ từ điển | Medium | 2014-06-05 | 2014-06-05 | Done |  | Chau Le
2 | Web service - công cụ quản trị nhận câu hỏi từ android hiển thị bộ từ điển | Medium | 2014-06-05 | 2014-06-05 | Done |  | Chau Le
3
4
Plan for next days
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Dao Khau
Admission System Project
Report date: 07/5/2014 |  |  | Phase: Daily report sprint 4
Reporter: Dao Khau
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Web service - Xử lý tìm kiếm từ android hiển thị bộ từ điển | Medium | 2014-05-05 | 2014-05-05 | Done |  | Dao Khau
2 | Deploy-cong cu hien thi android | High | 2014-06-05 | 2014-06-05 | On-going |  | Dao Khau
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Huy Ngo
Admission System Project
Report date: 07/5/2014 |  |  | Phase: Daily report sprint 4
Reporter: Huy Ngo
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Detail design cho ứng dụng hiển thị bộ từ điển trên android application | High | 2014-06-05 | 2014-06-05 | Done |  | Huy Ngo
2
3
4
6
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
2
3

## Huy Nguyen
Admission System Project
Report date: 07/5/2014 |  |  | Phase: Daily report sprint 4
Reporter: Huy Nguyen
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Implement - Cập nhật bộ từ điển trên android hiển thị bộ từ điển | Medium | 2014-05-05 | 2014-05-05 | Done |  | Huy Nguyen
2
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Khang Huynh
Admission System Project
Report date: 07/5/2014 |  |  | Phase: Daily report sprint 4
Reporter: Khang Huynh
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Implement - Xem chi tiết câu hỏi trên android hiển thị bộ từ điển | Medium | 2014-05-05 | 2014-05-05 | Done |  | Khang Huynh
2 | Lấy thêm yêu cầu cho business rule cho công cụ hiển thị từ điển trên android application | High | 2014-06-05 | 2014-06-05 | On-going |  | Khang Huynh
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1 | Android virtual sometime being crash
The most significance knowledge gained last week
# | Description
1
2
3

## Phu Ta
Admission System Project
Report date: 07/5/2014 |  |  | Phase: Daily report sprint 4
Reporter: Phu Ta
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Web service - Gửi danh sách câu hỏi sang android hiển thị bộ từ điển | Medium | 2014-06-05 | 2014-06-05 | Done |  | Phu Ta
2
3
4
Plan for next days
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3