## Team member
Chau Le
Dao Khau
Huy Ngo
Huy Nguyen
Khang Huynh
Phu Ta

## Chau Le
Admission System Project
Report date: 18/4/2014 |  |  | Phase: Daily report sprint 3
Reporter: Chau Le
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Cập nhật giao diện | High | 16/04/2014 | 16/04/2014 | On-going |  | Chau Le
2 | Implement system test | medium | 16/04/2014 | 16/04/2014 | On-going |  | Chau Le
3
4
Plan for next days
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Dao Khau
Admission System Project
Report date: 18/4/2014 |  |  | Phase: Daily report sprint 3
Reporter: Dao Khau
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Implement-cập nhật index | High | 16/04/2014 | 16/04/2014 | On-going |  | Dao Khau
2 | Deploy-cong cu quan tri | Medium | 16/04/2014 | 16/04/2014 | On-going |  | Dao Khau
3 | Deploy-cong cu hien thi | Medium | 16/04/2014 | 16/04/2014 | On-going |  | Dao Khau
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Huy Ngo
Admission System Project
Report date: 18/4/2014 |  |  | Phase: Daily report sprint 3
Reporter: Huy Ngo
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Implement system test | medium | 16/04/2014 | 16/04/2014 | On-going | some function not available for test | Huy Ngo
2
3
4
5
6
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
2
3

## Huy Nguyen
Admission System Project
Report date: 18/4/2014 |  |  | Phase: Daily report sprint 3
Reporter: Huy Nguyen
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Implement system test | medium | 16/04/2014 | 16/04/2014 | On-going |  | Huy Nguyen
2
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Khang Huynh
Admission System Project
Report date: 18/4/2014 |  |  | Phase: Daily report sprint 3
Reporter: Khang Huynh
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | fix bug | High | 16/04/2014 | 16/04/2014 | On-going |  | Khang Huynh
2
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Phu Ta
Admission System Project
Report date: 18/4/2014 |  |  | Phase: Daily report sprint 3
Reporter: Phu Ta
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | fix bug | High | 16/04/2014 | 16/04/2014 | On-going |  | Phu Ta
2 | Webservice-gửi index | Medium | 17/04/2014 | 17/04/2014 | On-going |  | Phu Ta
3
4
Plan for next days
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3