## LeNgocChau
Admission System Project
Report date: 18/4/2014 |  |  | Phase: Daily report sprint 3
Reporter: Le Ngoc Chau
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Cập nhật giao diện | High | 16/04/2014 | 16/04/2014 | On-going |  | Le Ngoc Chau
2 | Implement system test | medium | 16/04/2014 | 16/04/2014 | On-going |  | Le Ngoc Chau
3
4
Plan for next days
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## KhauThanhDao
Admission System Project
Report date: 18/4/2014 |  |  | Phase: Daily report sprint 3
Reporter: Khau Thanh Dao
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Implement-cập nhật index | High | 16/04/2014 | 16/04/2014 | On-going |  | Khau Thanh Dao
2 | Deploy-cong cu quan tri | Medium | 16/04/2014 | 16/04/2014 | On-going |  | Khau Thanh Dao
3 | Deploy-cong cu hien thi | Medium | 16/04/2014 | 16/04/2014 | On-going |  | Khau Thanh Dao
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## NgoQuangHuy
Admission System Project
Report date: 18/4/2014 |  |  | Phase: Daily report sprint 3
Reporter: Ngo Quang Huy
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Implement system test | medium | 16/04/2014 | 16/04/2014 | On-going | some function not available for test | Ngo Quang Huy
2
3
4
5
6
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1

## NguyenPhanXuanHuy
Admission System Project
Report date: 18/4/2014 |  |  | Phase: Daily report sprint 3
Reporter: Nguyen Phan Xuan Huy
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Implement system test | medium | 16/04/2014 | 16/04/2014 | On-going |  | Nguyen Phan Xuan Huy
2
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## HuynhTrongKhang
Admission System Project
Report date: 18/4/2014 |  |  | Phase: Daily report sprint 3
Reporter: Huynh Trong Khang
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | fix bug | High | 16/04/2014 | 16/04/2014 | On-going |  | Huynh Trong Khang
2
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## TaNgocThienPhu
Admission System Project
Report date: 18/4/2014 |  |  | Phase: Daily report sprint 3
Reporter: Ta Ngoc Thien Phu
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | fix bug | High | 16/04/2014 | 16/04/2014 | On-going |  | Ta Ngoc Thien Phu
2 | Webservice-gửi index | Medium | 17/04/2014 | 17/04/2014 | On-going |  | Ta Ngoc Thien Phu
3
4
Plan for next days
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Team member
No | Team member
1 | Le Ngoc Chau
2 | Khau Thanh Dao
3 | Ngo Quang Huy
4 | Nguyen Phan Xuan Huy
5 | Huynh Trong Khang
6 | Ta Ngoc Thien Phu