## LeNgocChau
Admission System Project
Report date: 5/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Le Ngoc Chau
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Code interface for list question that is anwser | Medium | 2014-03-03 | 2014-04-03 | Done |  | Le Ngoc Chau
2
3
4
Plan for next days
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Code interface for dictionary |  | 2014-05-03 |  |  |  | Le Ngoc Chau
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1 | understand how to use ckeditor
2
3

## KhauThanhDao
Admission System Project
Report date: 5/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Khau Thanh Dao
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Code interface for login | Medium | 2014-03-03 | 2014-03-03 | Done |  | Khau Thanh Dao
2 | Research ckeditor | High | 2014-03-03 | 2014-04-03 | Done |  | Khau Thanh Dao
3
4
Plan for next days
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Code interface for menu |  | 2014-05-03 |  |  |  | Khau Thanh Dao
2 | Research tiles template |  | 2014-05-03 |  |  |  | Khau Thanh Dao
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1 | understand how to use ckeditor
2
3

## NgoQuangHuy
Admission System Project
Report date: 5/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Ngo Quang Huy
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Code interface for list not replied | Medium | 2014-03-03 | 2014-03-03 | On-going |  | Ngo Quang Huy
2 | Implement for login/ logout | High | 2014-03-05 | 2014-03-05 | On-going |  | Ngo Quang Huy
3 | Implement database intranet | High | 2014-03-06 | 2014-03-06 | On-going |  | Ngo Quang Huy
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Code interface for list not replied |  | 2014-07-03 |  |  |  | Ngo Quang Huy
2 | Implement for login/ logout |  | 2014-10-03 |  |  |  | Ngo Quang Huy
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## NguyenPhanXuanHuy
Admission System Project
Report date: 5/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Nguyen Phan Xuan Huy
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Researh testcase template | Medium | 2014-05-03 | 2014-05-03 | On-going |  | Nguyen Phan Xuan Huy
2
3
4
Plan for next day
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## HuynhTrongKhang
Admission System Project
Report date: 5/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Huynh Trong Khang
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Code interface for dictionary-list | Medium | 2014-03-03 | 2014-03-03 | Done |  | Huynh Trong Khang
2 | Ajax for load page | High | 2014-03-03 | 2014-04-03 | Done |  | Huynh Trong Khang
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Implement login to understand webflow |  | 2014-05-03 |  |  |  | Huynh Trong Khang
2 | Update user dictionary-list interface |  | 2014-05-03 |  |  |  | Huynh Trong Khang
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1 | How to convert psd to HTML
2 | Knowledge about springMVC flow
3

## TaNgocThienPhu
Admission System Project
Report date: 5/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Ta Ngoc Thien Phu
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Code list-question interface | Medium | 2014-03-03 | 2014-03-03 | Done |  | Ta Ngoc Thien Phu
2
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Research load list-question from db |  | 2014-05-03 |  |  |  | Ta Ngoc Thien Phu
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1 | understand how to use ckeditor
2
3

## Team member
No | Team member
1 | Le Ngoc Chau
2 | Khau Thanh Dao
3 | Ngo Quang Huy
4 | Nguyen Phan Xuan Huy
5 | Huynh Trong Khang
6 | Ta Ngoc Thien Phu