## LeNgocChau
Admission System Project
Report date: 11/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Le Ngoc Chau
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Update header and footer | High | 2014-09-03 | 2014-10-03 | Done |  | Le Ngoc Chau
2 | Integrate inteface | Medium | 2014-09-04 | 2014-10-04 | On-going |  | Le Ngoc Chau
3
4
Plan for next days
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Code function search |  | 2014-11-03 |  |  |  | Le Ngoc Chau
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## KhauThanhDao
Admission System Project
Report date: 9/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Khau Thanh Dao
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Code function checkbox in interface | High | 2014-09-03 | 2014-10-03 | Done |  | Khau Thanh Dao
2 | Integrate inteface | High | 2014-09-03 | 2014-10-03 | Done |  | Khau Thanh Dao
3
4
Plan for next days
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Code function load page when choose item |  | 2014-11-03 |  |  |  | Khau Thanh Dao
2 | Integrate code |  | 2014-11-03 |  |  |  | Khau Thanh Dao
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## NgoQuangHuy
Admission System Project
Report date:9/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Ngo Quang Huy
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Code interface for list not replied | medium | 2014-11-03 | 2014-11-03 | Done |  | Ngo Quang Huy
2 | Thực hiện database intranet | High | 2014-11-04 | 2014-11-04 | Done |  | Ngo Quang Huy
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## NguyenPhanXuanHuy
Admission System Project
Report date: 11/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Nguyen Phan Xuan Huy
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Addition testcase | High | 2014-11-03 | 2014-11-03 | On-going |  | Nguyen Phan Xuan Huy
2 | Research and demo send mail | Medium | 2014-11-03 | 2014-11-03 | On-going |  | Nguyen Phan Xuan Huy
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## HuynhTrongKhang
Admission System Project
Report date: 9/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Huynh Trong Khang
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Update dictionary-list interface |  | 2014-09-03 | 2014-10-03 | Done |  | Huynh Trong Khang
2 | Login with session on SpringMVC |  | 2014-09-03 | 2014-10-03 | On-going |  | Huynh Trong Khang
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Update dictionary-list interface |  | 2014-11-03 |  |  |  | Huynh Trong Khang
2 | Research and implements send mail on SpringMVC |  | 2014-12-03 |  |  |  | Huynh Trong Khang
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## TaNgocThienPhu
Admission System Project
Report date: 11/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Ta Ngoc Thien Phu
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | design database intranet | Medium | 2014-09-03 | 2014-09-03 | Done |  | Ta Ngoc Thien Phu
2 | Coding load list-question from db |  | 2014-09-03 | 2014-09-03 | On-going |  | Ta Ngoc Thien Phu
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Coding load list-question from db |  | 2014-11-03 |  |  |  | Ta Ngoc Thien Phu
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Team member
No | Team member
1 | Le Ngoc Chau
2 | Khau Thanh Dao
3 | Ngo Quang Huy
4 | Nguyen Phan Xuan Huy
5 | Huynh Trong Khang
6 | Ta Ngoc Thien Phu