## LeNgocChau
Admission System Project
Report date: 2/4/2014 |  |  | Phase: Daily report sprint 2
Reporter: Le Ngoc Chau
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Test - move to dictionaty | Medium | 31/03/2014 | 31/03/2014 | On-going |  | Le Ngoc Chau
2 | Test - edit show items in dictionary | Medium | 31/03/2014 | 31/03/2014 | On-going |  | Le Ngoc Chau
3 | Test - config sent mail | Medium | 31/03/2014 | 31/03/2014 | On-going |  | Le Ngoc Chau
4 | Test - user management | Medium | 31/03/2014 | 31/03/2014 | On-going |  | Le Ngoc Chau
5 | Integration test | Medium | 31/03/2014 | 31/03/2014 | On-going |  | Le Ngoc Chau
Plan for next days
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## KhauThanhDao
Admission System Project
Report date: 2/4/2014 |  |  | Phase: Daily report sprint 2
Reporter: Khau Thanh Dao
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Implement - Paggination iin DMS | Medium | 31/3/2014 | 31/3/2014 | On-going |  | Khau Thanh Dao
2 | User management | High | 31/3/2014 | 31/3/2014 | On-going |  | Khau Thanh Dao
3 | Implement - Update index | High | 31/3/2014 | 31/3/2014 | On-going |  | Khau Thanh Dao
4 | Test - Update index | Low | 31/3/2014 | 31/3/2014 | On-going |  | Khau Thanh Dao
5 | Test - Web service - Receive question from DDS | Low | 31/3/2014 | 31/3/2014 | On-going |  | Khau Thanh Dao
6 | Implement - Config sent mail | High | 31/3/2014 | 31/3/2014 | On-going |  | Khau Thanh Dao
7
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1 | Hard to config send mail
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## NgoQuangHuy
Admission System Project
Report date: 2/4/2014 |  |  | Phase: Daily report sprint 2
Reporter: Ngo Quang Huy
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Test - Search in DMS | Low | 31/03/2014 | 31/03/2014 | On-going |  | Ngo Quang Huy
2 | Test - show list question | Low | 31/03/2014 | 31/03/2014 | On-going |  | Ngo Quang Huy
3 | Test - view detail of question | Low | 31/03/2014 | 31/03/2014 | On-going |  | Ngo Quang Huy
4 | Test - create question | Low | 31/03/2014 | 31/03/2014 | On-going |  | Ngo Quang Huy
5 | Test Web service - sent question to DMS | Low | 31/03/2014 | 31/03/2014 | On-going |  | Ngo Quang Huy
6 | Test - state of dictionary | Low | 31/03/2014 | 31/03/2014 | On-going |  | Ngo Quang Huy
7 | Detail design DDS - android app | High | 2014-01-04 | 2014-01-04 | On-going |  | Ngo Quang Huy
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## NguyenPhanXuanHuy
Admission System Project
Report date: 2/4/2014 |  |  | Phase: Daily report sprint 2
Reporter: Nguyen Phan Xuan Huy
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Implement - view detail of question | Medium | 31/03/2014 | 31/03/2014 | On-going |  | Nguyen Phan Xuan Huy
2 | Web service - sent question to DMS | High | 31/03/2014 | 31/03/2014 | Done |  | Nguyen Phan Xuan Huy
3 | Test - search in DMS | Low | 2014-01-04 | 2014-01-04 | On-going |  | Nguyen Phan Xuan Huy
4 | Test - update dictionary | Low | 2014-01-04 | 2014-01-04 | On-going |  | Nguyen Phan Xuan Huy
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## HuynhTrongKhang
Admission System Project
Report date: 2/4/2014 |  |  | Phase: Daily report sprint 2
Reporter: Huynh Trong Khang
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Test - Tạo index | High | 31/03/2014 | 31/03/2014 | On-going |  | Huynh Trong Khang
2 | Implement integration | Medium | 31/03/2014 | 31/03/2014 | On-going |  | Huynh Trong Khang
3 | Test - Web service - move list question to DDS | Low | 31/03/2014 | 31/03/2014 | On-going |  | Huynh Trong Khang
4 | Test - delete more question | Medium | 31/03/2014 | 31/03/2014 | On-going |  | Huynh Trong Khang
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## TaNgocThienPhu
Admission System Project
Report date: 2/4/2014 |  |  | Phase: Daily report sprint 2
Reporter: Ta Ngoc Thien Phu
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Test - move more question to dictionary | Low | 2014-01-04 | 2014-01-04 | On-going |  | Ta Ngoc Thien Phu
2
3
4
Plan for next days
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Team member
No | Team member
1 | Le Ngoc Chau
2 | Khau Thanh Dao
3 | Ngo Quang Huy
4 | Nguyen Phan Xuan Huy
5 | Huynh Trong Khang
6 | Ta Ngoc Thien Phu
Low
Medium
High