## LeNgocChau
Admission System Project
Report date: 4/4/2014 |  |  | Phase: Daily report sprint 2
Reporter: Le Ngoc Chau
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Prototype for DDS - android app | High | 2014-02-04 | 2014-02-04 | Done |  | Le Ngoc Chau
2 | Implement - File config | High | 2014-02-04 | 2014-02-04 | On-going |  | Le Ngoc Chau
3 | Implement - remove question in dictionary | Medium | 2014-02-04 | 2014-02-04 | On-going |  | Le Ngoc Chau
4
Plan for next days
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1 | hard to research config file
The most significance knowledge gained last week
# | Description
1
2
3

## KhauThanhDao
Admission System Project
Report date: 4/4/2014 |  |  | Phase: Daily report sprint 2
Reporter: Khau Thanh Dao
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | User management | High | 2014-02-04 | 2014-02-04 | On-going |  | Khau Thanh Dao
2 | Web serivce - sent index | High | 2014-03-04 | 2014-03-04 | On-going |  | Khau Thanh Dao
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## NgoQuangHuy
Admission System Project
Report date: 4/4/2014 |  |  | Phase: Daily report sprint 2
Reporter: Ngo Quang Huy
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Detail design for DDS | High | 2014-03-04 | 2014-03-04 | Done |  | Ngo Quang Huy
2 | Web service - Receiw question for DDS | Medium | 2014-02-04 | 2014-02-04 | Done |  | Ngo Quang Huy
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## NguyenPhanXuanHuy
Admission System Project
Report date: 4/4/2014 |  |  | Phase: Daily report sprint 2
Reporter: Nguyen Phan Xuan Huy
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Test - Web serivce - sent index | Low | 2014-02-04 | 2014-02-04 | On-going |  | Nguyen Phan Xuan Huy
2
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## HuynhTrongKhang
Admission System Project
Report date: 4/4/2014 |  |  | Phase: Daily report sprint 2
Reporter: Huynh Trong Khang
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Implement - move to dictionary | High | 2014-03-04 | 2014-03-04 | On-going |  | Huynh Trong Khang
2
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## TaNgocThienPhu
Admission System Project
Report date: 4/4/2014 |  |  | Phase: Daily report sprint 2
Reporter: Ta Ngoc Thien Phu
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Implement - search in DMS | High | 2014-03-04 | 2014-03-04 | On-going |  | Ta Ngoc Thien Phu
2 | Implement - create question | High | 2014-02-04 | 2014-02-04 | Done |  | Ta Ngoc Thien Phu
3 | Implement - states of dictionary | Medium | 2014-02-04 | 2014-02-04 | Done |  | Ta Ngoc Thien Phu
4
Plan for next days
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Team member
No | Team member
1 | Le Ngoc Chau
2 | Khau Thanh Dao
3 | Ngo Quang Huy
4 | Nguyen Phan Xuan Huy
5 | Huynh Trong Khang
6 | Ta Ngoc Thien Phu