## Schedule
Schedule
Project: Admission system - DeadlineTeam - Mentor: Mr. Bui Minh Phung
Project Change Manager:
Week | Day | Date | Task / Activity | Resource | Expected Work Completion (%) | Actual Work Completion (%) | Completion (%) of week | Note
1 | Thursday | 2013-11-07 | - Project organization and team structuring | Deadline Team | 100% | 80% | 64.81%
|  |  | - Create project plan | Le Ngoc Chau | 100% | 70%
|  |  | - Create master plan | Ngo Quang Huy | 100% | 40%
|  |  | - Kick-off meeting of team | Deadline Team | 100% | 100%
|  |  | - Create risk management plan | Ngo Quang Huy | 100% | 50%
|  |  | - Create change management plan | Khau Thanh Dao | 100% | 45%
|  |  | - Create test management plan | Nguyen Phan Xuan Huy | 100% | 30%
|  |  | - Create communication | Le Ngoc Chau | 100% | 40%
|  |  | - Create configuration document | Ta Ngoc Thien Phu | 100% | 30%
|  |  | - Create measurement plan | Huynh Trong Khang | 100% | 35%
|  |  | - Create team charter | Le Ngoc Chau | 100% | 45%
|  |  | - Create timelog | Le Ngoc Chau | 100% | 45%
| Friday | 2013-11-08 | - kick-off meeting with mentor | Deadline Team | 100% | 100%
| Saturday | 2013-11-09 | - Update project plan | Le Ngoc Chau | 100% | 50%
|  |  | - Update master plan | Ngo Quang Huy | 100% | 50%
|  |  | - Update risk management plan | Ngo Quang Huy | 100% | 65%
|  |  | - Update change management plan | Khau Thanh Dao | 100% | 70%
| Monday | 2013-11-11
| Tuesday | 2013-11-12 | - Team meetings | Deadline Team | 100% | 100%
|  |  | - Update test management plan | Nguyen Phan Xuan Huy | 100% | 50%
|  |  | - Update communication | Le Ngoc Chau | 100% | 80%
|  |  | - Update configuration document | Ta Ngoc Thien Phu | 100% | 95%
|  |  | - Update measurement plan | Huynh Trong Khang | 100% | 75%
|  |  | - Create product backlog | Huynh Trong Khang | 100% | 60%
| Wednesday | 2013-11-13 | - Team meetings | Deadline Team | 100% | 100%
|  |  | - Update team charter | Le Ngoc Chau | 100% | 100%
|  |  | - Update timelog | Le Ngoc Chau | 100% | 80%
2 | Thursday | 2013-11-14 | - Reivew team process | Deadline Team | 100% | 75% | 97%
|  |  | - Meetings with Faculty | Deadline Team | 100% | 100%
| Friday | 2013-11-15 | - Review Spring framework | Deadline Team | 100% | 100%
|  |  | - Review risk management plan | Deadline Team | 100% | 95%
| Saturday | 2013-11-16
| Monday | 2013-11-18 | - Review team process | Deadline Team | 100% | 100%
|  |  | - Develop requirement plan | Huynh Trong Khang | 100% | 100%
|  |  | - Create architectural plan | Ta Ngoc Thien Phu | 100% | 100%
| Tuesday | 2013-11-19 | - Review change management plan | Deadline Team | 100% | 100%
|  |  | - Review test management plan | Deadline Team | 100% | 100%
| Wednesday | 2013-11-20 | - Update team process | Le Ngoc Chau | 100% | 100%
3 | Thursday | 2013-11-21 | - Create architect driver specification | Ta Ngoc Thien Phu | 100% | 75% | 92.7%
|  |  | - Meetings with Faculty | Deadline Team | 100% | 100%
|  |  | - Team meeting | Deadline Team | 100% | 100%
| Friday | 2013-11-22 | - Review ACDM | Deadline Team | 100% | 85%
| Saturday | 2013-11-23 | - Team meetings | Deadline Team | 100% | 100%
| Monday | 2013-11-25
| Tuesday | 2013-11-26 | - Review team process - Review communication plan - Review change management plan - Review risk management plan - Review measurement plan - Review timelog - Review weekly report - Review requirement plan - Review architectural plan - Review template - Review test plan, test case template, test report | Deadline Team | 100% | 97%
|  |  | - Meetings with Faculty | Deadline Team | 100% | 100%
|  |  | - Prepare question list to gather requirement | Deadline Team | 100% | 70%
| Wednesday | 2013-11-27 | - Update architiectural plan | Ta Ngoc Thien Phu | 100% | 100%
|  |  | - Update question list to gather requirement | Huynh Trong Khang | 100% | 100%
4 | Thursday | 2013-11-28 | - Meetings with Faculty | Deadline Team | 100% | 100% | 79.58%
|  |  | - Communicate with customer to gather requirement | Deadline Team | 100% | 100%
|  |  | - Identify entities of product | Deadline Team | 100% | 40%
|  |  | - Identify functional requirement | Deadline Team | 100% | 50%
|  |  | - Identify quality attribute | Deadline Team | 100% | 55%
| Friday | 2013-11-29 | - Update entities of product | Deadline Team | 100% | 70%
|  |  | - Update functional requirement | Deadline Team | 100% | 60%
|  |  | - Update quality attribute | Deadline Team | 100% | 80%
| Saturday | 2013-11-30
| Monday | 2013-12-02 | - Team meetings | Deadline Team | 100% | 100%
| Tuesday | 2013-12-03 | - Trainning spring core | Deadline Team | 100% | 100%
|  |  | - Meetings with Customer | Deadline Team | 100% | 100%
|  |  | - Team meetings | Deadline Team | 100% | 100%
| Wednesday | 2013-12-04
5 | Thursday | 2013-12-05 | - Meetings with Faculty | Deadline Team | 100% | 100% | 85.38%
|  |  | - Team meetings | Deadline Team | 100% | 100%
|  |  | - Create use case for "Article system" | Deadline Team | 100% | 70%
|  |  | - Create use case for "Category" | Deadline Team | 100% | 70%
|  |  | - Create use case for " Dictionary management system & Dictionary display system" | Deadline Team | 100% | 70%
|  |  | - Create use case for " Dictionary management system & Dictionary display system" (andrioid app) | Deadline Team | 100% | 70%
| Friday | 2013-12-06 | - Meetings with Customer | Deadline Team | 100% | 100%
| Saturday | 2013-12-07
| Monday | 2013-12-09 | - Update use case for "Article system" | Deadline Team | 100% | 85%
|  |  | - Update use case for "Category" |  | 100% | 70%
|  |  | - Update use case for " Dictionary management system & Dictionary display system" | Deadline Team | 100% | 100%
|  |  | - Update use case for " Dictionary management system & Dictionary display system" (andrioid app) | Deadline Team | 100% | 100%
| Tuesday | 2013-12-10 | - Update use case for "Article system" | Deadline Team | 100% | 80%
|  |  | - Update use case for "Category" | Deadline Team | 100% | 95%
| Wednesday | 2013-12-11
6 | Thursday | 2013-12-12 | - Meetings with Faculty | Deadline Team | 100% | 100% | 95.56%
|  |  | - Identify vision and scope project | Deadline Team | 100% | 85%
| Friday | 2013-12-13 | - Update use case for "Article system" | Deadline Team | 100% | 90%
|  |  | - Update use case for "Category" | Deadline Team | 100% | 85%
| Saturday | 2013-12-14 | - Training code | Deadline Team | 100% | 100%
| Monday | 2013-12-16 | - Update use case for " Dictionary management system & Dictionary display system" | Deadline Team | 100% | 100%
| Tuesday | 2013-12-17 | - Update use case for " Dictionary management system & Dictionary display system" (andrioid app) | Deadline Team | 100% | 100%
|  |  | - Training code | Deadline Team | 100% | 100%
| Wednesday | 2013-12-18 | - Update use case for " Dictionary management system & Dictionary display system" (andrioid app) | Deadline Team | 100% | 100%
7 | Thursday | 2013-12-19 | - Meetings with Faculty | Deadline Team | 100% | 100% | 77.88%
|  |  | - Team meetings | Deadline Team | 100% | 100%
|  |  | - Update use case for "Article system" | Deadline Team | 100% | 79%
|  |  | - Update use case for "Category" | Deadline Team | 100% | 45%
| Friday | 2013-12-20 | - Update use case for " Dictionary management system & Dictionary display system" | Deadline Team | 100% | 79%
| Saturday | 2013-12-21 | - Update use case for " Dictionary management system & Dictionary display system" (andrioid app) | Deadline Team | 100% | 85%
| Monday | 2013-12-23 | - Update use case for " Dictionary management system & Dictionary display system" (andrioid app) | Deadline Team | 100% | 35%
| Tuesday | 2013-12-24 | - Training code | Deadline Team | 100% | 100%
| Wednesday | 2013-12-25
8 | Thursday | 2013-12-26 | - Meetings with Faculty | Deadline Team | 100% | 100% | 74.38%
|  |  | - Team meetings | Deadline Team | 100% | 100%
| Friday | 2013-12-27
| Saturday | 2013-12-28
| Monday | 2013-12-30 | - Team meeting (Baseline requirement) | Deadline Team | 100% | 90%
| Tuesday | 2013-12-31 | - Meetings with Customer | Deadline Team | 100% | 100%
|  |  | - Define system context | Deadline Team | 100% | 60%
|  |  | - Develop overal physical view for admission system (high level) | Deadline Team | 100% | 65%
|  |  | - Develop overal static view for admission system (high level) | Deadline Team | 100% | 40%
|  |  | - Develop overal dynamic view for admission system (high level) | Deadline Team | 100% | 40%
| Wednesday | 2014-01-01
9 | Thursday | 2014-01-02 | -Meetings with Faculty | Deadline Team | 100% | 100% | 57.5%
|  |  | - Team meetings | Deadline Team | 100% | 100%
| Friday | 2014-01-03
| Saturday | 2014-01-04
| Monday | 2013-01-06 | - Mapping physical with dynamic | Ta Ngoc Thien Phu | 100% | 70%
|  |  | - Mapping static with dynamic | Ta Ngoc Thien Phu | 100% | 75%
| Tuesday | 2013-01-07 | - Evaluate architect and design for admission system | Deadline Team | 100% | 0%
| Wednesday | 2013-01-08 | - Update evaluate architect and design for admission system document | Deadline Team | 100% | 0%
10 | Thursday | 2013-01-09 | - Meetings with Faculty | Deadline Team | 100% | 100% | 60%
|  |  | - Review evaluate architect and design for admission system document | Deadline Team | 100% | 0%
| Friday | 2013-01-10 | - Review architect and design with Mr.Quang | Deadline Team | 100% | 0%
| Saturday | 2013-01-11
| Monday | 2013-01-13
| Tuesday | 2013-01-14 | - Review architect and design with Mr.Quang | Deadline Team | 100% | 100%
|  |  | - Team meetings | Deadline Team | 100% | 100%
| Wednesday | 2013-01-15
11 | Thursday | 2013-01-16 | - Meetings with Faculty | Deadline Team | 100% | 100% | 50%
|  |  | - Team meetings | Deadline Team | 100% | 0%
| Friday | 2013-01-17 | - Review architect and design with Mr.Quang | Deadline Team | 100% | 100%
| Saturday | 2013-01-18 | - Update architecture design | Deadline Team | 100% | 40%
| Monday | 2013-01-20 | - Update architecture design | Deadline Team | 100% | 20%
| Tuesday | 2013-01-21 | - Meetings with Customer | Deadline Team | 100% | 100%
|  |  | - Update architecture design | Deadline Team | 100% | 35%
| Wednesday | 2013-01-22 | - Update architecture design | Deadline Team | 100% | 5%
12 | Thursday | 2013-01-23 | - Review architecture design | Deadline Team | 100% | 100% | 45%
| Friday | 2013-01-24 | - Create sprint backlog | Ngo Quang Huy | 100% | 80%
| Saturday | 2013-01-25 | - Review sprint backlog | Deadline Team | 100% | 90%
| Monday | 2013-01-27 | - Tet holiday | Deadline Team | 0% | 0%
| Tuesday | 2013-01-28 | - Tet holiday | Deadline Team | 0% | 0%
| Wednesday | 2013-01-29 | - Tet holiday | Deadline Team | 0% | 0%
13 | Thursday | 2013-01-30 | - Tet holiday | Deadline Team | 0% | 0% | 0%
| Friday | 2013-01-31 | - Tet holiday | Deadline Team | 0% | 0%
| Saturday | 2013-02-01 | - Tet holiday | Deadline Team | 0% | 0%
| Monday | 2013-02-03 | - Tet holiday | Deadline Team | 0% | 0%
| Tuesday | 2013-02-04 | - Tet holiday | Deadline Team | 0% | 0%
| Wednesday | 2013-02-05 | - Tet holiday | Deadline Team | 0% | 0%
14 | Thursday | 2013-02-06 | - Tet holiday | Deadline Team | 0% | 0% | 20%
| Friday | 2013-02-07 | - Tet holiday | Deadline Team | 0% | 0%
| Saturday | 2013-02-08 | - Tet holiday | Deadline Team | 0% | 0%
| Monday | 2013-02-10
| Tuesday | 2013-02-11 | - Meetings with Customer | Deadline Team | 100% | 80%
| Wednesday | 2013-02-12
15 | Thursday | 2013-02-13 | - Meetings with Faculty | Deadline Team | 100% | 0% | 71.44%
|  |  | - Team meetings | Deadline Team | 100% | 100%
|  |  | - Update architecture design | Deadline Team | 100% | 70%
| Friday | 2013-02-14 | - Update architecture design | Deadline Team | 100% | 75%
| Saturday | 2013-02-15 | - Update architecture design | Deadline Team | 100% | 40%
| Monday | 2013-02-17 | - Update architecture design | Deadline Team | 100% | 78%
| Tuesday | 2013-02-18 | - Team meetings | Deadline Team | 100% | 100%
|  |  | - Meeting with Customer | Deadline Team | 100% | 100%
| Wednesday | 2013-02-19 | - Update architecture design | Deadline Team | 100% | 80%
16 | Thursday | 2013-02-20 | - Meetings with Faculty | Deadline Team | 100% | 100% | 75.33%
|  |  | - Team meeting | Deadline Team | 100% | 100%
| Friday | 2013-02-21 | - Update architecture design | Deadline Team | 100% | 40%
| Saturday | 2013-02-22 | - Update architecture design | Deadline Team | 100% | 65%
| Monday | 2013-02-24 | - Update architecture design | Deadline Team | 100% | 80%
| Tuesday | 2013-02-25 | - Team meeting | Deadline Team | 100% | 100%
| Wednesday | 2013-02-26 | - Update architecture design | Deadline Team | 100% | 84%
|  |  | - Update architecture design | Deadline Team | 100% | 33%
|  |  | - Update architecture design | Deadline Team | 100% | 76%
17 | Thursday | 2013-02-27 | - Meetings with Faculty | Deadline Team | 100% | 100% | 52.5%
|  |  | - Team meeting | Deadline Team | 100% | 100%
| Friday | 2013-02-28 | - Update architecture design | Deadline Team | 100% | 45%
| Saturday | 2013-03-01 | - Update architecture design | Deadline Team | 100% | 45%
| Monday | 2013-03-03 | - Update architecture design | Deadline Team | 100% | 70%
| Tuesday | 2013-03-04 | - Meetings with Customer | Deadline Team | 100% | 0%
|  |  | - Team meeting | Deadline Team | 100% | 80%
|  |  | - Login Prototype | Khau Thanh Dao | 100% | 30%
|  |  | - List-unanswer Prototype | Ngo Quang Huy | 100% | 20%
| Wednesday | 2013-03-05 | - List-TempSave Prototype | Le Ngoc Chau | 100% | 45%
|  |  | -List-Saved Prototype | Ta Ngoc Thien Phu | 100% | 45%
|  |  | - List-Dict Prototype | Huynh Trong Khang | 100% | 50%
18 | Thursday | 2013-03-06 | - Meetings with Faculty | Deadline Team | 100% | 100% | 73.38%
|  |  | - Team meeting (Daily meeting 1 for sprint 1) | Deadline Team | 100% | 100%
|  |  | - Meetings with Customer | Deadline Team | 100% | 90%
|  |  | - Detail design for DMS | Ta Ngoc Thien Phu | 100% | 50%
|  |  | - Write test case | Nguyen Phan Xuan Huy | 100% | 40%
| Friday | 2013-03-07 | - Team meeting (Daily meeting 2 for sprint 1) | Deadline Team | 100% | 100%
|  |  | - Design database intranet | Ta Ngoc Thien Phu | 100% | 100%
|  |  | - Login Prototype | Khau Thanh Dao | 100% | 90%
|  |  | - List-unanswer Prototype | Ngo Quang Huy | 100% | 98%
|  |  | - List-TempSave Prototype | Le Ngoc Chau | 100% | 80%
|  |  | -List-Saved Prototype | Ta Ngoc Thien Phu | 100% | 85%
|  |  | - Update test case | Nguyen Phan Xuan Huy | 100% | 45%
|  |  | - List-Dict Prototype | Huynh Trong Khang | 100% | 97%
| Saturday | 2013-03-08 | - Implement database intranet | Ngo Quang Huy | 100% | 100%
|  |  | - Update prototype | Le Ngoc Chau | 100% | 70%
|  |  | - Implement - Show list Q/A | Ta Ngoc Thien Phu | 100% | 60%
|  |  | - Implement - Send answer | Khau Thanh Dao | 100% | 40%
|  |  | - Implement - View Q/A | Huynh Trong Khang | 100% | 55%
|  |  | - Update test case into tfs | Nguyen Phan Xuan Huy | 100% | 64%
| Monday | 2013-03-10 | - Team meeting (Daily meeting 3 for sprint 1) | Deadline Team | 100% | 100%
|  |  | - User management | Khau Thanh Dao | 100% | 10%
|  |  | - Implement - Show list Q/A | Ta Ngoc Thien Phu | 100% | 100%
|  |  | - Implement - search Q/A | Le Ngoc Chau | 100% | 60%
|  |  | - Implement - View Q/A | Huynh Trong Khang | 100% | 80%
|  |  | - Implement - View user profile | Ngo Quang Huy | 100% | 90%
|  |  | - Implement - Save answer | Nguyen Phan Xuan Huy | 100% | 42%
| Tuesday | 2013-03-11 | - Implement - Send answer | Khau Thanh Dao | 100% | 80%
|  |  | - Implement - Save answer | Nguyen Phan Xuan Huy | 100% | 55%
|  |  | - Implement - insert dict | Huynh Trong Khang | 100% | 60%
|  |  | - Implement - Login/log out for dictionaty | Ngo Quang Huy | 100% | 50%
|  |  | - Implement - search Q/A | Le Ngoc Chau | 100% | 65%
|  |  | - Implement - Delete Q/A | Ta Ngoc Thien Phu | 100% | 79%
| Wednesday | 2013-03-12 | - Implement - Send answer | Khau Thanh Dao | 100% | 87%
|  |  | - Implement - Save answer | Nguyen Phan Xuan Huy | 100% | 76%
|  |  | - Implement - insert dict | Huynh Trong Khang | 100% | 88%
|  |  | - Implement - Login/log out for dictionaty | Ngo Quang Huy | 100% | 68%
|  |  | - Implement - search Q/A | Le Ngoc Chau | 100% | 65%
|  |  | - Implement - Create index | Khau Thanh Dao | 100% | 30%
|  |  | - Implement - Regist page | Ta Ngoc Thien Phu | 100% | 96%
|  |  | - Team meeting (Daily meeting 4 for sprint 1) | Deadline Team | 100% | 90%
19 | Thursday | 2013-03-13 | - Meetings with Faculty | Deadline Team | 100% | 100% | 73.02%
|  |  | - Team meetings | Deadline Team | 100% | 100%
|  |  | - Implement - search Q/A | Le Ngoc Chau | 100% | 70%
|  |  | - Implement - Create index | Khau Thanh Dao | 100% | 20%
|  |  | - Implement - Drop dict | Huynh Trong Khang | 100% | 70%
|  |  | - Test - Regist page | Ta Ngoc Thien Phu | 100% | 82%
|  |  | - Test - Login/log out for DMS | Nguyen Phan Xuan Huy | 100% | 84%
|  |  | - Test - Tìm kiếm | Nguyen Phan Xuan Huy | 100% | 70%
|  |  | - Test - Show list Q/A | Ngo Quang Huy | 100% | 90%
| Friday | 2013-03-14 | - Team meeting (Daily meeting 5 for sprint 1) | Deadline Team | 100% | 100%
|  |  | - Implement - Create index | Khau Thanh Dao | 100% | 25%
|  |  | - Implement - Drop dict | Huynh Trong Khang | 100% | 80%
|  |  | - Implement - captcha | Huynh Trong Khang | 100% | 50%
|  |  | - Update interface | Le Ngoc Chau | 100% | 90%
|  |  | - Implement - Change password | Le Ngoc Chau | 100% | 87%
|  |  | - Test - View Q/A | Ngo Quang Huy | 100% | 90%
|  |  | - Test - insert dict | Ngo Quang Huy | 100% | 87%
|  |  | - Test - Send answer | Nguyen Phan Xuan Huy | 100% | 90%
|  |  | - Test - Save answer | Nguyen Phan Xuan Huy | 100% | 91%
|  |  | - Test - captcha | Ta Ngoc Thien Phu | 100% | 70%
|  |  | - Fix bug | Ta Ngoc Thien Phu | 100% | 79%
| Saturday | 2013-03-15 | - Fix bug | Ta Ngoc Thien Phu | 100% | 65%
|  |  | - Implement - create Question | Huynh Trong Khang | 100% | 40%
|  |  | - Implement - Create index | Khau Thanh Dao | 100% | 31%
|  |  | - Implement - Update index | Khau Thanh Dao | 100% | 45%
| Monday | 2013-03-17 | - Team meeting (Daily meeting 6 for sprint 1) | Deadline Team | 100% | 100%
|  |  | - Implement - add sessions page | Khau Thanh Dao | 100% | 70%
|  |  | - Implement - Paggination | Khau Thanh Dao | 100% | 80%
|  |  | - Implement - Change password | Le Ngoc Chau | 100% | 89%
|  |  | - Implement - Create Question | Huynh Trong Khang | 100% | 72%
|  |  | - Implement - Checkbox list Q/A | Huynh Trong Khang | 100% | 85%
|  |  | - Integration code | Ta Ngoc Thien Phu | 100% | 84%
|  |  | - Test - View Q/A | Ngo Quang Huy | 100% | 88%
|  |  | - Test - insert dict | Ngo Quang Huy | 100% | 64%
|  |  | - Test - Send answer | Nguyen Phan Xuan Huy | 100% | 87%
| Tuesday | 2013-03-18 | - Team meeting | Deadline Team | 100% | 100%
|  |  | - Implement - Create index | Khau Thanh Dao | 100% | 40%
|  |  | - Implement - Update index | Khau Thanh Dao | 100% | 45%
|  |  | - Implement - show loading page | Huynh Trong Khang | 100% | 100%
|  |  | - Implement - captcha | Huynh Trong Khang | 100% | 40%
|  |  | - Test - Login/log out for DMS | Nguyen Phan Xuan Huy | 100% | 77%
|  |  | - Test - Tìm kiếm | Nguyen Phan Xuan Huy | 100% | 70%
|  |  | - Test - Send answer | Nguyen Phan Xuan Huy | 100% | 80%
|  |  | - Test - Save answer | Nguyen Phan Xuan Huy | 100% | 75%
|  |  | - Fix bug | Ta Ngoc Thien Phu | 100% | 90%
|  |  | - Test - Show list Q/A | Ngo Quang Huy | 100% | 100%
|  |  | - Test - View Q/A | Ngo Quang Huy | 100% | 92%
|  |  | - Test - insert dict | Ngo Quang Huy | 100% | 72%
| Wednesday | 2013-03-19 | - Team meeting (Daily meeting 7 for sprint 1) | Deadline Team | 100% | 100%
|  |  | - Update interface | Le Ngoc Chau | 100% | 87%
|  |  | - Test - Create index | Le Ngoc Chau | 100% | 50%
|  |  | - Test - Update index | Le Ngoc Chau | 100% | 30%
|  |  | - Fix bug | Ta Ngoc Thien Phu | 100% | 75%
|  |  | - Implement - Create index | Khau Thanh Dao | 100% | 33%
|  |  | - Implement - Update index | Khau Thanh Dao | 100% | 73%
|  |  | - Implement - Paggination | Khau Thanh Dao | 100% | 75%
|  |  | - Implement - captcha | Huynh Trong Khang | 100% | 30%
|  |  | - Implement - create Question | Huynh Trong Khang | 100% | 55%
|  |  | - Test - Paggination | Huynh Trong Khang | 100% | 70%
|  |  | - Test - show loading page | Huynh Trong Khang | 100% | 100%
|  |  | - Test - Checkbox list Q/A | Ngo Quang Huy | 100% | 88%
|  |  | - Update test case | Nguyen Phan Xuan Huy | 100% | 55%
20 | Thursday | 2013-03-20 | - Meetings with Faculty | Deadline Team | 100% | 0% | 60.51%
|  |  | - Team meetings | Deadline Team | 100% | 0%
|  |  | - Update interface | Le Ngoc Chau | 100% | 50%
|  |  | - Fig bug | Ta Ngoc Thien Phu | 100% | 80%
|  |  | - Implement - Create index | Khau Thanh Dao | 100% | 45%
|  |  | - Implement - Update index | Khau Thanh Dao | 100% | 50%
|  |  | - Implement - captcha | Huynh Trong Khang | 100% | 45%
|  |  | - Update test case & test plan | Nguyen Phan Xuan Huy | 100% | 70%
|  |  | - Update product backlog | Ngo Quang Huy | 100% | 95%
| Friday | 2013-03-21 | - Team meeting (Daily meeting 8 for sprint 1) | Deadline Team | 100% | 100%
|  |  | - Update interface | Le Ngoc Chau | 100% | 90%
|  |  | - Fix bug | Ta Ngoc Thien Phu | 100% | 85%
|  |  | - Implement - Create index | Khau Thanh Dao | 100% | 45%
|  |  | - Implement - Update index | Khau Thanh Dao | 100% | 50%
|  |  | - Implement - captcha | Huynh Trong Khang | 100% | 45%
|  |  | - Update test case & test plan | Nguyen Phan Xuan Huy | 100% | 70%
|  |  | - Update sprint backlog | Ngo Quang Huy | 100% | 95%
|  |  | - Update daily meeting | Ngo Quang Huy | 100% | 100%
| Saturday | 2013-03-22 | - Implement - Create index | Khau Thanh Dao | 100% | 45%
|  |  | - Implement - Update index | Khau Thanh Dao | 100% | 50%
|  |  | - Implement - captcha | Huynh Trong Khang | 100% | 45%
|  |  | - Implement - insert dict | Huynh Trong Khang | 100% | 40%
|  |  | - Implement - search Q/A | Le Ngoc Chau | 100% | 55%
|  |  | - Fix bug | Ta Ngoc Thien Phu | 100% | 85%
| Monday | 2013-03-24 | - Team meeting (Daily meeting 9 for sprint 1) | Deadline Team | 100% | 100%
| Tuesday | 2013-03-25 | - Meetings with Customer | Deadline Team | 100% | 100%
|  |  | - Team meeting (close sprint 1) | Deadline Team | 100% | 98%
|  |  | - Implement - Create index | Khau Thanh Dao | 100% | 30%
|  |  | - Implement - Update index | Khau Thanh Dao | 100% | 55%
|  |  | - Implement - captcha | Huynh Trong Khang | 100% | 20%
|  |  | - Implement - insert dict | Huynh Trong Khang | 100% | 40%
|  |  | - Update product backlog & sprint backlog | Ngo Quang Huy | 100% | 90%
|  |  | - Test functional | Nguyen Phan Xuan Huy | 100% | 50%
|  |  | - Fix bug | Ta Ngoc Thien Phu | 100% | 100%
| Wednesday | 2013-03-26 | - User management | Khau Thanh Dao | 100% | 5%
|  |  | - Implement - Paggination of DMS | Khau Thanh Dao | 100% | 85%
|  |  | - Implement - Create question on DMS | Huynh Trong Khang | 100% | 50%
|  |  | - Implement - Insert-Dict | Huynh Trong Khang | 100% | 65%
|  |  | - Implement - Update index | Ta Ngoc Thien Phu | 100% | 45%
|  |  | - Update interface | Le Ngoc Chau | 100% | 90%
|  |  | - Test - Insert-Dict | Le Ngoc Chau | 100% | 70%
|  |  | - Test - Search Q/A of DMS | Ngo Quang Huy | 100% | 60%
|  |  | - Web service - Receive question from DDS | Ngo Quang Huy | 100% | 10%
|  |  | - Implement - DDS's view detail Q/A | Nguyen Phan Xuan Huy | 100% | 30%
|  |  | - Team meeting (start sprint 2) | Deadline Team | 100% | 95%
21 | Thursday | 2013-03-27 | - Meetings with Faculty | Deadline Team | 100% | 100% | 59.74%
|  |  | - Team meeting | Deadline Team | 100% | 100%
|  |  | - User management | Khau Thanh Dao | 100% | 0%
|  |  | - Test - Update index | Khau Thanh Dao | 100% | 5%
|  |  | - Web serivce - Send index | Khau Thanh Dao | 100% | 60%
|  |  | - Update interface | Le Ngoc Chau | 100% | 80%
|  |  | - Prototype for DDS | Le Ngoc Chau | 100% | 90%
|  |  | - Implement - show Q/A | Ta Ngoc Thien Phu | 100% | 70%
|  |  | - Implement - DDS's Search Q/A | Ta Ngoc Thien Phu | 100% | 50%
|  |  | - DDS's Detail design | Ngo Quang Huy | 100% | 83%
|  |  | - Write test case | Nguyen Phan Xuan Huy | 100% | 50%
| Friday | 2013-03-28 | - Team meeting (Daily meeting 1 for sprint 2) | Deadline Team | 100% | 100%
|  |  | - User management | Khau Thanh Dao | 100% | 0%
|  |  | - Web serivce - Send index | Khau Thanh Dao | 100% | 65%
|  |  | - Prototype for DDS | Le Ngoc Chau | 100% | 95%
|  |  | - Implements- Configure system | Huynh Trong Khang | 100% | 50%
|  |  | - Implement - DDS's Search Q/A | Ta Ngoc Thien Phu | 100% | 90%
|  |  | - Update test case | Nguyen Phan Xuan Huy | 100% | 80%
|  |  | - Web service - Send question to DMS | Nguyen Phan Xuan Huy | 100% | 20%
|  |  | - Test - show Q/A | Ngo Quang Huy | 100% | 30%
|  |  | - Test - DDS's view detail Q/A | Ngo Quang Huy | 100% | 30%
| Saturday | 2013-03-29 | - User management | Khau Thanh Dao | 100% | 0%
|  |  | - Web serivce - Send index | Khau Thanh Dao | 100% | 80%
|  |  | - Update interface | Le Ngoc Chau | 100% | 85%
|  |  | - Implement - Update dictionary | Le Ngoc Chau | 100% | 15%
|  |  | - Implement - Create question | Ta Ngoc Thien Phu | 100% | 70%
|  |  | - Implement - Status of Dictionary page | Ta Ngoc Thien Phu | 100% | 54%
|  |  | - Implements- Configure system | Huynh Trong Khang | 100% | 80%
|  |  | - Web service - Send question to DMS | Nguyen Phan Xuan Huy | 100% | 30%
|  |  | - Implement - Create index | Ngo Quang Huy | 100% | 30%
|  |  | - Test - Search Q/A of DMS | Ngo Quang Huy | 100% | 70%
| Monday | 2013-03-31 | - Team meeting (Daily meeting 2 for sprint 2) | Deadline Team | 100% | 100%
|  |  | - Update interface | Le Ngoc Chau | 100% | 90%
|  |  | - Implement - Update dictionary | Le Ngoc Chau | 100% | 80%
|  |  | - Implement - Config : centralization & dispersal | Le Ngoc Chau | 100% | 20%
|  |  | - User management | Khau Thanh Dao | 100% | 40%
|  |  | - Test - Update index | Khau Thanh Dao | 100% | 35%
|  |  | - Implement - Paggination of DMS | Khau Thanh Dao | 100% | 90%
|  |  | - Test - Create question | Ngo Quang Huy | 100% | 30%
|  |  | - Web service - Receive question from DDS | Ngo Quang Huy | 100% | 20%
|  |  | - Web service - Send question to DMS | Nguyen Phan Xuan Huy | 100% | 25%
|  |  | - Implement - Create question on DMS | Huynh Trong Khang | 100% | 85%
|  |  | - Implement - Create question | Ta Ngoc Thien Phu | 100% | 75%
|  |  | - Implement - Status of Dictionary page | Ta Ngoc Thien Phu | 100% | 70%
| Tuesday | 2013-04-01 | - Team meeting | Deadline Team | 100% | 50%
|  |  | - Implement - Config : centralization & dispersal | Le Ngoc Chau | 100% | 75%
|  |  | - Test - Status of Dictionary page | Le Ngoc Chau | 100% | 75%
|  |  | - Test - Configure mail | Le Ngoc Chau | 100% | 60%
|  |  | - Test - usermanagement | Le Ngoc Chau | 100% | 20%
|  |  | - Update interface | Le Ngoc Chau | 100% | 85%
|  |  | - User management | Khau Thanh Dao | 100% | 0%
|  |  | - Web serivce - Send index | Khau Thanh Dao | 100% | 60%
|  |  | - Web service - Receive question from DDS | Ngo Quang Huy | 100% | 60%
|  |  | - Web service - Send question to DMS | Nguyen Phan Xuan Huy | 100% | 45%
|  |  | - Implement - Insert-Dict | Huynh Trong Khang | 100% | 75%
|  |  | - Implement - DDS's Search Q/A | Ta Ngoc Thien Phu | 100% | 85%
| Wednesday | 2013-04-02 | - Team meeting (Daily meeting 3 for sprint 2) | Deadline Team | 100% | 100%
|  |  | - Test - Status of Dictionary page | Le Ngoc Chau | 100% | 82%
|  |  | - Test - Configure mail | Le Ngoc Chau | 100% | 78%
|  |  | - Test - usermanagement | Le Ngoc Chau | 100% | 25%
|  |  | - Implement - Config : centralization & dispersal | Le Ngoc Chau | 100% | 5%
|  |  | - Deploy-DMS | Khau Thanh Dao | 100% | 90%
|  |  | - Deploy- DDS | Khau Thanh Dao | 100% | 90%
|  |  | - Web service - Receive question from DDS | Ngo Quang Huy | 100% | 45%
|  |  | - Implement - DDS's view detail Q/A | Nguyen Phan Xuan Huy | 100% | 55%
|  |  | - Implement - Refine items | Huynh Trong Khang | 100% | 80%
|  |  | - Implement - Configure mail | Huynh Trong Khang | 100% | 90%
|  |  | - Implement - DDS's Search Q/A | Ta Ngoc Thien Phu | 100% | 70%
|  |  | - Implement - Search Q/A of DMS | Ta Ngoc Thien Phu | 100% | 100%
22 | Thursday | 2013-04-03 | - Meetings with Faculty | Deadline Team | 100% | 100% | 53.72%
|  |  | - Team meeting | Deadline Team | 100% | 100%
|  |  | - Update interface | Le Ngoc Chau | 100% | 45%
|  |  | - Implement - Config : centralization & dispersal | Le Ngoc Chau | 100% | 20%
|  |  | - User management | Khau Thanh Dao | 100% | 10%
|  |  | - Web serivce - Send index | Khau Thanh Dao | 100% | 30%
|  |  | - Web service - Receive question from DDS | Ngo Quang Huy | 100% | 35%
|  |  | - Web service - Send question to DDS | Nguyen Phan Xuan Huy | 100% | 60%
|  |  | - Test - Create index | Huynh Trong Khang | 100% | 40%
|  |  | - Implement - show Q/A | Ta Ngoc Thien Phu | 100% | 100%
| Friday | 2013-04-04 | - Team meeting (Daily meeting 4 for sprint 2) | Deadline Team | 100% | 100%
|  |  | - Update interface | Le Ngoc Chau | 100% | 50%
|  |  | - Implement - Config : centralization & dispersal | Le Ngoc Chau | 100% | 20%
|  |  | - User management | Khau Thanh Dao | 100% | 10%
|  |  | - Test - Web service - Receive question from DDS | Khau Thanh Dao | 100% | 80%
|  |  | - Test - show Q/A | Ngo Quang Huy | 100% | 80%
|  |  | - Test - DDS's view detail Q/A | Ngo Quang Huy | 100% | 65%
|  |  | - Test - Create question | Ngo Quang Huy | 100% | 45%
|  |  | - Test Web service - Send question to DMS | Ngo Quang Huy | 100% | 50%
|  |  | - Web service - Send question to DDS | Nguyen Phan Xuan Huy | 100% | 80%
|  |  | - Test - Web serivce - Send index | Nguyen Phan Xuan Huy | 100% | 30%
|  |  | - Test - Delete multi question | Huynh Trong Khang | 100% | 70%
|  |  | - Implement - Update index | Ta Ngoc Thien Phu | 100% | 30%
| Saturday | 2013-04-05
| Monday | 2013-04-07 | - Team meeting (Daily meeting 5 for sprint 2) | Deadline Team | 100% | 100%
|  |  | - Update interface | Le Ngoc Chau | 100% | 70%
|  |  | - Implement - Config : centralization & dispersal | Le Ngoc Chau | 100% | 45%
|  |  | - User management | Khau Thanh Dao | 100% | 30%
|  |  | - Web serivce - Send index | Khau Thanh Dao | 100% | 35%
|  |  | - Update product backlog & sprint backlog | Huynh Trong Khang | 100% | 80%
|  |  | - Test - DDS's Search Q/A | Nguyen Phan Xuan Huy | 100% | 70%
|  |  | - Test - Create index | Huynh Trong Khang | 100% | 50%
|  |  | - Implement - Update index | Ta Ngoc Thien Phu | 100% | 50%
| Tuesday | 2013-04-08 | - Team meeting | Deadline Team | 100% | 80%
|  |  | - Test - Status of Dictionary page | Le Ngoc Chau | 100% | 82%
|  |  | - Test - Configure mail | Le Ngoc Chau | 100% | 78%
|  |  | - Test - usermanagement | Le Ngoc Chau | 100% | 0%
|  |  | - Implement - Config : centralization & dispersal | Le Ngoc Chau | 100% | 15%
|  |  | - User management | Khau Thanh Dao | 100% | 40%
|  |  | - Web serivce - Send index | Khau Thanh Dao | 100% | 25%
|  |  | - Test - Config : centralization & dispersal | Ngo Quang Huy | 100% | 30%
|  |  | - Implement - Delete multi question | Nguyen Phan Xuan Huy | 100% | 50%
|  |  | - Test - Create index | Huynh Trong Khang | 100% | 45%
|  |  | - Implement - Update index | Ta Ngoc Thien Phu | 100% | 45%
| Wednesday | 2013-04-09 | - Update test case | Nguyen Phan Xuan Huy | 100% | 80%
|  |  | - Update interface | Le Ngoc Chau | 100% | 85%
|  |  | - User management | Khau Thanh Dao | 100% | 20%
|  |  | - Sort question | Ta Ngoc Thien Phu | 100% | 70%
23 | Thursday | 2013-04-10 | - Meetings with Faculty | Deadline Team | 100% | 100% | 67.52%
|  |  | - Team meeting | Deadline Team | 100% | 40%
|  |  | - Team meeting (Daily meeting 6 for sprint 2) | Deadline Team | 100% | 100%
|  |  | - Implement - Config : centralization & dispersal | Le Ngoc Chau | 100% | 15%
|  |  | - Deploy-DMS | Khau Thanh Dao | 100% | 85%
|  |  | - Deploy- DDS | Khau Thanh Dao | 100% | 90%
|  |  | - Test - Config : centralization & dispersal | Ngo Quang Huy | 100% | 15%
|  |  | - Implement - Delete multi question | Nguyen Phan Xuan Huy | 100% | 60%
|  |  | - Test - Web service - Send question to DDS | Huynh Trong Khang | 100% | 40%
|  |  | - Fix bug | Ta Ngoc Thien Phu | 100% | 60%
| Friday | 2013-04-11 | - Team meeting (Daily meeting 7 for sprint 2) | Deadline Team | 100% | 100%
|  |  | - Implement - Config : centralization & dispersal | Le Ngoc Chau | 100% | 5%
|  |  | - User management | Khau Thanh Dao | 100% | 55%
|  |  | - Web serivce - Send index | Khau Thanh Dao | 100% | 43%
|  |  | - Test - Update index | Khau Thanh Dao | 100% | 80%
|  |  | - Implement - Delete multi question | Nguyen Phan Xuan Huy | 100% | 70%
|  |  | - Test - Update dictionary | Nguyen Phan Xuan Huy | 100% | 60%
|  |  | - Test - Web service - Send question to DDS | Huynh Trong Khang | 100% | 70%
|  |  | - Fix bug | Ta Ngoc Thien Phu | 100% | 80%
| Saturday | 2013-04-12
| Monday | 2013-04-14 | - Team meeting (Daily meeting 8 for sprint 2) | Deadline Team | 100% | 100%
|  |  | - Test - Update dictionary | Nguyen Phan Xuan Huy | 100% | 80%
|  |  | - Test - Web serivce - Send index | Nguyen Phan Xuan Huy | 100% | 50%
|  |  | - Test - Create index | Huynh Trong Khang | 100% | 55%
|  |  | - Test - Delete multi question | Huynh Trong Khang | 100% | 90%
|  |  | - Fix bug | Ta Ngoc Thien Phu | 100% | 90%
| Tuesday | 2013-04-15 | - Team meetings (close sprint 2) | Deadline Team | 100% | 100%
| Wednesday | 2013-04-16 | - Team meetings (opent sprint 3) | Deadline Team | 100% | 90%
24 | Thursday | 2013-04-17 | - Team meetings with Faculty | Deadline Team | 100% | 100% | 71.9%
|  |  | - Team meeting | Deadline Team | 100% | 75%
|  |  | - User management | Huynh Trong Khang | 100% | 50%
|  |  | - Implement - Update index | Khau Thanh Dao | 100% | 45%
|  |  | - Web serivce - Send index | Ta Ngoc Thien Phu | 100% | 50%
|  |  | - Implement - Config : centralization & dispersal | Le Ngoc Chau | 100% | 20%
|  |  | - Write test case | Nguyen Phan Xuan Huy | 100% | 80%
|  |  | - Update product backlog | Ngo Quang Huy | 100% | 90%
| Friday | 2013-04-18 | - Team meeting (Daily meeting 1 for sprint 3) | Deadline Team | 100% | 100%
|  |  | - Deploy- DMS | Khau Thanh Dao | 100% | 100%
|  |  | - Deploy- DDS | Khau Thanh Dao | 100% | 100%
|  |  | - Implement - Config : centralization & dispersal | Le Ngoc Chau | 100% | 25%
|  |  | - Web serivce - Send index | Ta Ngoc Thien Phu | 100% | 65%
|  |  | - User management | Huynh Trong Khang | 100% | 35%
|  |  | - Test - Update index | Nguyen Phan Xuan Huy | 100% | 80%
|  |  | - Update test case | Nguyen Phan Xuan Huy | 100% | 90%
|  |  | - Implement - Update index | Khau Thanh Dao | 100% | 55%
| Saturday | 2013-04-19 | - Test - Config : centralization & dispersal | Ngo Quang Huy | 100% | 20%
|  |  | - Test - Web serivce - Send index | Nguyen Phan Xuan Huy | 100% | 65%
|  |  | - Test - Update index | Nguyen Phan Xuan Huy | 100% | 85%
|  |  | - Implement - Update index | Khau Thanh Dao | 100% | 50%
|  |  | - Update interface | Le Ngoc Chau | 100% | 70%
|  |  | - Fix bug | Ta Ngoc Thien Phu | 100% | 90%
|  |  | - Implement - Config : centralization & dispersal | Le Ngoc Chau | 100% | 50%
|  |  | - User management | Huynh Trong Khang | 100% | 70%
| Monday | 2013-04-21 | - Team meeting (Daily meeting 2 for sprint 3) | Deadline Team | 100% | 100%
|  |  | - Test - Config : centralization & dispersal | Ngo Quang Huy | 100% | 60%
|  |  | - Test - Web serivce - Send index | Nguyen Phan Xuan Huy | 100% | 65%
|  |  | - Test - Update index | Nguyen Phan Xuan Huy | 100% | 85%
|  |  | - Implement - Update index | Khau Thanh Dao | 100% | 50%
|  |  | - Update interface | Le Ngoc Chau | 100% | 70%
|  |  | - Fix bug | Ta Ngoc Thien Phu | 100% | 90%
|  |  | - Implement - Config : centralization & dispersal | Le Ngoc Chau | 100% | 85%
| Tuesday | 2013-04-22 | - Meeting with Customer | Deadline Team | 100% | 0%
|  |  | - Team meeting | Deadline Team | 100% | 100%
|  |  | - Update interface | Le Ngoc Chau | 100% | 85%
|  |  | - Fix bug | Ta Ngoc Thien Phu | 100% | 95%
|  |  | - User management | Huynh Trong Khang | 100% | 70%
|  |  | - Test - Config : centralization & dispersal | Ngo Quang Huy | 100% | 75%
|  |  | - Test - Web serivce - Send index | Nguyen Phan Xuan Huy | 100% | 80%
|  |  | - Test - Update index | Nguyen Phan Xuan Huy | 100% | 60%
|  |  | - Deploy- DMS | Khau Thanh Dao | 100% | 100%
|  |  | - Deploy- DDS | Khau Thanh Dao | 100% | 100%
| Wednesday | 2013-04-23 | - Team meeting (close sprint 3) | Deadline Team | 100% | 100%
|  |  | - Update interface | Le Ngoc Chau | 100% | 85%
|  |  | - Fix bug | Ta Ngoc Thien Phu | 100% | 95%
|  |  | - User management | Huynh Trong Khang | 100% | 70%
|  |  | - Test - Config : centralization & dispersal | Ngo Quang Huy | 100% | 75%
|  |  | - Test - Web serivce - Send index | Nguyen Phan Xuan Huy | 100% | 80%
|  |  | - Test - Update index | Nguyen Phan Xuan Huy | 100% | 60%
25 | Thursday | 2013-04-24 | - Meetings with Faculty | Deadline Team | 100% | 100% | 70.05%
|  |  | - Team meeting | Deadline Team | 100% | 95%
|  |  | - Team meeting (open sprint 4) | Deadline Team | 100% | 90%
|  |  | - Implement - Login/log out on android | Le Ngoc Chau | 100% | 80%
|  |  | - Web service - search Q/A on Android DDS | Khau Thanh Dao | 100% | 40%
|  |  | - Prototype for android application | Ngo Quang Huy | 100% | 80%
|  |  | - Implement - Update dictionary on Android DMS | Nguyen Phan Xuan Huy | 100% | 15%
|  |  | - Implement - show Q/A on Android DDS | Huynh Trong Khang | 100% | 90%
|  |  | - Implement - Search Q/A on Android DDS | Ta Ngoc Thien Phu | 100% | 80%
| Friday | 2013-04-25 | - Update interface for DMS | Le Ngoc Chau | 100% | 90%
|  |  | - Web service - search Q/A on Android DDS | Khau Thanh Dao | 100% | 50%
|  |  | - Prototype for android application | Ngo Quang Huy | 100% | 80%
|  |  | - Implement - Update dictionary on Android DMS | Nguyen Phan Xuan Huy | 100% | 35%
|  |  | - Implement - View detail Q/A on Android | Huynh Trong Khang | 100% | 95%
|  |  | - Web service - Send Q/A from DDS to Android's DDS | Ta Ngoc Thien Phu | 100% | 69%
| Saturday | 2013-04-26 | - Team meeting (Daily meeting 1 for sprint 4) | Deadline Team | 100% | 100%
|  |  | - Implement - Login/log out on android | Le Ngoc Chau | 100% | 90%
|  |  | - Implement - View Q/A on android | Le Ngoc Chau | 100% | 95%
|  |  | - Web service - search Q/A on Android DDS | Khau Thanh Dao | 100% | 50%
|  |  | - Prototype for android application | Ngo Quang Huy | 100% | 85%
|  |  | - Prototype Android DMS application | Ngo Quang Huy | 100% | 70%
|  |  | - Implement - Show Q/A on android | Nguyen Phan Xuan Huy | 100% | 80%
|  |  | - Implement - Save Q/A on android | Huynh Trong Khang | 100% | 70%
|  |  | - Web service - Send Q/A from DDS to Android's DDS | Ta Ngoc Thien Phu | 100% | 90%
| Monday | 2013-04-28 | - Implement - Create question on Android | Le Ngoc Chau | 100% | 70%
|  |  | - Web service - Search Q/A on Android DDS | Le Ngoc Chau | 100% | 25%
|  |  | - Implement - Send mail on android DMS | Khau Thanh Dao | 100% | 50%
|  |  | - Detail design DDS | Ngo Quang Huy | 100% | 80%
|  |  | - Prototype Android DMS application | Ngo Quang Huy | 100% | 85%
|  |  | - Implement - Show Q/A on android DMS | Nguyen Phan Xuan Huy | 100% | 70%
|  |  | - Implement - Save Q/A on android DMS | Huynh Trong Khang | 100% | 84%
|  |  | - Implement - Search Q/A on Android DMS | Ta Ngoc Thien Phu | 100% | 88%
| Tuesday | 2013-04-29 | - Team meeting (Daily meeting 2 for sprint 4) | Deadline Team | 100% | 100%
|  |  | - Implement - Create question on Android | Le Ngoc Chau | 100% | 85%
|  |  | - Test - Create question | Le Ngoc Chau | 100% | 70%
|  |  | - Web service - Search Q/A on Android DMS | Le Ngoc Chau | 100% | 20%
|  |  | - Implement - Send mail on android DMS | Khau Thanh Dao | 100% | 70%
|  |  | - Detail design DDS | Ngo Quang Huy | 100% | 90%
|  |  | - Detail design DMS | Ngo Quang Huy | 100% | 50%
|  |  | - Implement - Insert dict on android | Nguyen Phan Xuan Huy | 100% | 30%
|  |  | - Implement -Delete Q/A DMS | Huynh Trong Khang | 100% | 57%
|  |  | - Test - show Q/A on Android | Ta Ngoc Thien Phu | 100% | 54%
|  |  | - Implement - Drop-dict on android | Ta Ngoc Thien Phu | 100% | 15%
| Wednesday | 2013-04-30 | - Celebrate Victory Day 30th april
26 | Thursday | 2013-05-01 | - International worker's Day |  |  |  | 52.89%
| Friday | 2013-05-02
| Saturday | 2013-05-03
| Monday | 2013-05-05 | - Team meeting (Daily meeting 3 for sprint 4) | Deadline Team | 100% | 100%
|  |  | - Web service - DMS receive question from Android app's DDS | Le Ngoc Chau | 100% | 70%
|  |  | - Test - Create question | Le Ngoc Chau | 100% | 80%
|  |  | - Web service - Search Q/A on Android | Le Ngoc Chau | 100% | 50%
|  |  | - Implement - Send mail on android | Khau Thanh Dao | 100% | 60%
|  |  | - Detail design DMS | Ngo Quang Huy | 100% | 57%
|  |  | - Implement - Insert dict on android | Nguyen Phan Xuan Huy | 100% | 30%
|  |  | - Implement -Delete Q/A DMS | Huynh Trong Khang | 100% | 79%
|  |  | - Test - Update dictionary on Android DDS | Ta Ngoc Thien Phu | 100% | 73%
|  |  | - Implement - Drop-dict on android | Ta Ngoc Thien Phu | 100% | 25%
| Tuesday | 2013-05-06 | - Meetings with Customer | Deadline Team | 100% | 100%
|  |  | - Team meetings | Deadline Team | 100% | 90%
|  |  | - Web service - DMS receive question from Android app's DDS | Le Ngoc Chau | 100% | 95%
|  |  | - Test - Web service - DMS receive question from Android app's DDS | Le Ngoc Chau | 100% | 83%
|  |  | - Test - Create question | Le Ngoc Chau | 100% | 55%
|  |  | - Web service - Drop-dict on android | Khau Thanh Dao | 100% | 0%
|  |  | - Web service - Search Q/A on Android DMS | Khau Thanh Dao | 100% | 85%
|  |  | - Test - Login/log out on android | Ngo Quang Huy | 100% | 90%
|  |  | - Test - Show Q/A on android | Ngo Quang Huy | 100% | 80%
|  |  | - Implement - Insert dict on android | Nguyen Phan Xuan Huy | 100% | 45%
|  |  | - Implement - Create question DMS | Huynh Trong Khang | 100% | 85%
|  |  | - Implement - Drop-dict on android | Ta Ngoc Thien Phu | 100% | 25%
|  |  | - Web service - Insert dict on android | Ta Ngoc Thien Phu | 100% | 0%
| Wednesday | 2013-05-07 | - Team meeting (Daily meeting 4 for sprint 4) | Deadline Team | 100% | 100%
|  |  | - Review Document | Le Ngoc Chau | 100% | 20%
|  |  | - Web service - Search Q/A on Android | Le Ngoc Chau | 100% | 15%
|  |  | - Test - Delete Q/A | Le Ngoc Chau | 100% | 0%
|  |  | - Web service - Drop-dict on android | Khau Thanh Dao | 100% | 0%
|  |  | - Implement - Send mail on android | Khau Thanh Dao | 100% | 50%
|  |  | - Test - Search Q/A on Android | Ngo Quang Huy | 100% | 70%
|  |  | - Web service - Save Q/A on android | Nguyen Phan Xuan Huy | 100% | 80%
|  |  | - Implement - Insert dict on android | Nguyen Phan Xuan Huy | 100% | 0%
|  |  | - Implement - Create question DMS | Huynh Trong Khang | 100% | 0%
|  |  | - Web service - send mail on android DMS | Huynh Trong Khang | 100% | 55%
|  |  | - Implement - Drop-dict on android | Ta Ngoc Thien Phu | 100% | 57%
|  |  | - Web service - Insert dict on android | Ta Ngoc Thien Phu | 100% | 0%
27 | Thursday | 2013-05-08 | - Meetings with Faculty | Deadline Team | 100% | 100% | 48.27%
|  |  | - Team meeting | Deadline Team | 100% | 90%
|  |  | - Review Document | Le Ngoc Chau | 100% | 50%
|  |  | - Test - Create question | Le Ngoc Chau | 100% | 55%
|  |  | - Web service - Drop-dict on android | Khau Thanh Dao | 100% | 0%
|  |  | - Test - View detail Q/A on Android | Khau Thanh Dao | 100% | 30%
|  |  | - Test - Web service - send mail on android | Khau Thanh Dao | 100% | 70%
|  |  | - Test - Send mail on android | Ngo Quang Huy | 100% | 66%
|  |  | - Test - Login/log out on android | Ngo Quang Huy | 100% | 94%
|  |  | - Test - Show Q/A on android | Ngo Quang Huy | 100% | 87%
|  |  | - Implement - Insert dict on android | Nguyen Phan Xuan Huy | 100% | 30%
|  |  | - Test - Web service - Drop-dict on android | Huynh Trong Khang | 100% | 0%
|  |  | - Test - Web service - search Q/A | Huynh Trong Khang | 100% | 15%
|  |  | ' - Web service - Insert dict on android | Ta Ngoc Thien Phu | 100% | 0%
|  |  | - Fix bug DDS and DMS | Ta Ngoc Thien Phu | 100% | 90%
| Friday | 2013-05-09 | - Team meeting (Daily meeting 5 for sprint 4) | Deadline Team | 100% | 100%
|  |  | - Review Document | Le Ngoc Chau | 100% | 70%
|  |  | - Fix bug DDS and DMS | Khau Thanh Dao | 100% | 80%
|  |  | - Fix bug DDS and DMS | Ta Ngoc Thien Phu | 100% | 70%
|  |  | - Test - View detail Q/A on Android | Khau Thanh Dao | 100% | 90%
|  |  | - Deploy-Android's DMS | Khau Thanh Dao | 100% | 0%
|  |  | - Update product backlog | Ngo Quang Huy | 100% | 75%
|  |  | - Test - Insert dict on android DMS | Nguyen Phan Xuan Huy | 100% | 15%
|  |  | - Test - Web service - Send Q/A from DDS to Android's DDS | Huynh Trong Khang | 100% | 70%
|  |  | - Web service - Insert dict on android | Ta Ngoc Thien Phu | 100% | 0%
| Saturday | 2013-05-10 | - Review Document | Le Ngoc Chau | 100% | 60%
|  |  | - Review Document | Ngo Quang Huy | 100% | 55%
|  |  | - Fix bug DMS and DDS | Khau Thanh Dao | 100% | 60%
|  |  | - Fix bug DMS and DDS | Ta Ngoc Thien Phu
|  |  | - Update product backlog | Ngo Quang Huy | 100% | 85%
|  |  | - Implement - Insert dict on android DMS | Nguyen Phan Xuan Huy | 100% | 45%
|  |  | - Test - Insert dict on android DMS | Nguyen Phan Xuan Huy | 100% | 10%
|  |  | - Test - Web service - search Q/A | Huynh Trong Khang | 100% | 15%
|  |  | - Implement - Create question | Huynh Trong Khang | 100% | 60%
|  |  | - Web service - Insert dict on android | Ta Ngoc Thien Phu | 100% | 0%
| Monday | 2013-05-12 | - Team meeting (Daily meeting 6 for sprint 4) | Deadline Team | 100% | 100%
|  |  | - Review Document | Le Ngoc Chau | 100% | 70%
|  |  | - Review Document | Ngo Quang Huy | 100% | 84%
|  |  | - Fix bug DMS and DDS | Khau Thanh Dao | 100% | 65%
|  |  | - Fix bug DMS and DDS | Ta Ngoc Thien Phu
|  |  | - Implement - Insert dict on android DMS | Nguyen Phan Xuan Huy | 100% | 45%
|  |  | - Test - Insert dict on android DMS | Nguyen Phan Xuan Huy | 100% | 10%
|  |  | - Test - Drop-dict on android | Nguyen Phan Xuan Huy | 100% | 56%
|  |  | - Test - Web service - Drop-dict on android | Huynh Trong Khang | 100% | 0%
|  |  | - Implement - Create question | Huynh Trong Khang | 100% | 77%
|  |  | - Web service - Insert dict on android | Ta Ngoc Thien Phu | 100% | 0%
| Tuesday | 2013-05-13 | - Meetings with Customer | Deadline Team | 100% | 100%
|  |  | - Review Document | Le Ngoc Chau | 100% | 35%
|  |  | - Fix bug DMS and DDS | Khau Thanh Dao | 100% | 63%
|  |  | - Fix bug DMS and DDS | Ta Ngoc Thien Phu
|  |  | - Implement - Insert dict on android DMS | Nguyen Phan Xuan Huy | 100% | 60%
|  |  | - Test - Insert dict on android DMS | Nguyen Phan Xuan Huy | 100% | 55%
|  |  | - Test - Drop-dict on android | Nguyen Phan Xuan Huy | 100% | 72%
|  |  | - Test - Web service - Insert dict on android DDS | Ngo Quang Huy | 100% | 0%
|  |  | - Implement - Create question | Huynh Trong Khang | 100% | 65%
|  |  | - Web service - Insert dict on android | Ta Ngoc Thien Phu | 100% | 0%
| Wednesday | 2013-05-14 | - Team meeting (Daily meeting 7 for sprint 4) | Deadline Team | 100% | 100%
|  |  | - Review Document | Le Ngoc Chau | 100% | 60%
|  |  | - Fix bug DMS and DDS | Khau Thanh Dao | 100% | 50%
|  |  | - Fix bug DMS and DDS | Ta Ngoc Thien Phu
|  |  | - Test - Web service - Insert dict on android DDS | Ngo Quang Huy | 100% | 0%
|  |  | - Implement - Insert dict on android DMS | Nguyen Phan Xuan Huy | 100% | 60%
|  |  | - Test - Insert dict on android DMS | Nguyen Phan Xuan Huy | 100% | 55%
|  |  | - Test - Web service - Search Q/A on Android | Nguyen Phan Xuan Huy | 100% | 0%
|  |  | - Test - Web service - Drop-dict on android | Huynh Trong Khang | 100% | 0%
|  |  | - Test - Web service - search Q/A | Huynh Trong Khang | 100% | 22%
|  |  | - Web service - Insert dict on android | Ta Ngoc Thien Phu | 100% | 0%
28 | Thursday | 2013-05-15 | - Meetings with Faculty | Deadline Team | 100% | 100% | 87%
|  |  | - Team meeting | Deadline Team | 100% | 80%
|  |  | - Fix bug DDS and DMS | Ta Ngoc Thien Phu | 100% | 90%
|  |  | - Fix bug DDS and DMS | Khau Thanh Dao
|  |  | - Fix bug Android DDS and DMS | Huynh Trong Khang | 100% | 80%
|  |  | - Fix bug Android DDS and DMS | Nguyen Phan Xuan Huy
|  |  | - Review document | Le Ngoc Chau | 100% | 80%
|  |  | - Review document | Ngo Quang Huy
| Friday | 2013-05-16 | - Meetings with Customer | Deadline Team | 100% | 100%
|  |  | - Fix bug DDS and DMS | Ta Ngoc Thien Phu | 100% | 90%
|  |  | - Fix bug DDS and DMS | Khau Thanh Dao
|  |  | - Fix bug Android DDS and DMS | Huynh Trong Khang | 100% | 80%
|  |  | - Fix bug Android DDS and DMS | Nguyen Phan Xuan Huy
|  |  | - Review document | Le Ngoc Chau | 100% | 89%
|  |  | - Review document | Ngo Quang Huy
| Saturday | 2013-05-17 | - Fix bug DDS and DMS | Ta Ngoc Thien Phu | 100% | 93%
|  |  | - Fix bug DDS and DMS | Khau Thanh Dao
|  |  | - Fix bug Android DDS and DMS | Huynh Trong Khang | 100% | 89%
|  |  | - Review document | Le Ngoc Chau | 100% | 85%
| Monday | 2013-05-19 | - Team meeting (close sprint 4) | Deadline Team | 100% | 95%
|  |  | - Review document | Deadline Team | 100% | 97%
| Tuesday | 2013-05-20 | - Team meeting | Deadline Team | 100% | 80%
|  |  | - Review document | Deadline Team | 100% | 83%
| Wednesday | 2013-05-21 | - Review document | Deadline Team | 100% | 85%
|  |  | - Prepair document for submit | Deadline Team | 100% | 70%
29 | Thursday | 2013-05-22 | - Meetings with Faculty | Deadline Team | 100% | 100% | 73.56%
|  |  | - Team meeting | Deadline Team | 100% | 98%
|  |  | - Prepair document to print | Deadline Team | 100% | 0%
|  |  | - Review document | Deadline Team | 100% | 60%
| Friday | 2013-05-23 | - Review document | Deadline Team | 100% | 75%
|  |  | - Prepair powerpoint | Deadline Team | 100% | 60%
|  |  | - Prepair document to print | Deadline Team | 100% | 70%
| Saturday | 2013-05-24 | - Review document | Deadline Team | 100% | 83%
| Monday | 2013-05-26 | - Review document | Deadline Team | 100% | 87%
|  |  | - Prepair powerpoint | Deadline Team | 100% | 60%
|  |  | - Prepair document to print | Deadline Team | 100% | 70%
|  |  | - Burn VCD | Deadline Team | 100% | 75%
| Tuesday | 2013-05-27 | - Team meeting | Deadline Team | 100% | 85%
|  |  | - Review document | Deadline Team | 100% | 87%
| Wednesday | 2013-05-28 | - Team meeting | Deadline Team | 100% | 80%
|  |  | - Review document | Deadline Team | 100% | 87%
30 | Thursday | 2013-05-29 | - Meetings with Faculty | Deadline Team | 100% | 100% | 96.67%
|  |  | - Team meeting | Deadline Team | 100% | 90%
| Friday | 2013-05-30 | - Team meeting (close project) | Deadline Team | 100% | 100%
| Saturday | 2013-05-31

## Team member
No | Team member
1 | Deadline Team
2 | Le Ngoc Chau
3 | Khau Thanh Dao
4 | Ngo Quang Huy
5 | Nguyen Phan Xuan Huy
6 | Huynh Trong Khang
7 | Ta Ngoc Thien Phu