## Team member
Chau Le
Dao Khau
Huy Ngo
Huy Nguyen
Khang Huynh
Phu Ta

## Chau Le
Admission System Project
Report date: 19/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Chau Le
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Code registration form | Medium | 18/3/2014 | 18/3/2014 | Done |  | Chau Le
2
3
4
Plan for next days
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Code change password |  | 19/3/2014 |  |  |  | Chau Le
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1 | Can't insert data to database, need more time to research |  |  | Increase time and resource
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Dao Khau
Admission System Project
Report date: 19/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Dao Khau
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Code function create index | High | 17/3/2014 | 18/3/2014 | On-going |  | Dao Khau
2 | Code Funtion user management | High | 17/3/2014 | 18/3/2014 | On-going |  | Dao Khau
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Integrate code |  | 19/3/2013
2 | Check data in view layer |  | 19/3/2013
3 | Pagination |  | 19/3/2013
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1 | understand how to use ckeditor
2
3

## Huy Ngo
Admission System Project
Report date: 19/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Huy Ngo
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1
2
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Huy Nguyen
Admission System Project
Report date: 19/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Huy Nguyen
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Update UAT | High | 03.17.2014 | 03.19.2014 | On-going |  | Huy Nguyen
2 | Coding Spring MVC FTP Adapter | High | 03.17.2014 | 03.18.2014 | Done |  | Huy Nguyen
3 | Update Testcase on TFS | High | 03.17.2014 | 03.17.2014 | On-going |  | Huy Nguyen
4 | Addition testcase | High | 03.17.2014 | 03.19.2014 | On-going |  | Huy Nguyen
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Update Testcase on TFS |  | 03.20.2014 |  |  |  | Huy Nguyen
2 | Update defect report, test report |  | 03.20.2014 |  |  |  | Huy Nguyen
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Khang Huynh
Admission System Project
Report date: 19/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Khang Huynh
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Research and coding ftp transfers file | High | 17/3/2014 | 17/3/2014 | Done |  | Khang Huynh
3 | Demo ftp and coding put Q/A into dictionary | High | 18/3/2014 | 19/3/2014 | Done |  | Khang Huynh
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Coding put Q/A into dictionary |  | 19/3/2014 |  |  |  | Khang Huynh
2 | Coding loading page |  | 20/3/2014 |  |  |  | Khang Huynh
3 | Resarch pagination |  | 20/3/2014 |  |  |  | Khang Huynh
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Phu Ta
Admission System Project
Report date: 19/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Phu Ta
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Coding dictionary-available tab | High | 18/3/2014 | 18/3/2014 | Done
2 | Coding dictionary-recent tab | High | 18/3/2014 | 19/3/2014 | On-going
3 | Coding dictionary-delete tab | High | 18/3/2014 | 19/3/2014 | On-going
4
Plan for next days
#
1 | Coding dictionary-recent tab |  | 19/3/2014
2 | Coding dictionary-delete tab |  | 19/3/2014
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1 | understand how to use ckeditor
2
3