## Team member
Team member list
Project: [Project's name] - [Team's name] - Mentor: [Mentor's name]
Project Risk Manager: [Name]
No | Name
1 | [Name of team member]
2 | [Name of team member]
3 | [Name of team member]
4 | [Name of team member]
5 | [Name of team member]
6 | [Name of team member]

## <Name of team member>
Risk priority list
Project: [Project's name] - [Team's name] - Mentor: [Mentor's name]
Member: [Name]
RISK ID | LIST RISK | PROBABILITY | IMPACT | MITIGATE METHOD
1 | Time is not enough for project development | 50 | 90
2 | Communication between project team and stakeholder (mentor and customer) is not good | 50 | 75
3 | Estimation is not well | 68 | 85
4 | Many defects in product after release | 70 | 80
5 | Don't complete the full functionality required | 80 | 70
6 | Morale of the team was down | 80 | 90
7 | The goal of stakeholders are different | 25 | 95
8 | Not enough knowledge about programming | 60 | 89
9 | Difficult to communicate with customer | 5 | 55
10 | Team member's laptop is decayed | 10 | 69
11 | A lots defect in architecture phase | 20 | 40
12 | Progress of architecture phase is slow | 10 | 30
13 | Lack of meeting place | 85 | 20
14 | lack of experience to manage project | 80 | 99
15 | Lack of skills about test tool | 30 | 50
16 | Communicate about tester and developer | 30 | 40
17 | test case pass not enough | 50 | 50
18 | Team members have to focus on semester (I,II) | 20 | 20
19 | Occurring conflict between team members | 70 | 75
20 | Team members working not complete, working on time deadline | 60 | 70
21 | Team members have illness, need a few days to rest | 20 | 30
22 | Identify the scope unclear of project | 40 | 75
23 | Concentrate too much to elicit depth of detail requirement stage | 50 | 50
24 | Exceeded time for requirement phase | 60 | 50

## Risk management list
Risk management list
Project: [Project's name] - [Team's name] - Mentor: [Mentor's name]
Project Risk Manager: [Name]
Step 1 : Risk Identification | [5 empty] | Step 2 : Risk analysis |  |  |  | Step 3 : Response Planing |  |  | Step 4 : Risk management
Risk ID | List of poissible risk | Trigger | Raised By | Date Raises | Risk Category | Probability | Impact | Priority Score | Mitigation methods | Risk strategy | Response plan | Owner | Status | Note
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
Risk strategy | Avoid | Go away too far from that risk
| Mitigate | Use some method to control that risk
| Accept | Live with that risk
Transfer
Status | Identified | Define risk
| Analys complete | Risk was analys
| Planning complete | Planning for control risk
| Triggered | Describe risk
| Resolved | Risk was mitgate

## Recorded
Risk recorded
Project: [Project's name] - [Team's name] - Mentor: [Mentor's name]
Project Risk Manager: [Name]
Risk ID | Week | Risk | Plan/Methods
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## risk priority (probability) (hidden)
ID | Châu | Đạo | Q.Huy | X.Huy | Khang | Phú
1 | 50 | 40 | 60 | 40 | 50 | 60
2 | 50 | 40 | 40 | 50 | 30 | 40
3 | 68 | 60 | 40 | 60 | 50 | 40
4 | 70 | 40 | 60 | 30 | 60 | 60
5 | 80 | 30 | 50 | 50 | 50 | 50
6 | 80 | 60 | 50 | 50 | 60 | 50
7 | 25 | 30 | 40 | 20 | 30 | 40
8 | 60 | 50 | 50 | 20 | 50 | 50
9 | 5 | 30 | 45 | 20 | 30 | 45
10 | 10 | 40 | 30 | 25 | 70 | 30
11 | 20 | 50 | 80 | 70 | 60 | 80
12 | 10 | 80 | 85 | 80 | 50 | 85
13 | 85 | 80 | 80 | 10 | 80 | 80
14 | 80 | 60 | 60 | 30 | 30 | 60
15 | 30 | 50 | 70 | 30 | 30 | 70
16 | 30 | 30 | 40 | 55 | 30 | 40
17 | 50 | 50 | 80 | 60 | 60 | 80
18 | 20 | 70 | 90 | 40 | 90 | 90
19 | 70 | 60 | 70 | 20 | 70 | 70
20 | 60 | 60 | 80 | 50 | 80 | 80
21 | 20 | 60 | 70 | 10 | 50 | 70
22 | 40 | 60 | 65 | 10 | 30 | 65
23 | 50 | 50 | 60 | 30 | 60 | 60
24 | 60 | 60 | 70 | 40 | 40 | 70

## risk priority (impact) (hidden)
ID | Châu | Đạo | Q.Huy | X.Huy | Khang | Phú
1 | 90 | 80 | 80 | 80 | 80 | 80
2 | 75 | 50 | 60 | 50 | 60 | 60
3 | 85 | 70 | 60 | 70 | 60 | 60
4 | 80 | 80 | 80 | 60 | 80 | 80
5 | 70 | 80 | 70 | 50 | 70 | 90
6 | 90 | 60 | 70 | 80 | 70 | 70
7 | 95 | 80 | 70 | 80 | 70 | 90
8 | 89 | 50 | 70 | 40 | 70 | 60
9 | 55 | 70 | 70 | 60 | 70 | 75
10 | 69 | 50 | 70 | 30 | 70 | 60
11 | 40 | 70 | 80 | 65 | 80 | 70
12 | 30 | 80 | 70 | 70 | 70 | 70
13 | 20 | 40 | 60 | 10 | 60 | 60
14 | 99 | 60 | 70 | 50 | 70 | 60
15 | 50 | 50 | 30 | 30 | 30 | 70
16 | 40 | 40 | 30 | 50 | 30 | 50
17 | 50 | 50 | 50 | 50 | 50 | 60
18 | 20 | 50 | 70 | 50 | 70 | 60
19 | 75 | 70 | 70 | 30 | 70 | 80
20 | 70 | 70 | 70 | 70 | 70 | 80
21 | 30 | 50 | 50 | 30 | 50 | 60
22 | 75 | 70 | 80 | 80 | 80 | 80
23 | 50 | 50 | 50 | 40 | 50 | 50
24 | 50 | 50 | 40 | 30 | 40 | 60