## LeNgocChau
Admission System Project
Report date: 7/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Le Ngoc Chau
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Code interface for dictionary | Medium | 2014-05-03 | 2014-06-03 | Done |  | Le Ngoc Chau
2
3
4
Plan for next days
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Code interface for change password |  | 2014-07-03 |  |  |  | Le Ngoc Chau
2 | Code interface for view profile |  | 2014-07-03 |  |  |  | Le Ngoc Chau
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## KhauThanhDao
Admission System Project
Report date: 7/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Khau Thanh Dao
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Code interface for menu | Medium | 2014-05-03 | 2014-06-03 | Done |  | Khau Thanh Dao
2 | Research tiles template | High | 2014-05-03 | 2014-07-03 | Done |  | Khau Thanh Dao
3
4
Plan for next days
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Code interface with ckeditor |  | 2014-07-03 |  |  |  | Khau Thanh Dao
2 | Integrate inteface |  | 2014-07-03 |  |  |  | Khau Thanh Dao
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## NgoQuangHuy
Admission System Project
Report date: 7/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Ngo Quang Huy
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Code interface for list not replied | Medium | 2014-07-03 | 2014-07-03 | On-going |  | Ngo Quang Huy
2
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Code interface for list not replied |  | 2014-11-03 |  |  |  | Ngo Quang Huy
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## NguyenPhanXuanHuy
Admission System Project
Report date: 7/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Nguyen Phan Xuan Huy
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Researh testcase template | Medium | 2014-07-03 | 2014-07-03 | On-going |  | Nguyen Phan Xuan Huy
2
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Code interface for list not replied |  | 2014-11-03 |  |  |  | Nguyen Phan Xuan Huy
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## HuynhTrongKhang
Admission System Project
Report date: 7/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Huynh Trong Khang
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Implement login | Medium | 2014-05-03 | 2014-05-03 | Done |  | Huynh Trong Khang
2 | Update dictionary-list interface | Medium | 2014-05-03 | 2014-05-03 | Done |  | Huynh Trong Khang
3 | Update login, register, menu interface | Medium | 2014-06-03 | 2014-06-03 | Done |  | Huynh Trong Khang
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Create business rule for Dictionary management on web application |  | 2014-07-03 |  |  |  | Huynh Trong Khang
2 | Create pagination, checkbox, security code |  | 2014-07-03 |  |  |  | Huynh Trong Khang
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Done |  | Owner
1 |  |  |  |  | Done
The most significance knowledge gained last week
# | Description
1
2
3

## TaNgocThienPhu
Admission System Project
Report date: 7/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Ta Ngoc Thien Phu
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Research load list-question from db | Medium | 2014-05-03 | 2014-06-03 | Done |  | Ta Ngoc Thien Phu
2 | Coding load list-question from db | High | 2014-06-03 | 2014-07-03 | On-going |  | Ta Ngoc Thien Phu
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Coding load list-question from db |  | 2014-07-03 |  |  |  | Ta Ngoc Thien Phu
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Team member
No | Team member
1 | Le Ngoc Chau
2 | Khau Thanh Dao
3 | Ngo Quang Huy
4 | Nguyen Phan Xuan Huy
5 | Huynh Trong Khang
6 | Ta Ngoc Thien Phu