## LeNgocChau
Admission System Project
Report date: 17/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Le Ngoc Chau
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Research registration | Medium | 14/3/2014 | 15/3/2014 | Done |  | Le Ngoc Chau
2
3
4
Plan for next days
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Code registration form |  | 18/3/2014 |  |  |  | Le Ngoc Chau
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## KhauThanhDao
Admission System Project
Report date: 17/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Khau Thanh Dao
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Code function send answer | High | 15/3/2014 | 15/3/2014 | Done |  | Khau Thanh Dao
2 | Code function create index | High | 15/3/2014 | 15/3/2014 | On-going |  | Khau Thanh Dao
3 | Code Funtion user management | High | 15/3/2014 | 15/3/2014 | On-going |  | Khau Thanh Dao
4 | Code Funtion Create index | High | 15/3/2014 | 15/3/2014 | On-going |  | Khau Thanh Dao
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Code function create index |  | 17/3/2014 |  |  |  | Khau Thanh Dao
2 | Code Funtion user management |  | 17/3/2014 |  |  |  | Khau Thanh Dao
3 | Code Funtion Create index |  | 17/3/2014 |  |  |  | Khau Thanh Dao
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## NgoQuangHuy
Admission System Project
Report date:17/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Ngo Quang Huy
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Implement - login/ logout DMS - android app | High | 14/3/2014 | 14/3/2015 | On-going |  | Ngo Quang Huy
2
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1 | coding for view profile |  | 20/3/2014 |  |  |  | Ngo Quang Huy
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## NguyenPhanXuanHuy
Admission System Project
Report date: 17/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Nguyen Phan Xuan Huy
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Coding FTP | High | 14/3/2014 | 14/3/2014 | On-going |  | Nguyen Phan Xuan Huy
2 | Testing Login-Logout | Medium | 15/3/2014 | 15/3/2014 | Done |  | Nguyen Phan Xuan Huy
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## HuynhTrongKhang
Admission System Project
Report date: 17/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Huynh Trong Khang
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Demo sessions |  | 14/3/2014 | 14/3/2014 | Done |  | Huynh Trong Khang
2 | Research and demo Crup in springMVC |  | 14/3/2014 | 15/03/2014 | On-going |  | Huynh Trong Khang
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Research and demo FTP transfer file |  | 17/3/2014 |  |  |  | Huynh Trong Khang
2 | Implement transfer file to FTP server |  | 18/3/2014 |  |  |  | Huynh Trong Khang
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## TaNgocThienPhu
Admission System Project
Report date: 17/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Ta Ngoc Thien Phu
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Coding delete delete-question | High | 15/3/2014 | 15/3/2014 | Done |  | Ta Ngoc Thien Phu
2
3
4
Plan for next days
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Update detail design |  | 17/3/2014 |  |  |  | Ta Ngoc Thien Phu
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Team member
No | Team member
1 | Le Ngoc Chau
2 | Khau Thanh Dao
3 | Ngo Quang Huy
4 | Nguyen Phan Xuan Huy
5 | Huynh Trong Khang
6 | Ta Ngoc Thien Phu