## List main task
No | Activities
1 | Team Meetings
2 | Reading
3 | Self Prepare
4 | Team Home Work
5 | Team Work
6 | Meetings with Faculty
7 | Meetings with Customer
8 | Training
9 | Research
10 | Review with customer
11 | Review with technical support

## SEP-PROJECT
Time Recording Log For: Admission project | [5 empty] | Start Date: 08/11/2013 End Date:
Huynh Trong Khang - T104898
[7 empty] | Minimum: 5 hours/day 25 hours/week (5hours * 5 days) 700 hours/30 weeks (25 hours * 28 weeks) | Maximum: 24 hours/day 168 hours/week (24hours * 7 days) 4704 hours/30 weeks (168 hours * 28 weeks)
Week | Date | Start | Stop | Delta Time | Total time of day | Activity | Description | Artifact | Note
1 | 2013-11-07 | 13:20 | 14:30 | 1.16 | 1.16 | Team Meetings | - Repair for kick off meeting - Devide team work for team member - Define role in project |  |  | SUMMARY: TIME FOR DOING PROJECT | 97.68 | HOURS
| 2013-11-08 | 14:00 | 15:10 | 1.1.6 | 1.67 | Kick off meeting | - Discuss about communication plan between customer and team - Discuss about system concept |  |  | Time for doing week 1 | 1.66 | HOURS
|  | 15:10 | 15:40 | 0.5 |  | Meetings with Faculty | - Discus about weekly report meeting
2 | 2013-11-11 | 1:00PM | 3:30PM | 2.5 | 5 | Team Meetings | Trainning ACDM combine some process
|  | 8:00PM | 10:30PM | 2.5 |  | Team Home Work | Do initial requirement plan document | AS_RE_RequirementPlan version 0.1
| 2013-11-12 | 13:45 | 15:00 | 2.25 | 3.75 | Team Meetings | - Discuss to team rule in team charter - Review project charter, communication plan, Configuration plan, Measurement plan, Weekly report and Timelog - Discuss to process model | - AS_PM_TeamCharter.docx version 1.0 - AS_PM _ConfigurationPlan.docx version 1.0 - AS_PM_CommunicationPlan.docx version 1.0 - AS_PM_MeasurementPlan.docx version 1.0 |  | Time for doing week 2 | 15.58 | HOURS
|  | 22:00 | 23:30 | 1.5 |  | Research | - Java overview
| 2013-11-13 | 9:00 | 11:00 | 2 | 4.5 | Research | - Spring core
|  | 13:30 | 15:30 | 2 |  | Team Meetings | - Review with team technical issues: Java, Hibernate, Spring, Maven | - Java Overview + Spring.docx - Training.pptx
|  | 20:00 | 20:30 | 0.5 |  | Research | - Android basic | - AS_DeadlineTeam_Week2.pptx |  | Time for doing week 3 | 24.96 | HOURS
| 2013-11-14 | 21:00 | 22:15 | 1.25 | 1.25 | Meetings with Faculty | - Present work that team completed in this week 2 | - AS_DeadlineTeam_Week2.pptx |  | Time for doing week 4 | 25.91 | HOURS
| 2013-11-15 | 13:00 | 14:05 | 1.08 | 1.08 | Team Meetings | - Ngo Quang Huy present about Risk management plan - Nguyen Phan Xuan Huy present about spring framwork | - AS_PM_RiskManagementPlan.docx version 1.0 - Folder Spring Framwork |  | Time for doing week 5 | 29.57 | HOURS
3 | 2013-11-18 | 8:00PM | 8:30PM | 0.5 | 3.5 | Team Home Work | Update Measurement Template | AS_PM_MeasurementPlan |  | Time for doing week 8 | 0 | HOURS
|  | 8:30PM | 11:30PM | 3 |  | Team Home Work | Create Requirement Plan initial | AS_RE_RequirementPlan.docx
| 2013-11-19 | 8:00AM | 10:00AM | 2 | 2.5 | Team Home Work | Update Requirement Plan | AS_RE_RequirementPlan.docx
|  | 10:00AM | 10:30AM | 0.5 |  | Team Home Work | Create Operation Requirement Document | AS_RE_OperationPlan.docx |  | Time for doing week 9 | 0 | HOURS
| 2013-11-20 | 13:30 | 17:30 | 4 | 4 | Team Work | Review Change process, Scrum model combine ACDM Update Schedule Requirement Plan | AS_RE_RequirementPlan.docx |  | Time for doing week 10 | 0 | HOURS
| 2013-11-21 | 9:00AM | 10:10AM | 1.16 | 7.06 | Meetings with Faculty | Review Requirement Plan, Architert Plan, Master Plan, Mapping with Scrum and ACDM
| 2013-11-21 | 10:10AM | 11:30AM | 1.3 |  | Team Meetings | 1
| 2013-11-21 | 1:30PM | 3:00PM | 1.5 |  | Team Work | Conduct work assign | Stage 1 - Stage 2 - RE
| 2013-11-21 | 3:00PM | 5:10PM | 2.1 |  | Team Meetings | Review ACDM Stages, Roles, Atifacts, Input, Output |  |  | Time for doing week 11 | 0 | HOURS
| 2013-11-21 | 8:00PM | 9:00PM | 1 |  | Team Home Work | Research roles on Scrum
| 2013-11-22 | 1.30PM | 2.45PM | 1.25 | 3.25 | Team Meetings
| 2013-11-22 | 2.45PM | 4.45PM | 2 |  | Team Home Work | Update Requirement Plan Create Product backlog template Create Spring backlog template |  |  | Time for doing week 12 | 0 | HOURS
| 2013-11-23 | 13:00 | 13:45 | 0.25 | 4.65
| 2013-11-23 | 2.00PM | 5.30PM | 3.5 |  | Team Home Work | Create Requirement Process follow ACDM Stage 1 & Stage 2 | AS_RE_RequirementPlan.docx
| 2013-11-23 | 9.30PM | 10.20PM | 0.9 |  | Team Home Work | Update process description, roles and responsibility | AS_RE_RequirementPlan.docx
4 | 2013-11-25 | 7:30PM | 11:30PM | 3 | 3 | Team Home Work | Review works for report to mentor tomorrow Update Templates Product + Sprint Backlog Research how to estimates user point with Poker Planning | Product Backlog Templates.xlsx |  | Time for doing week 13 | 0 | HOURS
| 2013-11-26 | 8.00AM | 9:00AM | 1 | 6.75 | Team Home Work | Teamsefl Review task works Pre-week (week 3)
| 2013-11-26 | 21:00 | 23:30 | 2.5 |  | Meetings with Faculty | Review task works Pre-week (week 3) | Meeting_Minutes_261113
| 2013-11-26 | 13:30 | 14:45 | 1.25 |  | Team Work | Devide work task about Stage 1 elicite | DevideTeamWork_2611.docx
| 2013-11-26 | 2:45PM | 4:45PM | 2 |  | Team Home Work | Update Measurement Plan - orientiton for GQM technical, frequencly measurement Update Requirement Plan - detail roles for Stage 1,2 and Requirement Schedule | AS_PM_MeasurementPlan.docx AS_RE_RequirementPlan.docx | Miss file Measurement Template | Time for doing week 14 | 0 | HOURS
| 2013-11-27 | 1:30PM | 3:50PM | 2.33 | 2.83 | Team Meetings | Raise some question for future system |  |  | Time for doing week 15 | 0 | HOURS
| 2013-11-27 | 3:50PM | 4:20PM | 0.5 |  | Team Work | Collect questions from members Establish meeting with customer | Question - Tong hop
| 2013-11-28 | 8:00AM | 9:15AM | 1.33 | 5.83 | Team Home Work | Review question have prepared for system
| 2013-11-28 | 9:15AM | 11:00AM | 1.75 |  | Meetings with Customer | Collect architect drivers raw and develop user stories
| 2013-11-28 | 1:30PM | 4:15PM | 2.75 |  | Team Meetings | Analyse architect drivers raw "Bảng tin" and "Danh mục" Draw activity diagrams business process |  | Done file devide for members 29/11 | Time for doing week 16 | 0 | HOURS
| 2013-11-29 | 1:30PM | 5:00P< | 3.5 | 3.5 | Team Meetings | Analyse architect drivers raw Divide work task Design interface Draw activity diagram | 3_DevideTeamWork_2911 |  | Time for doing week 17 | 0 | HOURS
| 2013-12-01 | 12:00AM | 2:00PM | 2 | 4 | Team Home Work | Reseach and define entities for "Hỏi đáp" module Create architecture drivers specification Update requirement tracability matrix template | AS_RE_ArchitectureDriverSpecification.docx AS_RE_RequirementTraceabilityMatrix.xlsx
| 2013-12-01 | 7:00PM | 9:00PM | 2 |  | Team Home Work | Define entities and functional, quality attribute for "Hoi dap" module add functional list into Operation document | AS_RE_OperationPlan.docx | các thành viên chưa hoàn thành đầy đủ những yêu cầu đặt ra
5 | 2013-12-02 | 2:00PM | 6:00PM | 4 | 4 | Team Home Work | Create Operation requirement viet version Update Operation requirement Systhesis task works devided for team members: + Entities + Functional & Quality Attribute |  |  | Time for doing week 18 | 0 | HOURS
| 2013-12-03 | 9.00AM | 10.30AM | 1.5 | 7 | Meetings with Customer | Discuss entities and collection document + Rework entities + Implement analysis document <Archi Driver specification>
| 2013-12-03 | 1:30PM | 5:00PM | 3.5 |  | Training | First Training Java + Spring with Mr. Thanh + Setup nessecsary tools + Understand DI and AOP in Spring framework + Demo Hello world with Spring |  |  | Time for doing week 19 | 0 | HOURS
| 2013-12-03 | 8:00PM | 10:00PM | 2 |  | Team Home Work | Raise some risk on requirement phase Update templates entities, func,QA for team members Update measurement plan | AS_PM_MeasurementPlan Template-entities-function-quality Requirement_RiskList | Tomorrow, excute templates measurement plan v2,0i Re-idetify entities Hoi dap module Weekly report
| 2013-12-04 | 9:45AM | 10:30AM | 0.75 | 6.5 | Team Home Work | Update measurement plan + customer survey and defect report templates | AS_PM_MeasurementPlan.docx AS_ME_Customer Satisfaction Survey_Template.xlsx AS_ME_DefectReport_Template.docx | Remain works at this day: + Entities + Weekly report | Time for doing week 20 | 0 | HOURS
| 2013-12-04 | 1:30PM | 6:00PM | 4.5 |  | Team Meetings | Review + Master Design Plan + List Risk + Measurement + Process + Entities
| 2013-12-04 | 9:00PM | 11:00PM | 2 |  | Team Home Work | Update measurement template Synthesis entities create weekly report week 4 | AS_PM_WeeklyReport_Week4 Enities_Tonghop
| 2013-12-05 | 3:00 | 6:00 | 3 | 7.82 | Team Home Work | - Define weekly report - Update project plan - Update timelog
| 2013-12-05 | 8:00 | 9:10AM | 1.16 |  | Team Work | - Update timelog for team
| 2013-12-05 | 9:10AM | 10:40AM | 1.5 |  | Meetings with Faculty | - Review List risk, measurement plan - Review master plan, master design plan - Review project plan - Review sprint backlog template
| 2013-12-05 | 10:40AM | 11:30AM | 0.66 |  | Team Meetings | - Devide team work - Update entities
| 2013-12-05 | 16:30 | 6:00PM | 1.5 |  | Team Work | - Update timelog for team - Update timelog |  |  | Time for doing week 21 | 0 | HOURS
| 2013-12-08 | 6:30PM | 10:00PM | 3.5 | 3.5 | Team Home Work | - Update architectural drivers specification + Entties + List functional + Use model + Requirement Traceability Matrix - Create architectural driver specification - Viet version | AS_RE_ArchitectureDriverSpecification-EN-version.docx AS_RE_ArchitectureDriverSpecification-VN-version.docx usecase-diagram.vsd | Không gửi tài liệu cho khách hàng review được do thành viên vẽ use case còn nhiều sai sót | Time for doing week 22 | 0 | HOURS
6 | 2013-12-09 | 1:30PM | 6:-00PM | 4.5 | 6.5 | Team Meetings | - Collection and update driver specification document + Usecase diagram + Quality Attribute - Pioritize risk - Update requirement plan - schedule | AS_RE_ArchitectureDriverSpecification-VN-version.docx | Châu vắng vì có việc bận Huy Ngô vắng vì đi nhậu Huy Nguyễn vắng vì không có lý do | Time for doing week 23 | 0 | HOURS
| 2013-12-09 | 9:00PM | 11:00PM | 2 |  | Team Home Work | Update drivers specification document -viet version + Use case "Hoi dap" + Quality Attribute + Business and Technical constraint | AS_RE_ArchitectureDriverSpecification-VN-version.docx
| 2013-12-10 | 1:30 | 4:00PM | 2.5 | 2.5 | Training | Training spring core + MySQL + Insert/Update/Delete |  |  | Time for doing week 24 | 0 | HOURS
| 2013-12-11 | 5:00PM | 6:30PM | 1.5 | 1.5 | Team Home Work | Create customer satisfaction survey report teamplate Create weekly report for week 7 |  |  | Time for doing week 25 | 0 | HOURS
| 2013-12-12 | 9:00AM | 11:00PM | 2 | 6 | Meetings with Faculty | Meeting with mentor review week 6 and plan for week 7 Update some plan document
| 2013-12-12 | 11:00AM | 12:00PM | 1 |  | Team Meetings | Meeting about internal way of works
| 2013-12-12 | 2:00PM | 5:00PM | 3 |  | Meetings with Customer | Review architecturals drivers specification |  |  | Time for doing week 26 | 0 | HOURS
| 2013-12-13 | 2:00PM | 5:00PM | 3 | 4 | Team Work | Update use case diagram "Hỏi đáp" module Draw interface "Hỏi đáp" module
| 2013-12-13 | 10:00PM | 11:00PM | 1 |  | Team Home Work | Update requirement schedule Update plan for next week |  |  | Time for doing week 27 | 0 | HOURS
| 2013-12-15 | 7:00PM | 11 | 4 | 4 | Team Home Work | + Create assign task works for members week 6 + Update team members evaluation week 6 + Update driver specification + Update requirement plan <process> <roles&responsibility> <IDEF0>..
7 | 2013-12-16 | 2:00PM | 5:00PM | 3 | 3 | Team Work | Research Java with team |  |  | Time for doing week 28 | 0 | HOURS
| 2013-12-17 | 10:00AM | 12:00AM | 2 | 5 | Team Home Work | Update Architecture Drivers Specification | AS_RE_ArchitectureDriverSpecification-VN-version-0.5 | Waiting for review outline - Huy Nguyen and overview document - Chau Le
| 2013-12-17 | 1:30PM | 3:30PM | 2 |  | Training | Training validation with spring in Java
| 2013-12-17 | 8:00PM | 9:00PM | 1 |  | Team Home Work | Update requirement plan Create weekly report 5 |  |  | Time for doing week 29 | 0 | HOURS
| 2013-12-18 |  |  |  | 0 |  |  |  |  | Time for doing week 30 | 0 | HOURS
| 2013-12-19 |  |  |  | 0
| 2013-12-20 |  |  |  | 0
8 | 2013-12-23 |  |  |  | 0
| 2013-12-24 |  |  |  | 0
| 2013-12-25 |  |  |  | 0
| 2013-12-26 |  |  |  | 0
| 2013-12-27 |  |  |  | 0
9 | 2013-12-30 |  |  |  | 0
| 2013-12-31 |  |  |  | 0
| 2014-01-01 |  |  |  | 0
| 2014-01-02 |  |  |  | 0
| 2014-01-03 |  |  |  | 0
10 | 2014-01-06 |  |  |  | 0
| 2014-01-07 |  |  |  | 0
| 2014-01-08 |  |  |  | 0
| 2014-01-09 |  |  |  | 0
| 2014-01-10 |  |  |  | 0
11 | 2014-01-13 |  |  |  | 0
| 2014-01-14 |  |  |  | 0
| 2014-01-15 |  |  |  | 0
| 2014-01-16 |  |  |  | 0
| 2014-01-17 |  |  |  | 0
12 | 2014-01-20 |  |  |  | 0
| 2014-01-21 |  |  |  | 0
| 2014-01-22 |  |  |  | 0
| 2014-01-23 |  |  |  | 0
| 2014-01-24 |  |  |  | 0
13 | 2014-01-27 |  |  |  | 0 | Nghỉ tết
| 2014-01-28 |  |  |  | 0 | Nghỉ tết
| 2014-01-29 |  |  |  | 0 | Nghỉ tết
| 2014-01-30 |  |  |  | 0 | Nghỉ tết
| 2014-01-31 |  |  |  | 0 | Nghỉ tết
14 | 2014-02-03 |  |  |  | 0 | Nghỉ tết
| 2014-02-04 |  |  |  | 0 | Nghỉ tết
| 2014-02-05 |  |  |  | 0 | Nghỉ tết
| 2014-02-06 |  |  |  | 0 | Nghỉ tết
| 2014-02-07 |  |  |  | 0 | Nghỉ tết
15 | 2014-02-10 |  |  |  | 0
| 2014-02-11 |  |  |  | 0
| 2014-02-12 |  |  |  | 0
| 2014-02-13 |  |  |  | 0
| 2014-02-14 |  |  |  | 0
16 | 2014-02-17 |  |  |  | 0
| 2014-02-18 |  |  |  | 0
| 2014-02-19 |  |  |  | 0
| 2014-02-20 |  |  |  | 0
| 2014-02-21 |  |  |  | 0
17 | 2014-02-24 |  |  |  | 0
| 2014-02-25 |  |  |  | 0
| 2014-02-26 |  |  |  | 0
| 2014-02-27 |  |  |  | 0
| 2014-02-28 |  |  |  | 0
18 | 2014-03-03 |  |  |  | 0
| 2014-03-04 |  |  |  | 0
| 2014-03-05 |  |  |  | 0
| 2014-03-06 |  |  |  | 0
| 2014-03-07 |  |  |  | 0
19 | 2014-03-10 |  |  |  | 0
| 2014-03-11 |  |  |  | 0
| 2014-03-12 |  |  |  | 0
| 2014-03-13 |  |  |  | 0
| 2014-03-14 |  |  |  | 0
20 | 2014-03-17 |  |  |  | 0
| 2014-03-18 |  |  |  | 0
| 2014-03-19 |  |  |  | 0
| 2014-03-20 |  |  |  | 0
| 2014-03-21 |  |  |  | 0
21 | 2014-03-24 |  |  |  | 0
| 2014-03-25 |  |  |  | 0
| 2014-03-26 |  |  |  | 0
| 2014-03-27 |  |  |  | 0
| 2014-03-28 |  |  |  | 0
22 | 2014-03-31 |  |  |  | 0
| 2014-04-01 |  |  |  | 0
| 2014-04-02 |  |  |  | 0
| 2014-04-03 |  |  |  | 0
| 2014-04-04 |  |  |  | 0
23 | 2014-04-07 |  |  |  | 0
| 2014-04-08 |  |  |  | 0
| 2014-04-09 |  |  |  | 0
| 2014-04-10 |  |  |  | 0
| 2014-04-11 |  |  |  | 0
24 | 2014-04-14 |  |  |  | 0
| 2014-04-15 |  |  |  | 0
| 2014-04-16 |  |  |  | 0
| 2014-04-17 |  |  |  | 0
| 2014-04-18 |  |  |  | 0
25 | 2014-04-21 |  |  |  | 0
| 2014-04-22 |  |  |  | 0
| 2014-04-23 |  |  |  | 0
| 2014-04-24 |  |  |  | 0
| 2014-04-25 |  |  |  | 0
26 | 2014-04-28 |  |  |  | 0
| 2014-04-29 |  |  |  | 0
| 2014-04-30 |  |  |  | 0
| 2014-05-01 |  |  |  | 0
| 2014-05-02 |  |  |  | 0
27 | 2014-05-05 |  |  |  | 0
| 2014-05-06 |  |  |  | 0
| 2014-05-07 |  |  |  | 0
| 2014-05-08 |  |  |  | 0
| 2014-05-09 |  |  |  | 0
28 | 2014-05-12 |  |  |  | 0
| 2014-05-13 |  |  |  | 0
| 2014-05-14 |  |  |  | 0
| 2014-05-15 |  |  |  | 0
| 2014-05-16 |  |  |  | 0
29 | 2014-05-19 |  |  |  | 0
| 2014-05-20 |  |  |  | 0
| 2014-05-21 |  |  |  | 0
| 2014-05-22 |  |  |  | 0
| 2014-05-23 |  |  |  | 0
30 | 2014-05-26 |  |  |  | 0
| 2014-05-27 |  |  |  | 0
| 2014-05-28 |  |  |  | 0
| 2014-05-29 |  |  |  | 0
| 2014-05-30 |  |  |  | 0