## risk management
|  | Step 1 : Risk Identification |  |  |  |  | Step 2 : Risk analysis |  |  |  | Step 3 : Response Planing |  | Step 4 : Risk management
Risk ID | List of poissible risk | Trigger | Raised By | Date Raises | Risk Category | Probability | Impact | Priority Score | Mitigation methods | Risk strategy | Response plan | Owner | Status | Note
1 | Time is not enough for project development | The remaining time for project is not enough to implement remaining tasks in plan | Ngo Quang Huy | 2013-02-12 | Time | 0.27333 | 0.86667 | 0.23689 |  |  |  |  | Triggered
2 | Communication between project team and stakeholder (mentor and customer) is not good | Mentor doesn’t know current progress of project Customer misjudge team’s ability | Ngo Quang Huy | 2013-02-12 | Resource | [7 empty] | Triggered
3 | Estimation is not well | We usually working over or behind schedule ( >10 task everyweek ) | Ngo Quang Huy | 2013-02-12 | Estimating | [7 empty] | Triggered
4 | Many defects in product after release | Defects > 10 | Ngo Quang Huy | 2013-02-12 | [8 empty] | Triggered
5 | Don't complete the full functionality required | A few members lose trust in the group | Ngo Quang Huy | 2013-02-12 | Performance | [7 empty] | Triggered
6 | Morale of the team was down | Too difficult to do or manage time is unresonable | Ngo Quang Huy | 2013-02-12 | Resource | [7 empty] | Triggered
7 | The goal of stakeholders are different | Not understand about the ability and ambitious of stakeholders | Ngo Quang Huy | 2013-02-12 | Scope/Requirement | [7 empty] | Triggered
8 | Not enough knowledge about programming | Not be able to programing in java and android | Ngo Quang Huy | 2013-02-12 | Skills | [7 empty] | Triggered
9 | Difficult to communicate with customer | Can't establish meeting with customer regularly becasuse customer is too busy | Ngo Quang Huy | 2013-02-12 | Comunication | [7 empty] | Triggered
10 | Team member's laptop is decayed | To announce from team member | Ngo Quang Huy | 2013-02-12 | Resource | [7 empty] | Triggered
11 | A lots defect in architecture phase | Member lack of experience use to ACDM and design architecture | Ta Ngoc Thien Phu | 2013-04-12 | [8 empty] | Triggered
12 | Progress of architecture phase is slow | Not clearly understand to using ACDM, a lots defect is defined | Ta Ngoc Thien Phu | 2013-04-12 | [8 empty] | Triggered
13 | Lack of meeting place | no room to meeting | Ta Ngoc Thien Phu | 2013-04-12 | Resource | [7 empty] | Triggered
14 | lack of experience to manage project | Member lack of experience use to manage project on time and meet expectation | Ta Ngoc Thien Phu | 2013-04-12 | Skills | [7 empty] | Triggered
15 | Lack of skills about test tool | Member lack of experience use tool to test phase | Nguyen Phan Xuan Huy | 2013-04-12 | Technology | [7 empty] | Triggered
16 | Communicate about tester and developer | Can't understand between tester and developer | Nguyen Phan Xuan Huy | 2013-04-12 | Comunication | [7 empty] | Triggered
17 | test case pass not enough |  | Nguyen Phan Xuan Huy | 2013-04-12 | Controlling
18 | Team members have to focus on semester (I,II) | members of team no focus on capstone project because they must prepare for final subjects | Huynh Trong Khang | 2013-04-12 | Time | [7 empty] | Triggered
19 | Occurring conflict between team members | members can't understand together | Huynh Trong Khang | 2013-04-12 | Comunication | [7 empty] | Triggered
20 | Team members working not complete, working on time deadline |  | Huynh Trong Khang | 2013-04-12 | Performance
21 | Team members have illness, need a few days to rest |  | Huynh Trong Khang | 2013-04-12 | Resource
22 | Identify the scope unclear of project |  | Huynh Trong Khang | 2013-04-12 | Scope/Requirement
23 | Concentrate too much to elicit depth of detail requirement stage | focus too deep on high level requirement | Huynh Trong Khang | 2013-04-12 | Scope | [7 empty] | Triggered
24 | Exceeded time for requirement phase |  | Huynh Trong Khang | 2013-04-12 | Time
| avoid | go away far from that risk
| mitigate | use some method to control that risk
| accept | live with that risk
| identified | define risk
| analys complete | risk was analys
| planning complete | planning for control risk
| triggered | descrie risk
| resolved | risk wae mitgate

## risk priority (probability)
ID | Châu | Đạo | Q.Huy | X.Huy | Khang | Phú
1 |  | 40 |  |  |  | 60
2 |  | 40 |  |  |  | 40
3 |  | 60 |  |  |  | 40
4 |  | 40 |  |  |  | 60
5 |  | 30 |  |  |  | 50
6 |  | 60 |  |  |  | 50
7 |  | 30 |  |  |  | 40
8 |  | 50 |  |  |  | 50
9 |  | 30 |  |  |  | 45
10 |  | 40 |  |  |  | 30
11 |  | 50 |  |  |  | 80
12 |  | 80 |  |  |  | 85
13 |  | 80 |  |  |  | 80
14 |  | 60 |  |  |  | 60
15 |  | 50 |  |  |  | 70
16 |  | 30 |  |  |  | 40
17 |  | 50 |  |  |  | 80
18 |  | 70 |  |  |  | 90
19 |  | 60 |  |  |  | 70
20 |  | 60 |  |  |  | 80
21 |  | 60 |  |  |  | 70
22 |  | 60 |  |  |  | 65
23 |  | 50 |  |  |  | 60
24 |  | 60 |  |  |  | 70

## risk priority (impact)
ID | Châu | Đạo | Q.Huy | X.Huy | Khang | Phú
1 |  | 80 |  |  |  | 80
2 |  | 50 |  |  |  | 60
3 |  | 70 |  |  |  | 60
4 |  | 80 |  |  |  | 80
5 |  | 80 |  |  |  | 90
6 |  | 60 |  |  |  | 70
7 |  | 80 |  |  |  | 90
8 |  | 50 |  |  |  | 60
9 |  | 70 |  |  |  | 75
10 |  | 50 |  |  |  | 60
11 |  | 70 |  |  |  | 70
12 |  | 80 |  |  |  | 70
13 |  | 40 |  |  |  | 60
14 |  | 60 |  |  |  | 60
15 |  | 50 |  |  |  | 70
16 |  | 40 |  |  |  | 50
17 |  | 50 |  |  |  | 60
18 |  | 50 |  |  |  | 60
19 |  | 70 |  |  |  | 80
20 |  | 70 |  |  |  | 80
21 |  | 50 |  |  |  | 60
22 |  | 70 |  |  |  | 80
23 |  | 50 |  |  |  | 50
24 |  | 50 |  |  |  | 60