## Sheet1
|  | Step 1 : Risk Identification |  |  |  |  | Step 2 : Risk analysis |  |  |  | Step 3 : Response Planing |  | Step 4 : Risk management
Risk ID | List of poissible risk | Trigger | Raised By | Date Raises | Risk Category | Likelihood | Impact | Priority Score | Mitigation methods | Risk strategy | Response plan | Owner | Status | Note
1 | Requirements are misunderstood | No have a specific plan No meet customer regularly to review SRS | team | 2013-02-12
2 | Time is not enough for project development | The remaining time for project is not enough to implement remaining tasks in plan | team | 2013-02-13
3 | Communication between project team and stakeholder (mentor and customer) is not good | Mentor doesn’t know current progress of project Customer misjudge team’s ability | team | 2013-02-14
4 | Estimation is not well | We usually working over or behind schedule ( >10 task everyweek ) | team | 2013-02-15
5 | Many defects in product after release | Defects > 10 | team | 2013-02-16
6 | Don't complete the full functionality required | A few members lose trust in the group | team | 2013-02-17
7 | Morale of the team was down | Too difficult to do or manage time is unresonable | team | 2013-02-18
8 | The goal of stakeholders are different | Not understand about the ability and ambitious of stakeholders | team | 2013-02-19
9 | Members lack the knowledge of professional | Not understand what has been training about HVAC The new knowledge is very difficult | team | 2013-02-20
10 | Not enough knowledge about programming | Not be able to programing in C# and don't understand 3-tiers architecture | team | 2013-02-21
11 | Difficult to communicate with customer | Can't establish meeting with customer regularly becasuse customer is too busy | team | 2013-02-22
12 | Team member's laptop is decayed | To announce from team member | team | 2013-02-23
13 |  |  |  | 2013-02-24
14
| A lots defect in architecture phase | Member lack of experience use to ACDM and design architecture |  |  | Skills
| Progress of architecture phase is slow | Not clearly understand to using ACDM, a lots defect is defined |  |  | Time
| Difficult to use Scrum model | Almosst members first time use Scrum |  |  | Skills
| Lack of meeting place | Meeting room is not enough