## Team member
Chau Le
Dao Khau
Huy Ngo
Huy Nguyen
Khang Huynh
Phu Ta

## Chau Le
Admission System Project
Report date: 4/4/2014 |  |  | Phase: Daily report sprint 2
Reporter: Chau Le
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Prototype cho ứng dụng hiển thị bộ từ điển trên web application | High | 2014-02-04 | 2014-02-04 | Done |  | Chau Le
2 | Implement - File câu hình tập trung và phân tán | High | 2014-02-04 | 2014-02-04 | On-going |  | Chau Le
3 | Implement - Cập nhật bộ từ điển (hạ câu hỏi) | Medium | 2014-02-04 | 2014-02-04 | On-going |  | Chau Le
4
Plan for next days
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1 | hard to research config file
The most significance knowledge gained last week
# | Description
1
2
3

## Dao Khau
Admission System Project
Report date: 4/4/2014 |  |  | Phase: Daily report sprint 2
Reporter: Dao Khau
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Quản trị người dùng | High | 2014-02-04 | 2014-02-04 | On-going |  | Dao Khau
2 | Web serivce - Gửi index | High | 2014-03-04 | 2014-03-04 | On-going |  | Dao Khau
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Huy Ngo
Admission System Project
Report date: 4/4/2014 |  |  | Phase: Daily report sprint 2
Reporter: Huy Ngo
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Detail design cho ứng dụng hiển thị bộ từ điển trên web application | High | 2014-03-04 | 2014-03-04 | Done |  | Huy Ngo
2 | Web service - Nhận câu hỏi từ công cụ hiển thị | Medium | 2014-02-04 | 2014-02-04 | Done |  | Huy Ngo
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Huy Nguyen
Admission System Project
Report date: 4/4/2014 |  |  | Phase: Daily report sprint 2
Reporter: Huy Nguyen
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Test - Web serivce - Gửi index | Low | 2014-02-04 | 2014-02-04 | On-going |  | Huy Nguyen
2
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Khang Huynh
Admission System Project
Report date: 4/4/2014 |  |  | Phase: Daily report sprint 2
Reporter: Khang Huynh
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Implement - Đưa vào từ điển | High | 2014-03-04 | 2014-03-04 | On-going |  | Khang Huynh
2
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Phu Ta
Admission System Project
Report date: 4/4/2014 |  |  | Phase: Daily report sprint 2
Reporter: Phu Ta
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Implement - Tìm kiếm trên công cụ quản trị bộ từ điển | High | 2014-03-04 | 2014-03-04 | On-going |  | Phu Ta
2 | Implement - Tạo câu hỏi | High | 2014-02-04 | 2014-02-04 | Done |  | Phu Ta
3 | Implement - Các trạng thái trong bộ từ điển | Medium | 2014-02-04 | 2014-02-04 | Done |  | Phu Ta
4
Plan for next days
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3