## risk management
|  | Step 1 : Risk Identification |  |  |  |  | Step 2 : Risk analysis |  |  |  | Step 3 : Response Planing |  | Step 4 : Risk management
Risk ID | List of poissible risk | Trigger | Raised By | Date Raises | Risk Category | Probability | Impact | Priority Score | Mitigation methods | Risk strategy | Response plan | Owner | Status | Note
1 | Requirements are misunderstood | No have a specific plan No meet customer regularly to review product backlog & architectural drivers | team | 2013-02-12 | requirement | 0.66667 | 0.86667 | 0.57778
2 | Time is not enough for project development | The remaining time for project is not enough to implement remaining tasks in plan | team | 2013-02-12 | Time | 0.27333 | 0.86667 | 0.23689
3 | Communication between project team and stakeholder (mentor and customer) is not good | Mentor doesn’t know current progress of project Customer misjudge team’s ability | team | 2013-02-12 | Resource | 0.66667 | 0.86667 | 0.57778
4 | Estimation is not well | We usually working over or behind schedule ( >10 task everyweek ) | team | 2013-02-12 | Estimating | 0.66667 | 0.86667 | 0.57778
5 | Many defects in product after release | Defects > 10 | team | 2013-02-12 |  | 0.66667 | 0.86667 | 0.57778
6 | Don't complete the full functionality required | A few members lose trust in the group | team | 2013-02-12 | Performance | 0.66667 | 0.86667 | 0.57778
7 | Morale of the team was down | Too difficult to do or manage time is unresonable | team | 2013-02-12 | Resource | 0.66667 | 0.86667 | 0.57778
8 | The goal of stakeholders are different | Not understand about the ability and ambitious of stakeholders | team | 2013-02-12 | Scope/Requirement | 0.66667 | 0.86667 | 0.57778
9 | Members lack the knowledge of professional | The new knowledge is very difficult | team | 2013-02-12 |  | 0.66667 | 0.86667 | 0.57778
10 | Not enough knowledge about programming | Not be able to programing in java and android | team | 2013-02-12 | Skills | 0.66667 | 0.86667 | 0.57778
11 | Difficult to communicate with customer | Can't establish meeting with customer regularly becasuse customer is too busy | team | 2013-02-12 | Comunication | 0.66667 | 0.86667 | 0.57778
12 | Team member's laptop is decayed | To announce from team member | team | 2013-02-12 | Resource | 0.66667 | 0.86667 | 0.57778
13 | A lots defect in architecture phase | Member lack of experience use to ACDM and design architecture | Phu |  |  | 0.66667 | 0.86667 | 0.57778
14 | Progress of architecture phase is slow | Not clearly understand to using ACDM, a lots defect is defined | Phu |  |  | 0.66667 | 0.86667 | 0.57778
| Lack of meeting place | no room to meeting | Phu |  | Resource | 0.66667 | 0.86667 | 0.57778
| lack of experience to manage project | Member lack of experience use to manage project on time and meet expectation | Phu |  | Skills | 0.66667 | 0.86667 | 0.57778
| Lack of skills about test tool |  | Xuan Huy |  | Technology | 0.66667 | 0.86667 | 0.57778
| Communicate about tester and developer |  | Xuan Huy |  | Comunication | 0.66667 | 0.86667 | 0.57778
| pass k du testcase |  | Xuan Huy |  | Controlling | 0.66667 | 0.86667 | 0.57778
| Team members have to focus on semester (I,II) |  | Khang |  | Time | 0.66667 | 0.86667 | 0.57778
| Occurring conflict between team members |  | Khang |  | Comunication | 0.66667 | 0.86667 | 0.57778
| Team members working not complete, working on time deadline |  | Khang |  | Performance | 0.66667 | 0.86667 | 0.57778
| Team members have illness, need a few days to rest |  | Khang |  | Resource | 0.66667 | 0.86667 | 0.57778
| Identify the scope unclear of project |  | Khang |  | Scope/Requirement | 0.66667 | 0.86667 | 0.57778
| Concentrate too much to elicit depth of detail requirement stage |  | Khang |  | Scope | 0.66667 | 0.86667 | 0.57778
| Exceeded time for requirement phase |  | Khang |  | Time | 0.66667 | 0.86667 | 0.57778
| avoid | go away far from that risk
| mitigate | use some method to control that risk
| accept | live with that risk