## Sheet1
|  | Step 1 : Risk Identification |  |  |  |  | Step 2 : Risk analysis |  |  |  | Step 3 : Response Planing |  | Step 4 : Risk management
Risk ID | List of poissible risk | Trigger | Raised By | Date Raises | Risk Category | Likelihood | Impact | Priority Score | Mitigation methods | Risk strategy | Response plan | Owner | Status | Note
1 | Lack of skills about test tool | Áp dụng công cụ kiểm thử mới | Huy Nguyen | 4.12.2013 | Technology
2 | Problem about laptop | Laptop của thành viên gặp vấn đề (hư, mất,...) | Huy Nguyen | 4.12.2013 | Resource
3 | Communicate about tester and developer | Người kiểm thử và người phát triển mâu thuẫn trong quá trình kiểm thử | Huy Nguyen | 4.12.2013 | Comunication
4 | pass k du testcase
5 | A lots defect in architecture phase | Member lack of experience use to ACDM and design architecture |  |  | Skills
6 | Progress of architecture phase is slow | Not clearly understand to using ACDM, a lots defect is defined |  |  | Time
7 |  |  |  |  | Skills
8 | Lack of meeting place | no room to meeting
9 | lack of experience to manage project
10
11
12
13
14