## Team member
Chau Le
Dao Khau
Huy Ngo
Huy Nguyen
Khang Huynh
Phu Ta

## Recorded
RISK RECORDED
ID | Week | Risk | Plan/Methods
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
21 | 16 | Lack of team members | transfer tasks to another member
8 | 17 | Not enough knowledge about programming | Increase trainning per week about programming.
3 | 17 | Estimation is not well | Refer idea of experts
18
14 | 19 | lack of experience to manage project | consultation of the teachers
20