## Revision history
Document Reviewer Information
Reviewer Name | Review Attendance (R/S) | Comments
R/S: Required or Suggested participants or functions for the document review meeting
Document Approver Information
Approver Name | Approver Function | Comments
Document Revision History
Date | Revision | Status | Change Summary | Revised by | Version
25/11/2013 | design template | on going |  | Ngo Quang Huy | 1
2013-02-12 | update plan | on going |  | Ngo Quang Huy | 2

## Master design plan
MASTER DESIGN PLAN
CATEGORIES |  |  | ASSIGN | MAIN RESPONSIBLE | TIME
[5 empty] | START | FINISH | ACTUAL FINISH
STAGE 1 | Activities | Discover Architectural Drivers. | Team | Huynh Trong Khang | 26/11/2013 | 2013-02-12 | 2013-02-12
|  | meeting with customer #1 | Team |  | 28/11/2013 | 28/11/2013 | 28/11/2013
|  | Review with mentor #1 | Team |  | 29/11/2013 | 29/11/2013 | 29/11/2013
|  | Meeting with customer #2. | Team |  | 2013-03-12 | 2013-03-12 | 2013-03-12
|  | Meeting with mentor #2. | Team |  | 2013-03-12 | 2013-03-12 | 2013-03-12
|  | Review with customer #3. | Team |  | 2013-10-12 | 2013-10-12 | 2013-12-12
| Documents | Operation Requirement Document | Huynh Trong Khang |  | 26/11/2013 | 26/12/2013
|  | Review Operation Requirement Document. | Huynh Trong Khang |  | 2013-12-12 | 2013-12-12
STAGE 2 | Activities | Establish Project Scope. | Team | Huynh Trong Khang | 2013-12-12 | 2013-12-12
|  | Define entities Draw use-case model Create use-case description Create quality attribute scenario. | Team |  | 2013-12-12 | 16/12/2013 | 2013-09-12
|  | Review with mentor #1 | Team |  | 2013-12-12 | 2013-12-12 | 2013-12-12
|  | Meeting with customer #1 | Team |  | 17/12/2013 | 17/12/2013 | 19/12/2013
|  | Review with mentor #2 | Team |  | 19/12/2013 | 19/12/2013
|  | Review customer, mentor & closed architecture drivers specification & product backlog document. | Team |  | 24/12/2013 | 24/12/2013
| Documents | Architecture Drivers Specification | Team |  | 2013-12-11 | 22/12/2013 | 2013-09-12
|  | Product Backlog Document. | Team |  | 2013-12-11 | 22/12/2013
STAGE 3 | Activities |  |  | Tạ Ngọc Thien Phú
Documents
STAGE 4 | Activities |  |  | Nguyễn Phan Xuân Huy
Documents
STAGE 5 | Activities
Documents
STAGE 6 | Activities
Documents
STAGE 7 | Activities
Documents

## main filter
Member
Lê Ngọc Châu
Khấu Thành Đạo
Ngô Quang Huy
Nguyễn Phan Xuân Huy
Huỳnh Trọng Khang
Tạ Ngọc Thiên Phú