## LeNgocChau
Admission System Project
Report date: 9/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Dao Khau
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Code interface for change password | Medium | 2014-07-03 | 2014-07-03 | Done |  | Le Ngoc Chau
2 | Code interface for view profile | Medium | 2013-08-03 | 2014-08-03 | Done |  | Le Ngoc Chau
3
4
Plan for next days
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Update header and footer |  | 2014-09-03 |  |  |  | Le Ngoc Chau
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## KhauThanhDao
Admission System Project
Report date: 9/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Dao Khau
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Code interface with ckeditor | High | 2014-07-03 | 2014-08-03 | Done |  | Khau Thanh Dao
2 | Integrate inteface | High | 2014-07-03 | 2014-09-03 | On-going |  | Khau Thanh Dao
3
4
Plan for next days
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Code function checkbox in interface |  | 2014-09-03 |  |  |  | Khau Thanh Dao
2 | Integrate inteface |  | 2014-09-03 |  |  |  | Khau Thanh Dao
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## NgoQuangHuy
Admission System Project
Report date: 9/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Huy Ngo
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1
2
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## NguyenPhanXuanHuy
Admission System Project
Report date: 10/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Huy Nguyen
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Learning TFS | High | 2014-10-03 | 2014-10-03 | On-going |  | Nguyen Phan Xuan Huy
2 | Update testplan | High | 2014-10-03 | 2014-10-03 | On-going |  | Nguyen Phan Xuan Huy
3 | Learning Unit Test | Medium | 2014-10-03 | 2014-10-03 | On-going |  | Nguyen Phan Xuan Huy
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## HuynhTrongKhang
Admission System Project
Report date: 9/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Dao Khau
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Create business rule for Dictionary management on web application |  | 2014-07-03 | 2014-07-03 | Done |  | Huynh Trong Khang
2 | Create pagination, checkbox, security code interface |  | 2014-08-03 | 2014-08-03 | Done |  | Huynh Trong Khang
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Update dictionary-list interface |  | 2014-09-03 |  |  |  | Huynh Trong Khang
2 | Login with session on SpringMVC |  | 2014-09-03 |  |  |  | Huynh Trong Khang
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## TaNgocThienPhu
Admission System Project
Report date: 9/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Phu Ta
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Coding load list-question from db | High | 2014-07-03 | 2014-07-03 | On-going |  | Ta Ngoc Thien Phu
2 | design database intranet | High | 2014-07-03 | 2014-07-03 | On-going |  | Ta Ngoc Thien Phu
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1 | design database intranet |  | 2014-09-03 |  |  |  | Ta Ngoc Thien Phu
2 | Coding load list-question from db |  | 2014-09-03 |  |  |  | Ta Ngoc Thien Phu
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Team member
No | Team member
1 | Le Ngoc Chau
2 | Khau Thanh Dao
3 | Ngo Quang Huy
4 | Nguyen Phan Xuan Huy
5 | Huynh Trong Khang
6 | Ta Ngoc Thien Phu