## List main task
No | Activities
1 | Team Meetings
2 | Reading
3 | Self Prepare
4 | Team Home Work
5 | Team Work
6 | Meetings with Faculty
7 | Meetings with Customer
8 | Training
9 | Research
10 | Review with customer
11 | Review with technical support

## AS-PROJECT
Time Recording Log For: Capstone project | [5 empty] | Start Date: 08/11/2013 End Date:
Ta Ngoc Thien Phu - T101184
[7 empty] | Minimum: 5 hours/day 25 hours/week (5hours * 5 days) 700 hours/30 weeks (25 hours * 28 weeks) | Maximum: 24 hours/day 168 hours/week (24hours * 7 days) 4704 hours/30 weeks (168 hours * 28 weeks)
Week | Date | Start | Stop | Delta Time | Total time of day | Activity | Description | Artifact | Note
1 | 2013-11-08 | 1:00PM | 2:00PM | 1 | 1 | Kick off meeting |  |  |  | SUMMARY: TIME FOR DOING PROJECT | 85.51 | HOURS
2 | 2013-11-11 | 2:00PM | 3:30PM | 1.5 | 3 | Trainning | Quang Nguyen trainning ACDM |  |  | Time for doing week 1 | 1 | HOURS
| 2013-11-11 | 7:00PM | 8:30PM | 1.5 |  | Team Home Work | Define configuration management document and write meeting minutes of trainning ACDM |  |  | Time for doing week 2 | 16.3 | HOURS
| 2013-11-12 | 1:00PM | 3:00PM | 2 | 4 | Team meeting | _Discuss to team rule in team charter _Review project charter, communication plan, Configuration plan, Measurement plan, Weekly report and Timelog _Discuss to process model |  |  | Time for doing week 3 | 31.3 | HOURS
| 2013-11-12 | 9:00PM | 11:00PM | 2 |  | Team Home Work | _Review each stage in ACDM and role of ACDM _Update template configuration management document |  |  | Time for doing week 4 | 28.41 | HOURS
| 2013-11-13 | 1:30PM | 3:30PM | 2 | 2 | Team meeting | _Khang and Dao introduce about java spring core that they researched _Dao introduce about Maven and Hibernet _Khang introduce about Java 6 and Spring 3 |  |  | Time for doing week 5 | 8.5 | HOURS
| 2013-11-14 | 8:00AM | 9:00AM | 1 | 2.25 | Team work | Review development process of team |  |  | Time for doing week 6 | 0 | HOURS
| 2013-11-14 | 9:00AM | 10:15AM | 1.25 |  | Meetings with Faculty | Present work that team completed in this week |  |  | Time for doing week 7 | 0 | HOURS
| 2013-11-15 | 1:00PM | 2:05PM | 1.05 | 1.05 | Team meeting | Present about Scrum model, Risk management, Huy presnet spring framework |  |  | Time for doing week 8 | 0 | HOURS
| 2013-11-16 | 9:30PM | 10:30PM | 1 | 1 | Team Home Work | Research Srum model |  |  | Time for doing week 9 | 0 | HOURS
| 2013-11-17 | 7:30PM | 10:30PM | 3 | 3 | Team Home Work | Research Srum model (cont) Integrate ACDM to Scrum |  |  | Time for doing week 10 | 0 | HOURS
3 | 2013-11-18 | 9:00PM | 10:00PM | 1 | 1 | Team Home Work | Review Srcum that integrated ACDM |  |  | Time for doing week 11 | 0 | HOURS
| 2013-11-19 | 1:30PM | 2:30PM | 1 | 4.65 | Team meeting | 1/Present: -Change management document -Process of team -Test management document 2/Review time log |  |  | Time for doing week 12 | 0 | HOURS
|  | 4:30PM | 6:00PM | 1.5 |  | Team Home Work | Define architecture plan document Write meeting minutes | AS_AD_Architecture Plan.doxc |  | Time for doing week 13 | 0 | HOURS
|  | 9:00PM | 1:15PM | 2.15 |  | Team Home Work | Define team process document (use Scrum Model combine ACDM) | AS_PM_Deadline Team Process.doxc |  | Time for doing week 14 | 0 | HOURS
| 2013-11-20 | 1:30PM | 5:30PM | 4 | 4 | Team Home Work | Phu, Khang, Dao, Chau discuss about Scrum model combine ACDM Update architeture plan document and deadline team process document | AS_AD_Architecture Plan.doxc AS_PM_Deadline Team Process.doxc |  | Time for doing week 15 | 0 | HOURS
| 2013-11-21 | 8:00AM | 9:00AM | 1 | 9.65 | Team meeting | Prepare architecture plan and deadline team process to report with mentor | AS_AD_Architecture Plan.doxc AS_PM_Deadline Team Process.doxc |  | Time for doing week 16 | 0 | HOURS
|  | 9:00AM | 10:10AM | 1.16 |  | Meetings with Faculty | Report: -Change plan document -Requirement plan document -Architecture plan document -Master plan -Issue that team are meeting -Plan for next week |  |  | Time for doing week 17 | 0 | HOURS
|  | 10:10AM | 11:30AM | 1.33 |  | Team meeting | Divide ACDM task for each member |  |  | Time for doing week 18 | 0 | HOURS
|  | 1:30PM | 3:00PM | 1.5 |  | Team Home Work | Research chief architect role of ACDM and Stage 3 of ACDM |  |  | Time for doing week 19 | 0 | HOURS
|  | 3:00PM | 5:10PM | 2.16 |  | Team meeting | Report to research result |  |  | Time for doing week 20 | 0 | HOURS
|  | 9:00PM | 11:30PM | 2.5 |  | Team Home Work | Mapping ACDM to Scrum Model Mapping role of ACDM to role of Scrum Update Deadline Team process | AS_PM_Deadline Team Process.doxc |  | Time for doing week 21 | 0 | HOURS
| 2013-11-22 | 1:30PM | 3:00PM | 1.5 | 5.5 | Team meeting | Report research result about Scrum Divide task about Scrum continuous | AS_PM_Deadline Team Process.doxc |  | Time for doing week 22 | 0 | HOURS
|  | 3:00PM | 4:30PM | 1.5 |  | Team Home Work | Drawing Scrum model that have use ACDM Description for Scrum model | AS_PM_Deadline Team Process.doxc |  | Time for doing week 23 | 0 | HOURS
|  | 8:30PM | 11:00PM | 2.5 |  | Team Home Work | Update Deadline team process document Update Architect Plan | AS_AD_Architecture Plan.doxc AS_PM_Deadline Team Process.doxc |  | Time for doing week 24 | 0 | HOURS
| 2013-11-23 | 1:30PM | 3:00PM | 1.5 | 2.5 | Team meeting | Discuss about Scrum model that is draw by IDEF0 Divide task about Scrum continuous |  |  | Time for doing week 25 | 0 | HOURS
|  | 10:30PM | 11:30PM | 1 |  | Team Home Work | Define table that show description of phase 3 ACDM, inculde Name Steps, image of Process, description Write Meeting Minutes | AS_AD_Architecture Plan.doxc |  | Time for doing week 26 | 0 | HOURS
| 2013-11-24 | 8:00AM | 12:00PM | 4 | 4 | Trainning | Trainning Java at Nhat Nghe Center |  |  | Time for doing week 27 | 0 | HOURS
4 | 2013-11-25 | 2:00PM | 4:00PM | 2 | 2 | Team Home Work | Update Architecture Plan |  |  | Time for doing week 28 | 0 | HOURS
| 2013-11-26 | 9:00AM | 11:30PM | 2.5 | 5.25 | Meetings with Faculty | Report content that team will do it on the week before |  |  | Time for doing week 29 | 0 | HOURS
|  | 1:30PM | 2:45PM | 1.25 |  | Team meeting | Overview RE phase, divide module for each member to reaserch and give question for this module that members is assigned |  |  | Time for doing week 30 | 0 | HOURS
|  | 9:30PM | 11:90PM | 1.5 |  | Team Home Work | Brainstroming and give question that related to module Question & Anwser
| 2013-11-27 | 12:30PM | 1:30PM | 1 | 3.33 | Team Home Work | Write meeting minustes
|  | 1:30PM | 3:50PM | 2.33 |  | Team meeting | Discuss about question that is used to ask customer in each module Discuss Scrum model with Mrs.Hong
| 2013-11-28 | 8:00AM | 9:15AM | 1.33 | 8.33 | Team Home Work | Review question have prepared for system
|  | 9:15AM | 11:00AM | 1.75 |  | Meetings with Customer | Collect raw architect drivers and develop user stories
|  | 1:30PM | 4:15PM | 2.75 |  | Team Meetings | Analyse architect drivers
|  | 9:00PM | 11:30PM | 2.5 |  | Team Home Work | Write meeting minustes Draw Activity digram of Functional Tim Kiem and Chuyen Tin
| 2013-11-29 | 1:30PM | 5:00PM | 3.5 | 4.5 | Team meeting | Discuss and draw activity diagram of module Ban Tin, Hoi-Dap Design interface of system Divide task Update time log
|  | 10:30PM | 11:30PM | 1 |  | Team Home Work | Write meeting minustes Update time log
| 2013-12-01 | 12:30PM | 4:00PM | 3.5 | 5 | Team Home Work | Write Functional, Quality Attribute and Entity of Module Soan Tin
|  | 7:00PM | 8:30PM | 1.5 |  | Team Home Work | Update Functional, Quality Attribute and Entity of Module Soan Tin Update timlog
5 | 2013-12-02
| 2013-12-03 | 6:30PM | 10:30PM | 4 | 4 | Team Home Work | Update Entity Write Use case Update architecture plan document
| 2013-12-04 | 1:30PM | 6:00PM | 4.5 | 4.5 | Team Meeting | Review documents: Master plan Risk management Measuremet Process Entities
2013-12-05
2013-12-06
6 | 2013-12-09
2013-12-10
2013-12-11
2013-12-12
2013-12-13
7 | 2013-12-16
2013-12-17
2013-12-18
2013-12-19
2013-12-20
8 | 2013-12-23
2013-12-24
2013-12-25
2013-12-26
2013-12-27
9 | 2013-12-30
2013-12-31
2014-01-01
2014-01-02
2014-01-03
10 | 2014-01-06
2014-01-07
2014-01-08
2014-01-09
2014-01-10
11 | 2014-01-13
2014-01-14
2014-01-15
2014-01-16
2014-01-17
12 | 2014-01-20
2014-01-21
2014-01-22
2014-01-23
2014-01-24
13 | 2014-01-27 |  |  |  |  | Nghỉ tết
| 2014-01-28 |  |  |  |  | Nghỉ tết
| 2014-01-29 |  |  |  |  | Nghỉ tết
| 2014-01-30 |  |  |  |  | Nghỉ tết
| 2014-01-31 |  |  |  |  | Nghỉ tết
14 | 2014-02-03 |  |  |  |  | Nghỉ tết
| 2014-02-04 |  |  |  |  | Nghỉ tết
| 2014-02-05 |  |  |  |  | Nghỉ tết
| 2014-02-06 |  |  |  |  | Nghỉ tết
| 2014-02-07 |  |  |  |  | Nghỉ tết
15 | 2014-02-10
2014-02-11
2014-02-12
2014-02-13
2014-02-14
16 | 2014-02-17
2014-02-18
2014-02-19
2014-02-20
2014-02-21
17 | 2014-02-24
2014-02-25
2014-02-26
2014-02-27
2014-02-28
18 | 2014-03-03
2014-03-04
2014-03-05
2014-03-06
2014-03-07
19 | 2014-03-10
2014-03-11
2014-03-12
2014-03-13
2014-03-14
20 | 2014-03-17
2014-03-18
2014-03-19
2014-03-20
2014-03-21
21 | 2014-03-24
2014-03-25
2014-03-26
2014-03-27
2014-03-28
22 | 2014-03-31
2014-04-01
2014-04-02
2014-04-03
2014-04-04
23 | 2014-04-07
2014-04-08
2014-04-09
2014-04-10
2014-04-11
24 | 2014-04-14
2014-04-15
2014-04-16
2014-04-17
2014-04-18
25 | 2014-04-21
2014-04-22
2014-04-23
2014-04-24
2014-04-25
26 | 2014-04-28
2014-04-29
2014-04-30
2014-05-01
2014-05-02
27 | 2014-05-05
2014-05-06
2014-05-07
2014-05-08
2014-05-09
28 | 2014-05-12
2014-05-13
2014-05-14
2014-05-15
2014-05-16
29 | 2014-05-19
2014-05-20
2014-05-21
2014-05-22
2014-05-23
30 | 2014-05-26
2014-05-27
2014-05-28
2014-05-29
2014-05-30
2014-05-31
2014-06-01
2014-06-02
2014-06-03
2014-06-04
2014-06-05
2014-06-06
2014-06-07
2014-06-08
2014-06-09
2014-06-10
2014-06-11
2014-06-12
2014-06-13
2014-06-14
2014-06-15
2014-06-16
2014-06-17
2014-06-18
2014-06-19
2014-06-20
2014-06-21
2014-06-22
2014-06-23
2014-06-24
2014-06-25
2014-06-26
2014-06-27
2014-06-28
2014-06-29
2014-06-30
2014-07-01
2014-07-02
2014-07-03
2014-07-04