## LeNgocChau
Admission System Project
Report date: 21/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Le Ngoc Chau
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Code change password | Medium | 19/3/2014 | 19/3/2014 | Done |  | Le Ngoc Chau
2
3
4
Plan for next days
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1 | Can not compare new password with confirm password |  |  | Dao Khau help to validate code
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## KhauThanhDao
Admission System Project
Report date: 21/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Khau Thanh Dao
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Integrate code | High | 19/3/2014 | 20/3/2014 | On-going |  | Khau Thanh Dao
2 | Check data in view layer | Medium | 19/3/2014 | 20/3/2014 | Done |  | Khau Thanh Dao
3 | Pagination | High | 19/3/2014 | 20/3/2014 | On-going |  | Khau Thanh Dao
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Integrate code |  | 21/3/2014 |  |  |  | Khau Thanh Dao
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## NgoQuangHuy
Admission System Project
Report date: 21/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Ngo Quang Huy
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | coding xem thông tin người dùng | medium | 20/03/2014 | 20/03/2015 | Done |  | Ngo Quang Huy
2
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## NguyenPhanXuanHuy
Admission System Project
Report date: 21/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Nguyen Phan Xuan Huy
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Update UAT | High | 03.19.2014 | 03.20.2014 | On-going |  | Nguyen Phan Xuan Huy
2 | Update testcase on TFS | High | 03.19.2014 | 03.20.2014 | On-going |  | Nguyen Phan Xuan Huy
3 | Update defect report, test report | High | 03.19.2014 | 03.20.2014 | On-going |  | Nguyen Phan Xuan Huy
4 | Test Send mail |  | 03.19.2014 | 03.19.2014 | Done |  | Nguyen Phan Xuan Huy
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Update testcase on TFS |  | 03.20.2014 |  |  |  | Nguyen Phan Xuan Huy
2 | Update defect report, test report |  | 03.20.2014 |  |  |  | Nguyen Phan Xuan Huy
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1 | Chưa quen với quản lí công việc trên TFS
The most significance knowledge gained last week
# | Description
1
2
3

## HuynhTrongKhang
Admission System Project
Report date: 21/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Huynh Trong Khang
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Coding put Q/A into dictionary |  | 19/3/2014 | 19/3/2014 | On-going | Can't excute insert statement to dictionary list | Huynh Trong Khang
2 | Coding loading page |  | 20/3/2014 | 20/3/2014 | Done |  | Huynh Trong Khang
3 | Resarch pagination |  | 20/3/2014 | 20/3/2014 | Done |  | Huynh Trong Khang
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Coding put Q/A into dictionary |  | 21/3/2014 |  |  |  | Huynh Trong Khang
2 | Excute test cases have assiged |  | 22/3/2014 |  |  |  | Huynh Trong Khang
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## TaNgocThienPhu
Admission System Project
Report date: 21/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Ta Ngoc Thien Phu
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Coding dictionary-recent tab | High | 19/3/2014 | 19/3/2014 | Done |  | Ta Ngoc Thien Phu
2 | Coding dictionary-delete tab | High | 19/3/2014 | 19/3/2014 | Done |  | Ta Ngoc Thien Phu
3
4
Plan for next days
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Research password MD5 |  | 21/3/2014 |  |  |  | Ta Ngoc Thien Phu
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Team member
No | Team member
1 | Le Ngoc Chau
2 | Khau Thanh Dao
3 | Ngo Quang Huy
4 | Nguyen Phan Xuan Huy
5 | Huynh Trong Khang
6 | Ta Ngoc Thien Phu