## Sp1 - 5.3.2014
Admission System Project
Report date: 5/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Dao Khau
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Code interface for dictionary-list | Medium | 2014-03-03 | 2014-03-03 | Done
2 | Ajax for load page | High | 2014-03-03 | 2014-04-03 | Done
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Implement login to understand webflow |  | 2014-05-03
2 | Update user dictionary-list interface |  | 2014-05-03
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1 | How to convert psd to HTML
2 | Knowledge about springMVC flow
3

## Sp1 - 7.3.2014
Admission System Project
Report date: 7/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Dao Khau
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Implement login | Medium | 2014-05-03 | 2014-05-03 | Done
2 | Update dictionary-list interface | Medium | 2014-05-03 | 2014-05-03 | Done
3 | Update login, register, menu interface | Medium | 2014-06-03 | 2014-06-03 | Done
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Create business rule for Dictionary management on web application |  | 2014-07-03
2 | Create pagination, checkbox, security code |  | 2014-07-03
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Done |  | Owner
1 |  |  |  |  | Done
The most significance knowledge gained last week
# | Description
1
2
3

## Sp1 - 9.3.2014
Admission System Project
Report date: 9/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Dao Khau
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Create business rule for Dictionary management on web application |  | 2014-07-03 | 2014-07-03 | Done
2 | Create pagination, checkbox, security code interface |  | 2014-08-03 | 2014-08-03 | Done
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Update dictionary-list interface |  | 2014-09-03
2 | Login with session on SpringMVC |  | 2014-09-03
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Sp1 - 11.3.2014
Admission System Project
Report date: 9/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Dao Khau
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Update dictionary-list interface |  | 2014-09-03 | 2014-10-03 | Done
2 | Login with session on SpringMVC |  | 2014-09-03 | 2014-10-03 | On-going
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Update dictionary-list interface |  | 2014-11-03
2 | Research and implements send mail on SpringMVC |  | 2014-12-03
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Team member
Chau Le
Dao Khau
Huy Ngo
Huy Nguyen
Khang Huynh
Phu Ta