## risk management
|  | Step 1 : Risk Identification |  |  |  |  | Step 2 : Risk analysis |  |  |  | Step 3 : Response Planing |  | Step 4 : Risk management
Risk ID | List of poissible risk | Trigger | Raised By | Date Raises | Risk Category | Probability | Impact | Priority Score | Mitigation methods | Risk strategy | Response plan | Owner | Status | Note
1 | Requirements are misunderstood | No have a specific plan No meet customer regularly to review product backlog & architectural drivers | Ngo Quang Huy | 2013-02-12 | requirement | 0.66667 | 0.86667 | 0.57778 |  |  |  |  | Triggered
2 | Time is not enough for project development | The remaining time for project is not enough to implement remaining tasks in plan | Ngo Quang Huy | 2013-02-12 | Time | 0.27333 | 0.86667 | 0.23689 |  |  |  |  | Triggered
3 | Communication between project team and stakeholder (mentor and customer) is not good | Mentor doesn’t know current progress of project Customer misjudge team’s ability | Ngo Quang Huy | 2013-02-12 | Resource | [7 empty] | Triggered
4 | Estimation is not well | We usually working over or behind schedule ( >10 task everyweek ) | Ngo Quang Huy | 2013-02-12 | Estimating | [7 empty] | Triggered
5 | Many defects in product after release | Defects > 10 | Ngo Quang Huy | 2013-02-12 | [8 empty] | Triggered
6 | Don't complete the full functionality required | A few members lose trust in the group | Ngo Quang Huy | 2013-02-12 | Performance | [7 empty] | Triggered
7 | Morale of the team was down | Too difficult to do or manage time is unresonable | Ngo Quang Huy | 2013-02-12 | Resource | [7 empty] | Triggered
8 | The goal of stakeholders are different | Not understand about the ability and ambitious of stakeholders | Ngo Quang Huy | 2013-02-12 | Scope/Requirement | [7 empty] | Triggered
10 | Not enough knowledge about programming | Not be able to programing in java and android | Ngo Quang Huy | 2013-02-12 | Skills | [7 empty] | Triggered
11 | Difficult to communicate with customer | Can't establish meeting with customer regularly becasuse customer is too busy | Ngo Quang Huy | 2013-02-12 | Comunication | [7 empty] | Triggered
12 | Team member's laptop is decayed | To announce from team member | Ngo Quang Huy | 2013-02-12 | Resource | [7 empty] | Triggered
13 | A lots defect in architecture phase | Member lack of experience use to ACDM and design architecture | Ta Ngoc Thien Phu | 2013-04-12 | [8 empty] | Triggered
14 | Progress of architecture phase is slow | Not clearly understand to using ACDM, a lots defect is defined | Ta Ngoc Thien Phu | 2013-04-12 | [8 empty] | Triggered
15 | Lack of meeting place | no room to meeting | Ta Ngoc Thien Phu | 2013-04-12 | Resource | [7 empty] | Triggered
16 | lack of experience to manage project | Member lack of experience use to manage project on time and meet expectation | Ta Ngoc Thien Phu | 2013-04-12 | Skills | [7 empty] | Triggered
17 | Lack of skills about test tool | Member lack of experience use tool to test phase | Nguyen Phan Xuan Huy | 2013-04-12 | Technology | [7 empty] | Triggered
18 | Communicate about tester and developer | Can't understand between tester and developer | Nguyen Phan Xuan Huy | 2013-04-12 | Comunication | [7 empty] | Triggered
19 | test case pass not enough |  | Nguyen Phan Xuan Huy | 2013-04-12 | Controlling
20 | Team members have to focus on semester (I,II) | members of team no focus on capstone project because they must prepare for final subjects | Huynh Trong Khang | 2013-04-12 | Time | [7 empty] | Triggered
21 | Occurring conflict between team members | members can't understand together | Huynh Trong Khang | 2013-04-12 | Comunication | [7 empty] | Triggered
22 | Team members working not complete, working on time deadline |  | Huynh Trong Khang | 2013-04-12 | Performance
23 | Team members have illness, need a few days to rest |  | Huynh Trong Khang | 2013-04-12 | Resource
24 | Identify the scope unclear of project |  | Huynh Trong Khang | 2013-04-12 | Scope/Requirement
25 | Concentrate too much to elicit depth of detail requirement stage | focus too deep on high level requirement | Huynh Trong Khang | 2013-04-12 | Scope | [7 empty] | Triggered
26 | Exceeded time for requirement phase |  | Huynh Trong Khang | 2013-04-12 | Time
| avoid | go away far from that risk
| mitigate | use some method to control that risk
| accept | live with that risk
| identified | define risk
| analys complete | risk was analys
| planning complete | planning for control risk
| triggered | descrie risk
| resolved | risk wae mitgate