## List main task
No | Activities
1 | Team Meetings
2 | Reading
3 | Self Prepare
4 | Team Home Work
5 | Team Work
6 | Meetings with Faculty
7 | Meetings with Customer
8 | Training
9 | Research
10 | Review with customer
11 | Review with technical support

## SEP-PROJECT
Time Recording Log For: Admission project | [6 empty] | Start Date: 08/11/2013 End Date:
Ta Ngoc Thien Phu - T101184
[8 empty] | Minimum: 5 hours/day 25 hours/week (5hours * 5 days) 700 hours/30 weeks (25 hours * 28 weeks) | Maximum: 24 hours/day 168 hours/week (24hours * 7 days) 4704 hours/30 weeks (168 hours * 28 weeks)
Week | Date | Start | Stop | Delta Time | Total time of day | Plan | Activity | Description | Artifact | Note | SUMMARY: TIME FOR DOING PROJECT | 1075 | HOURS
1 | 2013-11-07 | 13:20 | 14:30 | 1.16 | 1.16 |  | Team meeting | - Repair for kick off meeting - Devide team work for team member - Define role in project |  |  | SUMMARY: TIME FOR DOING PROJECT | 339.03 | HOURS
| 2013-11-08 | 14:00 | 15:10 | 1.16 | 1.66 |  | Kick off meeting | - Discuss about communication plan between customer and team - Discuss about system concept |  |  | Time for doing week 1 | 2.82 | HOURS
|  | 15:10 | 15:40 | 0.5 |  |  | Meetings with Faculty | - Discus about weekly report meeting |  |  | Time for doing week 2 | 11.5 | HOURS
2 | 2013-11-11 | 14:00 | 15:30 | 1.5 | 3 |  | Training | - Training ACDM | - Java Overview + Spring.docx - Training.pptx |  | Time for doing week 3 | 24.55 | HOURS
|  | 19:00 | 20:30 | 1.5 |  |  | Team Home Work | Define configuration management document and write meeting minutes of trainning ACDM |  |  | Time for doing week 4 | 27.83 | HOURS
| 2013-11-12 | 13:45 | 15:00 | 1.25 | 1.25 |  | Team Meetings | - Review Team charter - Review Communication plan - Review Configuration plan - Review Measurement plan | - AS_PM_TeamCharter.docx version 1.0 - AS_PM _ConfigurationPlan.docx version 1.0 - AS_PM_CommunicationPlan.docx version 1.0 - AS_PM_MeasurementPlan.docx version 1.0 |  | Time for doing week 5 | 16.33 | HOURS
|  | 21:00 | 23:00 | 2 |  |  | Team Home Work | _Review each stage in ACDM and role of ACDM _Update template configuration management document
| 2013-11-13 | 13:30 | 15:30 | 2 | 2 |  | Team Meetings | - Review Maven, Spring, Hibernate, Java | - Training Document |  | Time for doing week 6 | 18.5 | HOURS
| 2013-11-14 | 8:00 | 9:00 | 1 | 2.25 |  | Team work | Review development process of team |  |  | Time for doing week 8 | 28.25 | HOURS
|  | 9:00 | 10:15 | 1.25 |  |  | Meetings with Faculty | - Present work that team completed in this week 2 | - AS_DeadlineTeam_Week2.pptx |  | Time for doing week 09 | 22.25 | HOURS
| 2013-11-15 | 13:00 | 14:00 | 1 | 1 |  | Team Meetings | - Ngo Quang Huy present about Risk management plan - Nguyen Phan Xuan Huy present about spring framwork |  |  | Time for doing week 10 | 31.5 | HOURS
3 | 2013-11-16 | 21:30 | 22:30 | 1 |  |  | Team Home Work | Research Srum model
| 2013-11-17 | 19:30 | 22:30 | 3 |  |  | Team Home Work | Research Srum model (cont) Integrate ACDM to Scrum
| 2013-11-18 | 15:00 | 16:00 | 1 | 1 |  | Team Home Work | Review Srcum that integrated ACDM |  |  | Time for doing week 12 | 19.5 | HOURS
| 2013-11-19 | 13:30 | 14:30 | 1 | 4.65 |  | Team Meetings | - Review Change management plan - Review Scrum modal and ACDM - Review Test management plan |  |  | Time for doing week 14 | 0 | HOURS
|  | 16:30 | 18:00 | 1.5 |  |  | Team Home Work | Define architecture plan document Write meeting minutes | AS_AD_Architecture Plan.doxc
|  | 21:00 | 13:15 | 2.15 |  |  | Team Home Work | Define team process document (use Scrum Model combine ACDM) | AS_PM_Deadline Team Process.doxc |  | Time for doing week 15 | 16 | HOURS
| 2013-11-20 | 13:30 | 17:30 | 4 | 4 |  | Team Home Work | Phu, Khang, Dao, Chau discuss about Scrum model combine ACDM Update architeture plan document and deadline team process document | AS_AD_Architecture Plan.doxc AS_PM_Deadline Team Process.doxc |  | Time for doing week 16 | 28 | HOURS
| 2013-11-21 | 8:00 | 9:00 | 1 | 8.65 |  | Team work | Prepare architecture plan and deadline team process to report with mentor | AS_AD_Architecture Plan.doxc AS_PM_Deadline Team Process.doxc
|  | 9:00 | 10:10 | 1.16 |  |  | Meetings with Faculty | - Present about work that assigned in week3 - Present about Change management plan - Present about ACDM and Scrum model - Present about Requirement plan |  |  | Time for doing week 17 | 26.5 | HOURS
|  | 10:10 | 11:30 | 1.33 |  |  | Team Meetings | - Devide work for week 4 |  |  | Time for doing week 18 | 44 | HOURS
|  | 1:30PM | 3:00PM | 1.5 |  |  | Team Home Work | Research chief architect role of ACDM and Stage 3 of ACDM |  |  | Time for doing week 19 | 21.5 | HOURS
|  | 15:00 | 17:10 | 2.16 |  |  | Team Meetings | - Integrate the work of member about ACDM - Devide team work for team member |  |  | Time for doing week 20 | 0 | HOURS
|  | 21:00 | 23:30 | 2.5 |  |  | Team Home Work | Mapping ACDM to Scrum Model Mapping role of ACDM to role of Scrum Update Deadline Team process | AS_PM_Deadline Team Process.doxc |  | Time for doing week 21 | 0 | HOURS
| 2013-11-22 | 13:30 | 14:45 | 1.25 | 5.25 |  | Team Meetings | - Review Scrum model - Review Scrum role and responsibility - Review how to map ACDM into Scrum - Devide team work for team member |  |  | Time for doing week 22 | 0 | HOURS
|  | 15:00 | 16:30 | 1.5 |  |  | Team Home Work | Drawing Scrum model that have use ACDM Description for Scrum model | AS_PM_Deadline Team Process.doxc |  | Time for doing week 23 | 0 | HOURS
|  | 20:30 | 23:00 | 2.5 |  |  | Team Home Work | Update Deadline team process document Update Architect Plan | AS_AD_Architecture Plan.doxc AS_PM_Deadline Team Process.doxc |  | Time for doing week 24 | 0 | HOURS
4 | 2013-11-23 | 13:00 | 13:45 | 0.75 | 1.75 |  | Team Meetings | - Review process, document, template |  |  | Time for doing week 25 | 0 | HOURS
|  | 22:30 | 23:30 | 1 |  |  | Team Home Work | Define table that show description of phase 3 ACDM, inculde Name Steps, image of Process, description Write Meeting Minutes | AS_AD_Architecture Plan.doxc |  | Time for doing week 26 | 0 | HOURS
| 2013-11-24 | 8:00 | 12:00 | 4 |  |  | Trainning | Trainning Java at Nhat Nghe Center
| 2013-11-25 | 14:00 | 16:00 | 2 | 2 |  | Team Home Work | Update Architecture Plan |  |  | Time for doing week 27 | 0 | HOURS
| 2013-11-26 | 9:00 | 23:30 | 2.5 |  |  | Meetings with Faculty | - Reivew process - Review Communication plan - Review Change management plan - Review Risk management plan - Review Measurement plan - Review timelog template, daily report - Review weekly report - Review requirement plan - Review Operation Requirement - Review Architecture plan - Architectural drivers template - Architecture design document template - Review test plan, test case template, test report template |  |  | Time for doing week 29 | 0 | HOURS
|  | 1.30 PM | 14:30 | 1 |  |  | Team Meetings | - Devide work task about Stage 1 elicite |  |  | Time for doing week 30 | 0 | HOURS
|  | 21:30 | 0:00 | 1.5 |  |  | Team Home Work | Brainstroming and give question that related to module Question & Anwser
| 2013-11-27 | 12:30 | 13:30 | 1 | 2.33 |  | Team Home Work | Write meeting minustes
|  | 13:30 | 15:50 | 2.33 |  |  | Team Meetings | - Repair question for meeting with customer
| 2013-11-28 | 8:00 | 9:15 | 1.25 | 5.75 |  | Team Home Work | Review question have prepared for system
|  | 9:15 | 11:00 | 1.75 |  |  | Meetings with Customer | - Get requirement about admission system
|  | 13:30 | 16:15 | 2.75 |  |  | Team Meetings | - Analyse architect drivers to raw Admission system (News module and Category module) - Draw activity diagrams business process
|  | 21:00 | 23:30 | 2.5 |  |  | Team Home Work | Write meeting minustes Draw Activity digram of Functional Tim Kiem and Chuyen Tin
| 2013-11-29 | 13:30 | 17:00 | 3.5 | 3.5 |  | Team Meetings | - Discuss about functions that supported by prouct owners
|  | 22:30 | 23:30 | 1 |  |  | Team Home Work | Write meeting minustes Update time log
5 | 2013-12-01 | 12:30 | 16:00 | 3.5 |  |  | Team Home Work | Write Functional, Quality Attribute and Entity of Module Soan Tin
|  | 19:00 | 20:30 | 1.5 |  |  | Team Home Work | Update Functional, Quality Attribute and Entity of Module Soan Tin Update timlog
| 2013-12-03 | 9.00 AM | 10.30 AM | 1.5 | 9.5 |  | Meetings with Customer | - Discuss entities and collection document + Rework entities + Implement analysis document <Archi Driver specification>
|  | 10:30 | 11:00 | 0.5 |  |  | Team Meatings | - Discuss about document
|  | 13:30 | 17:00 | 3.5 |  |  | Training | - First Training Java + Spring with Mr. Thanh + Setup nessecsary tools + Understand DI and AOP in Spring framework + Demo Hello world with Spring
|  | 18:30 | 22:30 | 4 |  |  | Team Home Work | Update Entities Write Use case Update architecture plan document Update timelog
| 2013-12-04 | 13:30 | 18:00 | 4.5 | 4.5 |  | Team Mettings | - Review list risk, measurement plan - Review master plan, master design plan - Reivew project plan - Review entities
| 2013-12-05 | 9:10 | 10:40 | 1.5 | 2.33 |  | Meetings with Faculty | - Review List risk, measurement plan - Review master plan, master design plan - Review project plan - Review sprint backlog template
|  | 10:40 | 11:30 | 0.83 |  |  | Team Meetings | - Devide team work - Update entities
| 2013-12-07 | 22:30 | 0:30 | 1.5 |  |  | Team Home Work | Write meeting minutes 4/12/2013 and 5/12/2013 | Meeting_Minutes_041213.doc Meeting_Minutes_051213.doc
| 2013-12-08 | 14:30 | 15:30 | 1 |  |  | Team Home Work | Priority and solution for risk list
|  | 19:30 | 23:00 | 3.5 |  |  | Team Home Work | Fix and update use case, quality attribute Create Architecture Schedule Create template Detail Design Document Draw use case diagram | AS_PM_Architecture Plan.docx AS_AD_Detail Design.docx
6 | 2013-12-09 | 13:30 | 18:00 | 4.5 | 4.5 |  | Team Meetings | - Collection and update driver specification document + Usecase diagram + Quality Attribute - Pioritize risk - Update requirement plan - schedule
| 2013-12-10 | 9:00 | 11:30 | 2.5 | 5 |  | Training | - Training spring frame work
|  | 1:30 | 16:00 | 2.5 |  |  | Training | - Training spring core + MySQL + Insert/Update/Delete
| 2013-12-12 | 9:00 | 11:00 | 2 | 6 |  | Meeting with Faculty | - Review project plan,risk management….
|  | 11:00 | 12:00 | 1 |  |  | Team Meetings | - Discuss about team work
|  | 14:00 | 17:00 | 3 |  |  | Meetings with Customer | - Review architecturals drivers specification
| 2013-12-13 | 14:00 | 17:00 | 3 | 3 |  | Team Work | Update use case diagram SoanTin module Draw interface of SoanTin module
7 | 2013-12-14 | 13:30 | 17:00 | 3.5 | 3.5 | 5 | Training | - Training code
| 2013-12-15 | 14:00 | 15:00 | 1 |  |  | Team Home Work | Update QA + Entity of SoanTin module
|  | 19:30 | 21:00 | 1.5 |  |  | Team Home Work | Update use case diagram + use case description of SoanTin module update timelog
| 2013-12-16 | 14:00 | 17:00 | 3 | 3 | 5 | Team Work | Research Java with team
| 2013-12-17 | 13:30 | 15:30 | 2 |  |  | Training | - Training validation with spring in Java
| 2013-12-18 | 13:30 | 16:00 | 2.5 | 5.5 | 5 | Team Meetings | - Review documents for mentor meetings at 19/12
|  | 19:00 | 22:00 | 3 |  |  | Team Home Work | Update Entity, Use case diagram Soan Tin | AS_RE_ArchitectureDriverSpecification-VN-version-0.6
| 2013-12-19 | 8:00 | 9:00 | 1 | 6.33 | 5 | Team Work | - Review usecase, entities | - AS_RE_ArchitectureDriverSpecification-VN-version.docx
|  | 9:10 | 10:30 | 1.33 |  |  | Meetings with Faculty | - Review project plan - Reivew requirement plan
|  | 10:30 | 12:00 | 1.5 |  |  | Team Meetings | - Devide work for next week - Review use case, entities
|  | 14:00 | 16:30 | 2.5 |  |  | Meetings with Customer | - Review Entity
|  | 21:30 | 23:00 | 1.5 |  |  | Team Home Work | Write meeting minutes 19/12/2013 Update timelog
| 2013-12-20 | 21:00 | 12:00 | 3 | 3 | 5 | Team Home Work | Edit entity + use case Soan Tin
8 | 2013-12-23 | 9:00 | 11:30 | 2.5 | 4 | 5 | Training | - Java: configuation and validator a form
|  | 21:30 | 23:00 | 1.5 |  |  | Team Home Work | Edit entity hoi dap follow Customer comments
| 2013-12-24 | 8:00 | 9:00 | 1 | 5 | 5 | Team Work | Prepare document for meeting with customer
|  | 9:00 | 11:00 | 2 |  |  | Meetings with Customer | - Review entity, usecase and QA and comment
|  | 13:30 | 15:30 | 2 |  |  | Training | - Review all
|  | 21:00 | 23:30 | 2.5 |  |  | Team Home Work | Edit Quality Attribute Update time log
| 2013-12-25 | 22:30 | 23:00 | 0.5 | 3.5 | 5 | Team Home Work | Update timelog
|  | 13:30 | 17:00 | 3.5 |  |  | Team Mettings | - Update timlog - Update individual evaluation - Integration QA and entity
| 2013-12-26 | 9:15 | 10:00AM | 0.75 |  |  | Meetings with Faculty | - Report team's work
|  | 14:00 | 17:00 | 3 |  |  | Team Home Work | Research Static View
|  | 22:00 | 23:00 | 1 |  |  | Team Home Work | Update timelog, write meetings minutes
| 2013-12-27 | 12:00 | 17:00 | 5 | 8 | 5 | Team Meetings | - Update usecase and entities - Update timelog
|  | 19:00 | 22:00 | 3 |  |  | Team Home Work | Research Static View
9 | 2013-12-28 | 14:00 | 16:30 | 2.5 | #REF! | 5 | Team Home Work | Research Physical View
|  | 21:30 | 12:00 | 2.5 |  |  | Team Home Work | Research Physical View
| 2013-12-29 | 13:30 | 18:00 | 4.5 | #REF! | 5 | Team Home Work | Research Dynamic View
|  | 21:00 | 23:00 | 2 |  |  | Team Home Work | Review Static View + Physical View
| 2013-12-30 | 13:30 | 15:00 | 1.5 | 1.5 | 5 | Team Meetings | - Review three views of Architecture Design
| 2013-12-31 | 9:00 | 12:00 | 3 |  |  | Meetings with Customer | - Review quality attribute - Reivew usecase
|  | 13:30 | 15:00 | 1.5 |  |  | Training | - Training about Lusence search - Update timelog
| 2014-01-01 |  |  |  | 0 | 5
| 2014-01-02 | 9:15 | 10:00 | 0.75 |  |  | Meetings with Faculty | - Report week 9 and review architecture plan
|  | 21:30 | 23:30 | 2 |  |  | Team Work | - Update guide how to use TFS
| 2014-01-03 | 13:00 | 15:00 | 2 | 2 | 3 | Team Meetings | - Review architecture components and understanding views in architect design
10 | 2014-01-04 |  |  |  | 0 | 5
| 2014-01-05 | 20:00 | 23:00 | 3 | 3 | 5 | Team Home Work | Update Decompose Style Review Physical Review Static - Layer Style
| 2014-01-06 | 8:00 | 21:30 | 1.5 | 1.5 | 5 | Team Mettings | - Review three views of Architecture Design
|  | 14:00 | 17:00 | 3 |  |  | Team Home Work | Update Decompose Style, combine Decompose Style and Layer Style
|  | 20:00 | 22:30 | 2.5 |  |  | Team Home Work | Update Decompose Style, combine Decompose Style and Layer Style
| 2014-01-07 | 9:00 | 11:30 | 2.5 | 5.5 | 3 | Team Meetings | Review work assignment of each member: physical, layer style, datamodel, system context
|  | 13:30 | 15:00 | 1.5 |  |  | Team Meetings
|  | 10:30PM | 0:00 | 1.5 |  |  | Team Home Work | Update Decompose Style Update timelog
| 2014-01-08 | 8:30 | 12:00 | 3.5 | 5 | 3 | Team Meetings | - Review 3 pespectives
|  | 21:30 | 23:00 | 1.5 |  |  | Team Home Work | Update Dynamic View Update timelog
| 2014-01-09 | 8:00 | 9:00 | 1 | 6 | 5 | Team Work | Review some document to review with mentor
|  | 9:10 | 10:10 | 1 |  |  | Meetings with Faculty | - Report week 10 and present some views in architect
|  | 14:00 | 16:30 | 2.5 |  |  | Meetings with Customer | - Review and update three view in high level
|  | 21:30 | 23:00 | 1.5 |  |  | Team Home Work | Update C&C View - công cụ soạn tin
| 2014-01-10 | 8:30 | 11:00 | 2.5 | 5 | 5 | Team Meetings | - Update dymanic view
|  | 21:30 | 0:00 | 2.5 |  |  | Team Home Work | Update Architecture Document
| 2014-01-11 |  |  |  | 0 | 8
| 2014-01-12 | 20:00 | 23:00 | 3 | 3 | 8 | Team Home Work | Edit architect document
11 | 2014-01-13 | 8:00 | 10:00 | 2 | 7.5 | 8 | Team Home Work | Research C&C view and Static View im Document of Mr.Quang
|  | 13:30 | 16:00 | 2.5 |  |  | Team Work | Discuss about architect document
|  | 20:00 | 23:00 | 3 |  |  | Team Home Work | Research C&C view and Static View im Document of Mr.Quang
| 2014-01-14 | 8:30 | 11:30 | 3 | 9 | 8 | Team Meetings | - Review and update c&c view
|  | 13:30 | 16:30 | 3 |  |  | Team Home Work | - Update c&c views
|  | 20:00 | 23:00 | 3 |  |  | Team Home Work | Update archutect document
| 2014-01-15 | 8:00 | 9:00 | 1 | 3 | 8 | Team Meetings | - Review entire c&c
|  | 9:00 | 11:00 | 2 |  |  | Meetings with Customer | - Present and record c&c for Admission system (Question and Anwser module)
|  | 17:00 | 17:45 | 0.75 |  |  | Team Home Work | Update timelog and evaluation team
| 2014-01-16 | 8:00 | 9:00 | 1 | 2 | 8 | Team Work | Prepare document
|  | 9:00 | 11:00 | 2 |  |  | Meetings with Faculty | - Report pre-week and present architectural elements
|  | 19:30 | 10:30 | 3 |  |  | Team Home Work | Design C&C View
| 2014-01-17 | 9:00 | 12:00 | 3 | 9 | 8 | Team Meetings | - Review and update static and physical views
|  | 14:00 | 17:00 | 3 |  |  | Team Home Work | Edit architecture design
|  | 19:30 | 10:30 | 3 |  |  | Team Home Work | Design Interface
| 2014-01-18 | 8:30 | 10:30 | 2 | 6.5 | 8 | Team Home Work | Edit arhitecture design and Interface
|  | 14:30 | 16:30 | 2 |  |  | Team Home Work | Edit Static View
|  | 19:30 | 22:00 | 2.5 |  |  | Team Home Work | Edit Interface
12 | 2014-01-20 | 19:30 | 23:00 | 3.5 | 3.5 |  | Team Home Work | Edit arhitecture design and Interface
| 2014-01-21 | 9:00 | 12:00 | 3 | 5.5 | 8 | Meeting with Customer | - Review Architect design
|  | 12:00 | 0:30 | 0.5 |  |  | Team Meetings | - Divide team works
|  | 21:00 | 23:00 | 2 |  |  | Team Home Work | Update C&C View + Static View and Interface
| 2014-01-22 | 19:00 | 23:00 | 4 | 4 | 8 | Team Home Work | Edit arhitecture design and Interface Update timelog
| 2014-01-23 |  |  |  | 0 | 8
| 2014-01-24 |  |  |  | 0 | 8
| 2014-01-25 |  |  |  | 0 |  | Nghỉ tết
| 2014-01-26 |  |  |  | 0 |  | Nghỉ tết
| 2014-01-27 |  |  |  | 0 |  | Nghỉ tết
13 | 2014-01-28 |  |  |  | 0 |  | Nghỉ tết
| 2014-01-29 |  |  |  | 0 |  | Nghỉ tết
| 2014-01-30 |  |  |  | 0 |  | Nghỉ tết
| 2014-01-31 |  |  |  | 0 |  | Nghỉ tết
| 2014-02-01 |  |  |  | 0 |  | Nghỉ tết
| 2014-02-02 |  |  |  | 0 |  | Nghỉ tết
14 | 2014-02-03 |  |  |  | 0 |  | Nghỉ tết
| 2014-02-04 |  |  |  | 0 |  | Nghỉ tết
| 2014-02-05 |  |  |  | 0 |  | Nghỉ tết
| 2014-02-06 |  |  |  | 0 |  | Nghỉ tết
| 2014-02-07 |  |  |  | 0 |  | Nghỉ tết
| 2014-02-08 |  |  |  | 0 | 8
| 2014-02-09 |  |  |  | 0 | 8
15 | 2014-02-10 |  |  |  | 0 | 8
| 2014-02-11 | 14:00 | 16:00 | 2 |  |  | Review with customer | - Reivew Dynamic View, Static View, Physical View
|  | 16:00 | 17:00 | 1 |  |  | Team Meetings | - Edit Dynamic view
|  | 19:00 | 10:00PM | 3 |  |  | Team Home Work | Edit C&C view, static view
| 2014-02-12 | 19:00 | 10:30PM | 3.5 | 3.5 | 8 | Team Home Work | Update timelog re-design C&C view, static view
| 2014-02-13 | 8:00 | 11:00 | 3 | 3 | 8 | Team Mettings | - Review static view - Review master plan
| 2014-02-14 | 20:30 | 12:00PM | 3.5 | 3.5 | 8 | Team Home Work | Update architecture design
| 2014-02-15 |  |  |  | 0 | 8
| 2014-02-16 |  |  |  | 0 | 8
16 | 2014-02-17 | 19:00 | 23:00 | 4 | 4 | 8 | Team Home Work | Update architecture design
| 2014-02-18 | 14:00 | 16:00 | 2 | 2 | 8 | Meeting with Customer | - Review Dynamic view, Static view, interface, behavior
| 2014-02-19 | 9:00 | 11:00 | 2 | 5 | 8 | Team Mettings | - Review architect document with team
|  | 11:30 | 12:30 | 1 |  |  | Team Work | Update timelog and evaluation team
|  | 13:30 | 15:30 | 2 |  |  | Team Home Work | Update architecture design and write interface
| 2014-02-20 | 9:30 | 10:30 | 1 | 4 | 8 | Meetings with Faculty | - Review architect documentation
|  | 10:30 | 11:30 | 1 |  |  | Team Meetings | - Divide team work
|  | 14:00 | 16:00 | 2 |  |  | Meeting with Customer | - Review dynamic view, static view, physical view, interface, mapping
|  | 7:00PM | 10:30PM | 3 |  |  | Team Home Work | Update architecture design
| 2014-02-21 | 9:00AM | 12:00PM | 3 | 6 | 8 | Team Work | Design Interface
|  | 1:00PM | 4:00PM | 3 |  |  | Team Work | Design Interface
| 2014-02-22 | 7:00PM | 11:00PM | 4 | 4 | 8 | Team Home Work | Research css and convert psd to html Dap web application and login page
17 | 2014-02-24 | 8:00AM | 12:00PM | 4 | 4 | 8 | Team Work | Design User Interface page 1
| 2014-02-25 | 8:00 | 12:00 | 4 | 7 | 8 | Team Meetings | - Divide code
|  | 1:00PM | 4:00PM | 3 |  |  | Team Work | Design User Interface page 2
| 2014-02-26 | 8:30AM | 12:00PM | 3.5 | 6.5 | 8 | Team Work | Update timelog, research ajax design User Interface
|  | 13:00 | 16:00 | 3 |  |  | Team Meetings | - Review product backlog, sprint backlog - Divide sprint
| 2014-02-27 | 8:00AM | 9:00AM | 1 | 6 | 8 | Team Work | prepare for Meetings with Faculty
|  | 9:00 | 10:00 | 1 |  |  | Meeting with Faculty | - Report team work
|  | 10:00 | 12:00 | 2 |  |  | Team Meetings | - Divide team work
|  | 9:00PM | 11:00PM | 2 |  |  | Team Home Work | detail design: description each interface
| 2014-02-28 | 7:00PM | 10:00PM | 3 | 3 | 8 | Team Home Work | detail design: update
| 2014-03-01 |  |  |  | 0 | 8
| 2014-03-02 |  |  |  | 0 | 8
18 | 2014-03-03 | 8:30AM | 11:30AM | 3 | 7 | 8 | Research | create daatabase
|  | 9:00PM | 1:00AM | 4 |  |  | Team Home Work | coding load QuestionList
| 2014-03-04 | 8:00AM | 12:00PM | 4 | 7 | 8 | Team Work | coding load QuestionList
|  | 13:00 | 16:00 | 3 |  |  | Team Meetings | - Review product backlog, interface
| 2014-03-05 | 8:00AM | 12:00PM | 4 | 10 | 8 | Team Work | coding load QuestionList
|  | 13:00 | 16:00 | 3 |  |  | Team Mettings | - Divide team work
|  | 7:00PM | 10:00PM | 3 |  |  | Team Home Work | coding load QuestionList
| 2014-03-06 | 8:00AM | 9:00AM | 1 | 7 | 8 | Team Work | review individuals task works to prepare present mentor
|  | 9:00 | 10:00 | 1 |  |  | Meeting with Faculty | - Report team work in week 17
|  | 10:00 | 12:00 | 2 |  |  | Team Meetings | - Divide team work - Prepair for meeting with customer to get business rule
|  | 1:00PM | 2:00PM | 1 |  |  | Team Meetings | Review question to ask customer
|  | 14:00 | 16:00 | 2 |  |  | Meeting with Customer | - Get business rules for sprint 1
| 2014-03-07 | 8:00AM | 12:00PM | 4 | 9 | 8 | Team Work | Coding "Load question list to form"
|  | 1:00PM | 6:00PM | 5 |  |  | Team Work | Coding "Load question list to form"
| 2014-03-08 | 8:00AM | 12:00PM | 4 | 4 | 8 | Team Work | Coding "Load question list to form"
| 2014-03-09 | 8:00PM | 11:00PM | 3 | 3 | 8 | Team Home Work | research coding "search data"
19 | 2014-03-10 | 8:00AM | 12:00PM | 4 | 7 | 8 | Team Work | Coding "search data"
|  | 1:00PM | 4:00PM | 3 |  |  | Team Work | Coding "search data"
| 2014-03-11 | 8:00 | 12:00 | 4 | 8 | 8 | Team Work | research and coding "search data"
|  | 13:00 | 17:00 | 4 |  |  | Team Work | research load home page
| 2014-03-12 | 8:00 | 12:00 | 4 | 6.5 | 8 | Team Work | research load home page
|  | 13:00 | 14:00 | 1 |  |  | Team Work | - Review code to prepare meeting Mr. Thanh
|  | 14:00 | 17:00 | 1.5 |  |  | Team Meetings | - Meeting with Mr. Thanh to present coding and raise ideas to implement
| 2014-03-13 |  |  |  | 0 | 8
| 2014-03-14 |  |  |  | 0 | 8
| 2014-03-15 |  |  |  | 0 | 8
| 2014-03-16 |  |  |  | 0 | 8
20 | 2014-03-17 |  |  |  | 0 | 8
| 2014-03-18 |  |  |  | 0 | 8
| 2014-03-19 |  |  |  | 0 | 8
| 2014-03-20 |  |  |  | 0 | 8
| 2014-03-21 |  |  |  | 0 | 8
| 2014-03-22 |  |  |  | 0 | 8
| 2014-03-23 |  |  |  | 0 | 8
21 | 2014-03-24 |  |  |  | 0 | 8
| 2014-03-25 |  |  |  | 0 | 8
| 2014-03-26 |  |  |  | 0 | 8
| 2014-03-27 |  |  |  | 0 | 8
| 2014-03-28 |  |  |  | 0 | 8
| 2014-03-29 |  |  |  | 0 | 8
| 2014-03-30 |  |  |  | 0 | 8
22 | 2014-03-31 |  |  |  | 0 | 8
| 2014-04-01 |  |  |  | 0 | 8
| 2014-04-02 |  |  |  | 0 | 8
| 2014-04-03 |  |  |  | 0 | 8
| 2014-04-04 |  |  |  | 0 | 8
| 2014-04-05 |  |  |  | 0 | 8
| 2014-04-06 |  |  |  | 0 | 8
23 | 2014-04-07 |  |  |  | 0 | 8
| 2014-04-08 |  |  |  | 0 | 8
| 2014-04-09 |  |  |  | 0 | 8
| 2014-04-10 |  |  |  | 0 | 8
| 2014-04-11 |  |  |  | 0 | 8
| 2014-04-12 |  |  |  | 0 | 8
| 2014-04-13 |  |  |  | 0 | 8
24 | 2014-04-14 |  |  |  | 0 | 8
| 2014-04-15 |  |  |  | 0 | 8
| 2014-04-16 |  |  |  | 0 | 8
| 2014-04-17 |  |  |  | 0 | 8
| 2014-04-18 |  |  |  | 0 | 8
| 2014-04-19 |  |  |  | 0 | 8
| 2014-04-20 |  |  |  | 0 | 8
25 | 2014-04-21 |  |  |  | 0 | 8
| 2014-04-22 |  |  |  | 0 | 8
| 2014-04-23 |  |  |  | 0 | 8
| 2014-04-24 |  |  |  | 0 | 8
| 2014-04-25 |  |  |  | 0 | 8
| 2014-04-26 |  |  |  | 0 | 8
| 2014-04-27 |  |  |  | 0 | 8
26 | 2014-04-28 |  |  |  | 0 | 8
| 2014-04-29 |  |  |  | 0 | 8
| 2014-04-30 |  |  |  | 0 | 8
| 2014-05-01 |  |  |  | 0 | 8
| 2014-05-02 |  |  |  | 0 | 8
| 2014-05-03 |  |  |  | 0 | 8
| 2014-05-04 |  |  |  | 0 | 8
27 | 2014-05-05 |  |  |  | 0 | 8
| 2014-05-06 |  |  |  | 0 | 8
| 2014-05-07 |  |  |  | 0 | 8
| 2014-05-08 |  |  |  | 0 | 8
| 2014-05-09 |  |  |  | 0 | 8
| 2014-05-10 |  |  |  | 0 | 8
| 2014-05-11 |  |  |  | 0 | 8
28 | 2014-05-12 |  |  |  | 0 | 8
| 2014-05-13 |  |  |  | 0 | 8
| 2014-05-14 |  |  |  | 0 | 8
| 2014-05-15 |  |  |  | 0 | 8
| 2014-05-16 |  |  |  | 0 | 8
| 2014-05-17 |  |  |  | 0 | 8
| 2014-05-18 |  |  |  | 0 | 8
29 | 2014-05-19 |  |  |  | 0 | 8
| 2014-05-20 |  |  |  | 0 | 8
| 2014-05-21 |  |  |  | 0 | 8
| 2014-05-22 |  |  |  | 0 | 8
| 2014-05-23 |  |  |  | 0 | 8
| 2014-05-24 |  |  |  | 0 | 8
| 2014-05-25 |  |  |  | 0 | 8
30 | 2014-05-26 |  |  |  | 0 | 8
| 2014-05-27 |  |  |  | 0 | 8
| 2014-05-28 |  |  |  | 0 | 8
| 2014-05-29 |  |  |  | 0 | 8
| 2014-05-30 |  |  |  | 0 | 8
| 2014-05-31 |  |  |  | 0 | 8