## List main task
No | Activities
1 | Team Meetings
2 | Reading
3 | Self Prepare
4 | Team Home Work
5 | Team Work
6 | Meetings with Faculty
7 | Meetings with Customer
8 | Training
9 | Research
10 | Review with customer
11 | Review with technical support

## SEP-PROJECT
Time Recording Log For: Admission project | [5 empty] | Start Date: 08/11/2013 End Date:
Ngo Quang Huy - T106772
[7 empty] | Minimum: 5 hours/day 25 hours/week (5hours * 5 days) 700 hours/30 weeks (25 hours * 28 weeks) | Maximum: 24 hours/day 168 hours/week (24hours * 7 days) 4704 hours/30 weeks (168 hours * 28 weeks)
Week | Date | Start | Stop | Delta Time | Total time of day | Activity | Description | Artifact | Note
1 | 2013-11-07 | 13:20 | 14:30 | 1.16 | 1.16 | Team meeting | - Repair for kick off meeting - Devide team work for team member - Define role in project |  |  | SUMMARY: TIME FOR DOING PROJECT | 47.303 | HOURS
| 2013-11-08 | 14:00 | 15:10 | 1.16 | 1.66 | Kick off meeting | - Discuss about communication plan between customer and team - Discuss about system concept |  |  | Time for doing week 1 | 2.82 | HOURS
|  | 15:10 | 15:40 | 0.5 |  | Meetings with Faculty | - Discus about weekly report meeting
2 | 2013-11-11 | 14:00 | 15:30 | 1.5 | 2.5 | trainning | -Training ACDM
|  | 21:00 | 22:00 | 1 |  | Research | - processes
| 2013-11-12 | 13:45 | 15:00 | 2.25 | 2.25 | Team Meetings | - Review Team charter - Review Communication plan - Review Configuration plan - Review Measurement plan | - AS_PM_TeamCharter.docx version 1.0 - AS_PM _ConfigurationPlan.docx version 1.0 - AS_PM_CommunicationPlan.docx version 1.0 - AS_PM_MeasurementPlan.docx version 1.0 |  | Time for doing week 2 | 10.583 | HOURS
|  | 21:00 | 22:00 | 1 | 1 | Team Home Work | - Risk management
| 2013-11-14 | 9:00 | 10:15 | 1.25 | 3.25 | Meetings with Faculty | - Review team rule,documents with mentor. | - AS_DeadlineTeam_Week2.pptx |  | Time for doing week 4 | 15.3 | HOURS
|  | 10:15 | 12:15 | 2 |  | Research | - SCRUM & ACDM
| 2013-11-15 | 13:00 | 14:05 | 1.083 | 1.083 | Team Meetings | - Review risk management plan,process of team. | - AS_PM_RiskManagementPlan.docx version 1.0 - Folder Spring Framwork |  | Time for doing week 5 | 18.6 | HOURS
| 2013-11-16 | 14:00 | 16:00 | 2 | 3 | Team Home Work | - Update risk management | - Team charter version 1.2 - Configuration management plan version 1.1 - Measurement plan version 1.1 |  | Time for doing week 7 | 0 | HOURS
|  | 20:00 | 23:00 | 1 |  | Team Home Work | - SCRUM & integrate between scrum and acdm | - Measurement plan version 1.1
3 | 2013-11-18 | 20:00 | 21:24 | 0.6 | 1.18 | Team Home Work | - review timelog | - AS_PM_TimeLog_DeadlineTeam |  | Time for doing week 8 | 0 | HOURS
|  | 21:25 | 22:00 | 0.58 |  | Research | - java and spring
| 2013-11-19 | 13:30 | 14:30 | 1 | 3 | Team Meetings | .- review change management - review test plan. - review timelog - review process |  |  | Time for doing week 9 | 0 | HOURS
|  | 22:00 | 23:30 | 2 |  | Team Home Work | .- update timelog. - draw process | - AS_PM_TimeLog_DeadlineTeam
| 2013-11-20 | 14:00 | 15:00 | 1 | 3 | self prepare | - risk register template |  |  | Time for doing week 10 | 0 | HOURS
|  | 22:00 | 12:00 | 2 |  | Team Home Work | - update timelog |  |  | Time for doing week 11 | 0 | HOURS
| 2013-11-21 | 8:00 | 9:00 | 1 | 10.35 | prepare
|  | 9:00 | 10:10 | 1.1 |  | Meetings with Faculty | discuss about : process,document of each phase
|  | 10:10 | 11:30 | 1.5 |  | team meeting
|  | 12:30 | 14:30 | 2 |  | self prepare | conduct stage 7-8 ACDM
|  | 15:00 | 17:10 | 2.1 |  | team meeting
|  | 20:15 | 23:00 | 2.65 |  | team homework | create master plan
| 2013-11-22 | 22:30 | 14:45 | 1.25 | 2.75 | team meeting | interate ACDM and SCRUM : role,step,document
|  | 15:00 | 16:30 | 1.5 |  | team homework | sprint life cycle
| 2013-11-23 | 13:30 | 13:45 | 0.25 | 1.5 | teammeeting | process
|  | 13:45 | 15:00 | 1.25 |  | team homework | description stage 7 & 8 of ACDM
4 | 2013-11-25 | 15:00 | 16:15 | 1.25 | 3.25 | team homework | update master design plan update product schedule update sprint life cycle update master plan |  |  | Time for doing week 13 | 0 | HOURS
|  | 22:00 | 12:00 | 2 |  | reading | review documents
| 2013-11-26 | 9:00 | 11:30 | 2.5 | 3.5 | Meetings with Faculty | presents about : process,change management,risk management,measure management,… |  |  | Time for doing week 14 | 0 | HOURS
|  | 13:30 | 14:30 | 1 |  | team meeting | devide task overall about website system
| 2013-11-27 | 13:30 | 15:50 | 2.3 | 2.3 | team meeting | prepare question to get requirement |  |  | Time for doing week 15 | 0 | HOURS
| 2013-11-28 | 13:30 | 16:15 | 2.75 | 2.75 | team meeting | analyze requirement |  |  | Time for doing week 16 | 0 | HOURS
| 2013-11-29 | 13:30 | 17:00 | 3.5 | 3.5 | team meeting | analyze requirement |  |  | Time for doing week 17 | 0 | HOURS
| 2013-11-30 | 14:30 | 16:00 | 1.5 | 2.5 | team homework | Write Functional, Quality Attribute and Entity of Module hỏi đáp
|  | 20:30 | 21:30 | 1 |  | team homework | update Functional, Quality Attribute and Entity of Module hỏi đáp
5 | 2013-12-02 | 20:30 | 21:30 | 1 | 3.5 | team homework | update risk log |  |  | Time for doing week 18 | 0 | HOURS
|  | 21:30 | 23:00 | 1.5 |  | team homework | update master design plan
|  | 23:00 | 24:00 | 1 |  | reading | review documents
| 2013-12-03 | 8:00 | 9:00 | 1 | 10.5 | prepare |  |  |  | Time for doing week 19 | 0 | HOURS
|  | 9:00 | 11:00 | 2 |  | meetings with customer | review entities,functional and quality attribute
|  | 13:30 | 17:00 | 3.5 |  | trainning | spring core,maven… install tool to program product
|  | 20:00 | 21:00 | 1 |  | team homework | update Risk Management | AS_PM_RiskManagment.xlsx
|  | 21:00 | 12:00 | 3 |  | team homework | update master plan. Update master design plan
| 2013-12-04 | 13:30 | 16:10 | 2.6 | 4.6 | teammeeting | review documents .-risk management .-master plan .-master design plan |  |  | Time for doing week 20 | 0 | HOURS
|  | 20:00 | 22:00 | 2 |  | team homework | update master plan. Update master design plan
| 2013-12-05 |  |  |  | 0 |  |  |  |  | Time for doing week 21 | 0 | HOURS
| 2013-12-06 |  |  |  | 0 |  |  |  |  | Time for doing week 22 | 0 | HOURS
6 | 2013-12-09 |  |  |  | 0 |  |  |  |  | Time for doing week 23 | 0 | HOURS
| 2013-12-10 |  |  |  | 0 |  |  |  |  | Time for doing week 24 | 0 | HOURS
| 2013-12-11 |  |  |  | 0 |  |  |  |  | Time for doing week 25 | 0 | HOURS
| 2013-12-12 |  |  |  | 0 |  |  |  |  | Time for doing week 26 | 0 | HOURS
| 2013-12-13 |  |  |  | 0 |  |  |  |  | Time for doing week 27 | 0 | HOURS
7 | 2013-12-16 |  |  |  | 0 |  |  |  |  | Time for doing week 28 | 0 | HOURS
| 2013-12-17 |  |  |  | 0 |  |  |  |  | Time for doing week 29 | 0 | HOURS
| 2013-12-18 |  |  |  | 0 |  |  |  |  | Time for doing week 30 | 0 | HOURS
| 2013-12-19 |  |  |  | 0
| 2013-12-20 |  |  |  | 0
8 | 2013-12-23 |  |  |  | 0
| 2013-12-24 |  |  |  | 0
| 2013-12-25 |  |  |  | 0
| 2013-12-26 |  |  |  | 0
| 2013-12-27 |  |  |  | 0
9 | 2013-12-30 |  |  |  | 0
| 2013-12-31 |  |  |  | 0
| 2014-01-01 |  |  |  | 0
| 2014-01-02 |  |  |  | 0
| 2014-01-03 |  |  |  | 0
10 | 2014-01-06 |  |  |  | 0
| 2014-01-07 |  |  |  | 0
| 2014-01-08 |  |  |  | 0
| 2014-01-09 |  |  |  | 0
| 2014-01-10 |  |  |  | 0
11 | 2014-01-13 |  |  |  | 0
| 2014-01-14 |  |  |  | 0
| 2014-01-15 |  |  |  | 0
| 2014-01-16 |  |  |  | 0
| 2014-01-17 |  |  |  | 0
12 | 2014-01-20 |  |  |  | 0
| 2014-01-21 |  |  |  | 0
| 2014-01-22 |  |  |  | 0
| 2014-01-23 |  |  |  | 0
| 2014-01-24 |  |  |  | 0
13 | 2014-01-27 |  |  |  | 0 | Nghỉ tết
| 2014-01-28 |  |  |  | 0 | Nghỉ tết
| 2014-01-29 |  |  |  | 0 | Nghỉ tết
| 2014-01-30 |  |  |  | 0 | Nghỉ tết
| 2014-01-31 |  |  |  | 0 | Nghỉ tết
14 | 2014-02-03 |  |  |  | 0 | Nghỉ tết
| 2014-02-04 |  |  |  | 0 | Nghỉ tết
| 2014-02-05 |  |  |  | 0 | Nghỉ tết
| 2014-02-06 |  |  |  | 0 | Nghỉ tết
| 2014-02-07 |  |  |  | 0 | Nghỉ tết
15 | 2014-02-10 |  |  |  | 0
| 2014-02-11 |  |  |  | 0
| 2014-02-12 |  |  |  | 0
| 2014-02-13 |  |  |  | 0
| 2014-02-14 |  |  |  | 0
16 | 2014-02-17 |  |  |  | 0
| 2014-02-18 |  |  |  | 0
| 2014-02-19 |  |  |  | 0
| 2014-02-20 |  |  |  | 0
| 2014-02-21 |  |  |  | 0
17 | 2014-02-24 |  |  |  | 0
| 2014-02-25 |  |  |  | 0
| 2014-02-26 |  |  |  | 0
| 2014-02-27 |  |  |  | 0
| 2014-02-28 |  |  |  | 0
18 | 2014-03-03 |  |  |  | 0
| 2014-03-04 |  |  |  | 0
| 2014-03-05 |  |  |  | 0
| 2014-03-06 |  |  |  | 0
| 2014-03-07 |  |  |  | 0
19 | 2014-03-10 |  |  |  | 0
| 2014-03-11 |  |  |  | 0
| 2014-03-12 |  |  |  | 0
| 2014-03-13 |  |  |  | 0
| 2014-03-14 |  |  |  | 0
20 | 2014-03-17 |  |  |  | 0
| 2014-03-18 |  |  |  | 0
| 2014-03-19 |  |  |  | 0
| 2014-03-20 |  |  |  | 0
| 2014-03-21 |  |  |  | 0
21 | 2014-03-24 |  |  |  | 0
| 2014-03-25 |  |  |  | 0
| 2014-03-26 |  |  |  | 0
| 2014-03-27 |  |  |  | 0
| 2014-03-28 |  |  |  | 0
22 | 2014-03-31 |  |  |  | 0
| 2014-04-01 |  |  |  | 0
| 2014-04-02 |  |  |  | 0
| 2014-04-03 |  |  |  | 0
| 2014-04-04 |  |  |  | 0
23 | 2014-04-07 |  |  |  | 0
| 2014-04-08 |  |  |  | 0
| 2014-04-09 |  |  |  | 0
| 2014-04-10 |  |  |  | 0
| 2014-04-11 |  |  |  | 0
24 | 2014-04-14 |  |  |  | 0
| 2014-04-15 |  |  |  | 0
| 2014-04-16 |  |  |  | 0
| 2014-04-17 |  |  |  | 0
| 2014-04-18 |  |  |  | 0
25 | 2014-04-21 |  |  |  | 0
| 2014-04-22 |  |  |  | 0
| 2014-04-23 |  |  |  | 0
| 2014-04-24 |  |  |  | 0
| 2014-04-25 |  |  |  | 0
26 | 2014-04-28 |  |  |  | 0
| 2014-04-29 |  |  |  | 0
| 2014-04-30 |  |  |  | 0
| 2014-05-01 |  |  |  | 0
| 2014-05-02 |  |  |  | 0
27 | 2014-05-05 |  |  |  | 0
| 2014-05-06 |  |  |  | 0
| 2014-05-07 |  |  |  | 0
| 2014-05-08 |  |  |  | 0
| 2014-05-09 |  |  |  | 0
28 | 2014-05-12 |  |  |  | 0
| 2014-05-13 |  |  |  | 0
| 2014-05-14 |  |  |  | 0
| 2014-05-15 |  |  |  | 0
| 2014-05-16 |  |  |  | 0
29 | 2014-05-19 |  |  |  | 0
| 2014-05-20 |  |  |  | 0
| 2014-05-21 |  |  |  | 0
| 2014-05-22 |  |  |  | 0
| 2014-05-23 |  |  |  | 0
30 | 2014-05-26 |  |  |  | 0
| 2014-05-27 |  |  |  | 0
| 2014-05-28 |  |  |  | 0
| 2014-05-29 |  |  |  | 0
| 2014-05-30 |  |  |  | 0