## Instructions
INSTRUCTIONS FOR COMPLETING THIS DOCUMENT
Term | Descriptions
Product Backlog Item | This is a reference to the ID defined in the Product Backlog document
Team Member | Who on team has taken ownership of this work item
Priority | The priority (0=High 25=Low). Work item with a higher priority should be claimed first. Every task has a value and a difficulty assigned to it, its priority is calculated by multiplying the two values together. Priority = Value*Difficulty This gives all task a priority from 0 (the highest priority) to 25 (the lowest priority) Priority 0: These tasks either have to be done or can be done so quickly that they might as well be done. If necessary, sort these tasks by difficulty if you want to know which one to do first. Priority 1-2: These should be the meat of the task list with all of the important tasks, and all of them should get done. If you miss any off these, you need to figure out why and prevent it from happening again Priority 3-5: To really be happy about meeting a deadline, you would need to get all of these done, but sometimes there will be one or two left at the end. Priority 6-10: If you complete all these tasks, you have nailed your dealine. You shouldn't feel too bad if you miss a good number of these, and sometimes you won't even get to any of them Priority 11+: These are tasks you are not going to complete.
| Task Value Each task have value ranging from 0 to 5. The lower task value number, the more important the task: Value 0: Essential. If even a one of these tasks is not complete, the dealine slips, even if that means the project will have to be canceled Value 1: Critical. All of these tasks must be completed, but if just one or two aren't, then the dealine can still be met although just barely, and it would usually be better to slip the deadline if possible). Value 2: High. All of these tasks should be completed, but realistically a small percentage of them probably won't be. You would only slip a dealine if you had barelt done any of these tasks. Value 3: Medium. These tasks certainly have value, and you should expect to complete at least half of them (the easy ones). You would never slip a dealine for these tasks, even if you did not do a single one. Value 4: Low. These are tasks you would like to get to, mainly just extra features and polish. you will likely end up doing easy ones, but that's all Value 5: Minimal. These are tasks that are of questionable value or something that you don't want to leave off the list, but don't really expect to do. | Task Difficulty Each task have difficulty ranging from 0 to 5. The higher the Task Difficulty number, the more difficult the task is (note that this is in reverse order from the Task Value) Difficulty 0: Instant. Takes minutes to do, has no chance to breaking anything, and doesn't generate any work for anyone else in another department Difficulty 1: Trivial. Takes an hour or less to do, should have no chance of breaking anything, and at most only requies you to run it by someone else in another department. Difficulty 2: Easy. Takes two hours or less to do, is unlikely to break anything, and at most requires a trivial amount of work from someone else in another department. Difficulty 3: Medium. Takes four hours or less to do, has chance of breaking somnthing, but not anything major, and at most requires only a small amount of work from some one else in another department Difficulty 4: Hard. Takes eight hours or less to do , might very well break something (or has a chance of breaking something major) Difficulty 5: Scary. Takes more than eight hours to do, is likely to break something, or requires a lot of work from someone else in another department.
Status | Current status of this work item. This can be used to ensure multiple people do not work on the same work item. The filter can also be used to filter out any task that have already been completed. Have 5 types: 1 - Proposed - This work item has been review and approved 2 - In Progress - This work item is being worked on 3 - Re-Opened - This work item has been open again, because of some problems are not resolve in before sprint 4 - Complete - This work item is finished 5 - Delete - This work item is delete from product back log, it may be re-opent in next sprint
Comment | Any additional comments or notes
Original Estimate (hours) | This is the estimate that was figured out at the beginning of the Sprint. For new work item, this should be zero.
New Estimate (hours) | If the estimate needs to be revised, or it's a new work item, the effort is here.
Change | This is the increase/decrease in hours that needs to be tracked
Revised Value (hours) | Calculated field. It is the new estimate, if applicable.
Amount Remaining (hours) | The amount of hours that are still remaining for this task. Should be zero for a task that is completed, and should never be negative.

## Sprint #1
SPRINT#1 BACKLOG FOR SCRUM MODIFY
Project Name:
Project Description:
Development team:
Project Manager Name:
Product Backlog Item | Category | Team Member | Type | Priority (0=High 25=Low) | Status | Comment | Original Estimate (hours) | New Estimate (hours) | Change | Revised Value (hours) | Amount Remaining (hours) | Thu 3/14/2013 | Fri 3/15/2013 | Sat 3/16/2013 | Sun 3/17/2013 | Mon 3/18/2013 | Tue 3/19/2013 | Wed 3/20/2013 | Thu 3/21/2013 | Fri 3/22/2013 | Sat 3/23/2013
Note on A8: VanLe: This is a reference to the ID defined in the Product Backlog document
Note on B8: VanLe: The Category. High level classification of the usecase
Note on C8: VanLe: Who on team has taken ownership of this work item
Note on D8: VanLe: What type of work item it is. Task - A new item Bug - A defect related to something that has already been completed.
Note on E8: VanLe: The priority. Work item with a higher priority should be claimed first. See sheet "Instructions" to caculate the priority. In the formula: value*difficulty
Note on F8: VanLe: Current status of this work item. This can be used to ensure multiple people do not work on the same work item. The filter can also be used to filter out any task that have already been completed. Have 5 types: 1 - Proposed - This work item has been review and approved 2 - In Progress - This work item is being worked on 3 - Re-Opened - This work item has been open again, because of some problems are not resolve in before sprint 4 - Complete - This work item is finished 5 - Delete - This work item is delete from product back log, it may be re-opent in next sprint
Note on G8: VanLe: Any additional comments or notes
Note on H8: VanLe: This is the estimate that was figured out at the beginning of the Sprint. For new work item, this should be zero.
Note on I8: VanLe: If the estimate needs to be revised, or it's a new work item, the effort is here.
Note on J8: VanLe: This is the increase/decrease in hours that needs to be tracked
Note on K8: VanLe: Calculated field. It is the new estimate, if applicable.
Note on L8: VanLe: The amount of hours that are still remaining for this task. Should be zero for a task that is completed, and should never be negative.
Note on M8: VanLe: This is the first day of the sprint. All of the other days are based on this. Please insert actual work time for this work item on that day
Note on N8: VanLe: Please insert actual work time for this work item on that day
Note on O8: VanLe: Please insert actual work time for this work item on that day
Note on P8: VanLe: It's optional. If you work overtime for complete work item. Please insert actual work time for this work item on that day
Note on Q8: VanLe: Please insert actual work time for this work item on that day
Note on R8: VanLe: Please insert actual work time for this work item on that day
Note on S8: VanLe: Please insert actual work time for this work item on that day
Note on T8: VanLe: Please insert actual work time for this work item on that day
Note on U8: VanLe: Please insert actual work time for this work item on that day
Note on V8: VanLe: This is the finally day of the sprint. Please insert actual work time for this work item on that day

## Sprint #2
SPRINT#2 BACKLOG FOR SCRUM MODIFY
Project Name:
Project Description:
Development team:
Project Manager Name:
Product Backlog Item | Category | Team Member | Type | Priority (0=High 25=Low) | Status | Comment | Original Estimate (hours) | New Estimate (hours) | Change | Revised Value (hours) | Amount Remaining (hours) | Mon 3/25/2013 | Tue 3/26/2013 | Wed 3/27/2013 | Thu 3/28/2013 | Fri 3/29/2013 | Sat 3/30/2013 | Sun 3/31/2013
Note on A8: VanLe: This is a reference to the ID defined in the Product Backlog document
Note on B8: VanLe: The Category. High level classification of the usecase
Note on C8: VanLe: Who on team has taken ownership of this work item
Note on D8: VanLe: What type of work item it is. Task - A new item Bug - A defect related to something that has already been completed.
Note on E8: VanLe: The priority. Work item with a higher priority should be claimed first. See sheet "Instructions" to caculate the priority. In the formula: value*difficulty
Note on F8: VanLe: Current status of this work item. This can be used to ensure multiple people do not work on the same work item. The filter can also be used to filter out any task that have already been completed. Have 5 types: 1 - Proposed - This work item has been review and approved 2 - In Progress - This work item is being worked on 3 - Re-Opened - This work item has been open again, because of some problems are not resolve in before sprint 4 - Complete - This work item is finished 5 - Delete - This work item is delete from product back log, it may be re-opent in next sprint
Note on G8: VanLe: Any additional comments or notes
Note on H8: VanLe: This is the estimate that was figured out at the beginning of the Sprint. For new work item, this should be zero.
Note on I8: VanLe: If the estimate needs to be revised, or it's a new work item, the effort is here.
Note on J8: VanLe: This is the increase/decrease in hours that needs to be tracked
Note on K8: VanLe: Calculated field. It is the new estimate, if applicable.
Note on L8: VanLe: The amount of hours that are still remaining for this task. Should be zero for a task that is completed, and should never be negative.
Note on M8: VanLe: Please insert actual work time for this work item on that day
Note on N8: VanLe: Please insert actual work time for this work item on that day
Note on O8: VanLe: Please insert actual work time for this work item on that day
Note on P8: VanLe: This is the finally day of the sprint. Please insert actual work time for this work item on that day