## LeNgocChau
Admission System Project
Report date: 14/5/2014 |  |  | Phase: Daily report sprint 4
Reporter: Le Ngoc Chau
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Web service - Search Q/A on Android | High | 2014-12-05 | 2014-12-05 | Done |  | Le Ngoc Chau
2
3
4
Plan for next days
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## KhauThanhDao
Admission System Project
Report date: 14/5/2014 |  |  | Phase: Daily report sprint 4
Reporter: Khau Thanh Dao
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Web service - Drop-dict on android | Medium | 2014-12-05 | 2014-12-05 | Done |  | Khau Thanh Dao
2 | Deploy-Android's DMS | Medium | 2014-12-05 | 2014-12-05 | On-going |  | Khau Thanh Dao
3 | Test - Web service - send mail on android | Low | 13/05/2014 | 13/05/2015 | On-going |  | Khau Thanh Dao
4 | Deploy-Android's DMS | Medium | 13/05/2014 | 13/05/2015 | On-going |  | Khau Thanh Dao
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## NgoQuangHuy
Admission System Project
Report date: 14/5/2014 |  |  | Phase: Daily report sprint 4
Reporter: Ngo Quang Huy
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Prototype Android DMS application | High | 2014-12-05 | 2014-12-05 | Done |  | Ngo Quang Huy
2 | Test - Send mail on android | Low | 2014-12-05 | 2014-12-05 | Done |  | Ngo Quang Huy
3
4
6
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1

## NguyenPhanXuanHuy
Admission System Project
Report date: 14/5/2014 |  |  | Phase: Daily report sprint 4
Reporter: Nguyen Phan Xuan Huy
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Implement - Insert dict on android | High | 2014-12-05 | 2014-12-05 | Done |  | Nguyen Phan Xuan Huy
2 | Implement test | Low | 2014-12-05 | 2014-12-05 | Done |  | Nguyen Phan Xuan Huy
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## HuynhTrongKhang
Admission System Project
Report date: 14/5/2014 |  |  | Phase: Daily report sprint 4
Reporter: Huynh Trong Khang
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Implement - Create question | High | 2014-12-05 | 2014-12-05 | Done |  | Huynh Trong Khang
2 | Web service - send mail on android | Medium | 2014-12-05 | 2014-12-05 | Done |  | Huynh Trong Khang
3 | Test - Web service - Drop-dict on android | Low | 2014-12-05 | 2014-12-05 | Done |  | Huynh Trong Khang
4 |  |  |  |  | On-going
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1 | Android virtual sometime being crash
The most significance knowledge gained last week
# | Description
1
2
3

## TaNgocThienPhu
Admission System Project
Report date: 14/5/2014 |  |  | Phase: Daily report sprint 4
Reporter: Ta Ngoc Thien Phu
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Implement - Search Q/A on Android | High | 2014-12-05 | 2014-12-05 | On-going |  | Ta Ngoc Thien Phu
2 | Implement - Restore question on Android | High | 2014-12-05 | 2014-12-05 | On-going |  | Ta Ngoc Thien Phu
3 | Implement - Drop-dict on android | High | 2014-12-05 | 2014-12-05 | On-going |  | Ta Ngoc Thien Phu
4 | Web service - Insert dict on android | Medium | 2014-12-05 | 2014-12-05 | On-going |  | Ta Ngoc Thien Phu
Plan for next days
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Team member
No | Team member
1 | Le Ngoc Chau
2 | Khau Thanh Dao
3 | Ngo Quang Huy
4 | Nguyen Phan Xuan Huy
5 | Huynh Trong Khang
6 | Ta Ngoc Thien Phu