## Team member
Chau Le
Dao Khau
Huy Ngo
Huy Nguyen
Khang Huynh
Phu Ta

## Chau Le
Admission System Project
Report date: 14/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Chau Le
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Research registration | Medium | 13/3/2014 | 13/3/2014 | On-going |  | Chau Le
2
3
4
Plan for next days
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Research registration |  | 14/3/2014 |  |  |  | Chau Le
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Dao Khau
Admission System Project
Report date: 14/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Dao Khau
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Code function send answer | High | 2014-12-03 | 2014-12-03 | On-going |  | Dao Khau
2 | Code function create index | High | 2014-12-03 | 2014-12-03 | On-going |  | Dao Khau
3 | Code Funtion user management | High | 2014-12-03 | 2014-12-03 | On-going |  | Dao Khau
4
Plan for next days
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Code function send answer |  | 14/3/2014
2 | Code function create index |  | 14/3/2014
3 | Code Funtion user management |  | 14/3/2014
4 | Code create Index |  | 14/3/2014
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1 | understand how to use ckeditor
2
3

## Huy Ngo
Admission System Project
Report date:14/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Huy Ngo
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Implement - Đang nhập/đăng xuất ứng dụng quản trị bộ từ điển | high | 2014-12-03 | 2014-12-04 | On-going |  | Huy Ngo
2
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Implement - Đang nhập/đăng xuất ứng dụng quản trị bộ từ điển |  | 14/3/2014 |  |  |  | Huy Ngo
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Huy Nguyen
Admission System Project
Report date: 14/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Huy Nguyen
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Coding Send mail | High | 2014-12-03 | 2014-12-03 | Done |  | Huy Nguyen
2 | Research FTP | High | 13/03/2014 | 13/03/2014 | On-going |  | Huy Nguyen
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Khang Huynh
Admission System Project
Report date: 14/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Khang Huynh
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Demo send mail |  | 2014-12-03 | 2014-12-03 | Done |  | Khang Huynh
2 | Research and implement sessesion, interceptors |  | 13/03/2014 | 13/03/2014 | Done |  | Khang Huynh
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Demo sessions |  | 14/3/2014 |  |  |  | Khang Huynh
2 | Research and demo Crup in springMVC |  | 14/3/2014 |  |  |  | Khang Huynh
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Phu Ta
Admission System Project
Report date: 14/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Phu Ta
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | design database intranet | Medium | 2014-09-03 | 2014-09-03 | Done |  | Phu Ta
2 | Coding load list-question from db |  | 2014-09-03 | 2014-09-03 | On-going |  | Phu Ta
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Coding load list-question from db |  | 2014-11-03
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1 | understand how to use ckeditor
2
3