## Team member
Chau Le
Dao Khau
Huy Ngo
Huy Nguyen
Khang Huynh
Phu Ta

## Chau Le
Admission System Project
Report date: 5/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Chau Le
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Code interface for list question that is anwser | Medium | 2014-03-03 | 2014-04-03 | Done |  | Chau Le
2
3
4
Plan for next days
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Code interface for dictionary |  | 2014-05-03
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1 | understand how to use ckeditor
2
3

## Dao Khau
Admission System Project
Report date: 5/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Dao Khau
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Code interface for login | Medium | 2014-03-03 | 2014-03-03 | Done |  | Dao Khau
2 | Research ckeditor | High | 2014-03-03 | 2014-04-03 | Done |  | Dao Khau
3
4
Plan for next days
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Code interface for menu |  | 2014-05-03
2 | Research tiles template |  | 2014-05-03
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1 | understand how to use ckeditor
2
3

## Huy Ngo
Admission System Project
Report date: 5/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Huy Ngo
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Code interface for danh sach cau hoi chua tra loi | Medium | 2014-03-03 | 2014-03-03 | On-going |  | Huy Ngo
2 | implement for dang nhap/dang xuat cong cu quan tri | High | 2014-03-05 | 2014-03-05 | On-going |  | Huy Ngo
3 | Thực hiện database intranet | High | 2014-03-06 | 2014-03-06 | On-going |  | Huy Ngo
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Code interface for danh sach cau hoi chua tra loi |  | 2014-07-03
2 | implement for dang nhap/dang xuat cong cu quan tri |  | 2014-10-03
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Huy Nguyen
Admission System Project
Report date: 5/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Huy Nguyen
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Researh testcase template | Medium | 2014-05-03 | 2014-05-03 | On-going |  | Huy Nguyen
2
3
4
Plan for next day
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Khang Huynh
Admission System Project
Report date: 5/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Dao Khau
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Code interface for dictionary-list | Medium | 2014-03-03 | 2014-03-03 | Done |  | Khang Huynh
2 | Ajax for load page | High | 2014-03-03 | 2014-04-03 | Done |  | Khang Huynh
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Implement login to understand webflow |  | 2014-05-03
2 | Update user dictionary-list interface |  | 2014-05-03
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1 | How to convert psd to HTML
2 | Knowledge about springMVC flow
3

## Phu Ta
Admission System Project
Report date: 5/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Phu Ta
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Code list-question interface | Medium | 2014-03-03 | 2014-03-03 | Done |  | Phu Ta
2
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Research load list-question from db |  | 2014-05-03
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1 | understand how to use ckeditor
2
3