## Team member
Chau Le
Dao Khau
Huy Ngo
Huy Nguyen
Khang Huynh
Phu Ta

## Chau Le
Admission System Project
Report date: 2/4/2014 |  |  | Phase: Daily report sprint 1
Reporter: Chau Le
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Test - Đưa vào từ điển | Medium | 31/03/2014 | 31/03/2014 | On-going |  | Chau Le
2 | Test - Điểu chỉnh hiển thị các items trong danh sách | Medium | 31/03/2014 | 31/03/2014 | On-going |  | Chau Le
3 | Test - Cấu hình gửi mail | Medium | 31/03/2014 | 31/03/2014 | On-going |  | Chau Le
4 | Test - Quản trị người dùng | Medium | 31/03/2014 | 31/03/2014 | On-going |  | Chau Le
5 | Test - Những tính năng khác trên công cụ hiển thị | Medium | 31/03/2014 | 31/03/2014 | On-going |  | Chau Le
Plan for next days
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Dao Khau
Admission System Project
Report date: 2/4/2014 |  |  | Phase: Daily report sprint 2
Reporter: Dao Khau
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Implement - Paggination cho trang trên công cụ quản trị | Medium | 31/3/2014 | 31/3/2014 | On-going |  | Dao Khau
2 | Quản trị người dùng | High | 31/3/2014 | 31/3/2014 | On-going |  | Dao Khau
3 | Implement - Cập nhật index | High | 31/3/2014 | 31/3/2014 | On-going |  | Dao Khau
4 | Test - Cập nhật index | Low | 31/3/2014 | 31/3/2014 | On-going |  | Dao Khau
5 | Test - Web service - Nhận câu hỏi từ công cụ hiển thị | Low | 31/3/2014 | 31/3/2014 | On-going |  | Dao Khau
6 | Implement - Cấu hình gửi mail | High | 31/3/2014 | 31/3/2014 | On-going |  | Dao Khau
7 | Test - File câu hình tập trung và phân tán | Low | 31/3/2014 | 31/3/2014 | On-going
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1 | hard to config send mail
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Huy Ngo
Admission System Project
Report date: 2/4/2014 |  |  | Phase: Daily report sprint 2
Reporter: Huy Ngo
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Test - Tìm kiếm trên công cụ quản trị bộ từ điển | Low | 31/03/2014 | 31/03/2014 | On-going |  | Huy Ngo
2 | Test - Hiển thị danh sách câu hỏi | Low | 31/03/2014 | 31/03/2014 | On-going |  | Huy Ngo
3 | Test - Xem chi tiết câu hỏi | Low | 31/03/2014 | 31/03/2014 | On-going |  | Huy Ngo
4 | Test - Tạo câu hỏi | Low | 31/03/2014 | 31/03/2014 | On-going |  | Huy Ngo
5 | Test Web service - Gửi câu hỏi sang công cụ quản trị bộ từ điển | Low | 31/03/2014 | 31/03/2014 | On-going |  | Huy Ngo
6 | Test - Các trạng thái trong bộ từ điển | Low | 31/03/2014 | 31/03/2014 | On-going |  | Huy Ngo
7 | Detail design cho ứng dụng hiển thị bộ từ điển trên web application | high | 2014-01-04 | 2014-01-04 | On-going |  | Huy Ngo
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Huy Nguyen
Admission System Project
Report date: 2/4/2014 |  |  | Phase: Daily report sprint 2
Reporter: Huy Nguyen
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Implement - Xem chi tiết câu hỏi | Medium | 31/03/2014 | 31/03/2014 | On-going |  | Huy Nguyen
2 | Web service - Gửi câu hỏi sang công cụ quản trị bộ từ điển | High | 31/03/2014 | 31/03/2014 | Done |  | Huy Nguyen
3 | Test - Tìm kiếm câu hỏi trên công cụ hiển thị | Low | 2014-01-04 | 2014-01-04 | On-going |  | Huy Nguyen
4 | Test - Cập nhật bộ từ điển | Low | 2014-01-04 | 2014-01-04 | On-going |  | Huy Nguyen
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Khang Huynh
Admission System Project
Report date: 2/4/2014 |  |  | Phase: Daily report sprint 2
Reporter: Khang Huynh
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Test - Tạo index |  | 31/03/2014 | 31/03/2014 | On-going |  | Khang Huynh
2 | Implement - Những tính năng khác trên công cụ hiển thị |  | 31/03/2014 | 31/03/2014 | On-going |  | Khang Huynh
3 | Test - Web service - Đưa danh sáchcâu hỏi qua công cụ hiển thị |  | 31/03/2014 | 31/03/2014 | On-going |  | Khang Huynh
4 | Test - Xóa nhiều câu hỏi trong bộ từ điển |  | 31/03/2014 | 31/03/2014 | On-going |  | Khang Huynh
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Phu Ta
Admission System Project
Report date: 2/4/2014 |  |  | Phase: Daily report sprint 2
Reporter: Phu Ta
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Test - Đưa nhiều câu hỏi vào bộ từ điển | Low | 2014-01-04 | 2014-01-04 | On-going |  | Phu Ta
2
3
4
Plan for next days
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3