## Team member
Chau Le
Dao Khau
Huy Ngo
Huy Nguyen
Khang Huynh
Phu Ta

## Chau Le
Admission System Project
Report date: 28/3/2014 |  |  | Phase: Daily report sprint 2
Reporter: Chau Le
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Prototype cho ứng dụng hiển thị bộ từ điển trên web application | High | 26/03/2014 | 26/03/2014 | On-going |  | Chau Le
2
3
4
Plan for next days
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Dao Khau
Admission System Project
Report date: 28/3/2014 |  |  | Phase: Daily report sprint 2
Reporter: Dao Khau
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Quản trị người dùng | High | 27/03/2014 | 27/03/2014 | On-going |  | Dao Khau
2 | Implement - Cập nhật index | High | 27/03/2014 | 27/03/2014 | On-going |  | Dao Khau
3 | Web serivce - Gửi index | High | 27/03/2014 | 27/03/2014 | On-going |  | Dao Khau
4 | Implement - Cấu hình gửi mail | Medium | 27/03/2014 | 27/03/2014 | On-going |  | Dao Khau
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Huy Ngo
Admission System Project
Report date: 28/3/2014 |  |  | Phase: Daily report sprint 2
Reporter: Huy Ngo
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Implement - Tạo index | high | 26/03/2014 | 26/03/2015 | On-going |  | Huy Ngo
2
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Huy Nguyen
Admission System Project
Report date: 28/3/2014 |  |  | Phase: Daily report sprint 2
Reporter: Huy Nguyen
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Web service - Đưa câu hỏi qua công cụ hiển thị | High | 27/03/2014 | 27/03/2014 | On-going |  | Huy Nguyen
2 | Implement - Xóa nhiều câu hỏi trong bộ từ điển | Medium | 27/03/2014 | 27/03/2014 | On-going |  | Huy Nguyen
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Khang Huynh
Admission System Project
Report date: 28/3/2014 |  |  | Phase: Daily report sprint 2
Reporter: Khang Huynh
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Implement - Tự tạo câu hỏi trên công cụ quản trị | medium | 26/03/2014 | 26/03/2014 | On-going |  | Khang Huynh
2 | Implement - Những tính năng khác trên công cụ hiển thị | medium | 27/03/2014 | 27/03/2014 | On-going |  | Khang Huynh
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Phu Ta
Admission System Project
Report date: 28/3/2014 |  |  | Phase: Daily report sprint 2
Reporter: Phu Ta
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Implement - Hiển thị danh sách câu hỏi | Medium | 26/03/2014 | 26/03/2014 | Done |  | Phu Ta
2
3
4
Plan for next days
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3