## Team member
Chau Le
Dao Khau
Huy Ngo
Huy Nguyen
Khang Huynh
Phu Ta

## Chau Le
Admission System Project
Report date: 19/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Chau Le
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Code registration form | Medium | 18/3/2014 | 18/3/2014 | Done |  | Chau Le
2
3
4
Plan for next days
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Code change password |  | 19/3/2014 |  |  |  | Chau Le
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1 | Can't insert data to database, need more time to research |  |  | Increase time and resource
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Dao Khau
Admission System Project
Report date: 19/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Dao Khau
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Code function send answer | High | 15/3/2014 | 15/3/2014 | Done |  | Dao Khau
2 | Code function create index | High | 15/3/2014 | 15/3/2014 | On-going |  | Dao Khau
3 | Code Funtion user management | High | 15/3/2014 | 15/3/2014 | On-going |  | Dao Khau
4 | Code Funtion Create index | High | 15/3/2014 | 15/3/2014 | On-going |  | Dao Khau
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Code function create index |  | 17/3/2014
2 | Code Funtion user management |  | 17/3/2014
3 | Code Funtion Create index |  | 17/3/2014
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1 | understand how to use ckeditor
2
3

## Huy Ngo
Admission System Project
Report date: 19/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Huy Ngo
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1
2
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Huy Nguyen
Admission System Project
Report date: 19/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Huy Nguyen
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1
2
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Khang Huynh
Admission System Project
Report date: 19/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Khang Huynh
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1
2
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Phu Ta
Admission System Project
Report date: 19/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Phu Ta
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1
2
3
4
Plan for next days
#
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1 | understand how to use ckeditor
2
3