## Revision history
Document Reviewer Information
Reviewer Name | Review Attendance (R/S) | Comments
R/S: Required or Suggested participants or functions for the document review meeting
Document Approver Information
Approver Name | Approver Function | Comments
Document Revision History
Date | Revision | Status | Change Summary | Revised by | Version
25/11/2013 | design template | on going |  | Ngo Quang Huy | 1
2013-02-12 | update plan | on going |  | Ngo Quang Huy | 2
19/12/2013 | update plan | on going |  | Ngo Quang Huy | 3

## Master design plan
MASTER DESIGN PLAN
CATEGORIES |  |  | ASSIGN | MAIN RESPONSIBLE | TIME
[5 empty] | START | FINISH | ACTUAL FINISH
STAGE 1 | Activities | Discover Architectural Drivers. | Team | Huynh Trong Khang | 26/11/2013 | 2013-02-12 | 2013-02-12
|  | meeting with customer #1 | Team |  | 28/11/2013 | 28/11/2013 | 28/11/2013
|  | Review with mentor #1 | Team |  | 29/11/2013 | 29/11/2013 | 29/11/2013
|  | Meeting with customer #2. | Team |  | 2013-03-12 | 2013-03-12 | 2013-03-12
|  | Meeting with mentor #2. | Team |  | 2013-03-12 | 2013-03-12 | 2013-03-12
|  | Review with customer #3. | Team |  | 2013-10-12 | 2013-10-12 | 2013-12-12
| Documents | Operation Requirement Document | Huynh Trong Khang |  | 26/11/2013 | 26/12/2013 | 18/12/2013
|  | Review Operation Requirement Document. | Huynh Trong Khang |  | 2013-12-12 | 2013-12-12
STAGE 2 | Activities | Establish Project Scope. | Team | Huynh Trong Khang | 2013-12-12 | 2013-12-12
|  | Define entities Draw use-case model Create use-case description Create quality attribute scenario. | Team |  | 2013-12-12 | 16/12/2013 | 2013-09-12
|  | Review with mentor #1 | Team |  | 2013-12-12 | 2013-12-12 | 2013-12-12
|  | Meeting with customer #4 | Team |  | 17/12/2013 | 17/12/2013 | 19/12/2013
|  | Review with mentor #2 | Team |  | 19/12/2013 | 19/12/2013
|  | Review Architectural Drivers Specification with team members | Team |  | 21/12/2013 | 21/12/2013
|  | Meeting with customer #5 + Review Quality attribute and constraints + Define prioritization | Team |  | 24/12/2013 | 24/12/2013
|  | Update whole architectural drivers specification document |  |  | 24/12/2013 | 24/12/2013
|  | Establish Project Scope. Review customer, mentor & closed architecture drivers specification |  |  | 26/12/2013 | 26/12/2013
| Documents | Architecture Drivers Specification | Team |  | 2013-12-11 | 22/12/2013 | 2013-09-12
|  | Product Backlog Document. | Team |  | 2013-12-11 | 22/12/2013
STAGE 3 | Activities | create architect plan |  | Tạ Ngọc Thien Phú | 18/11/2013 | 27/11/2013 | 27/11/2013
|  | system context |  |  | 31/12/2013 | 2014-03-01 | 2014-03-01
|  | Develop physical view for admission system (high level) |  |  | 31/12/2013 | 2014-04-01
|  | Develop dynamic view for admission system (high level) |  |  | 31/12/2013 | 2014-06-01
|  | Develop static view for admission system (high level) |  |  | 31/12/2013 | 2014-04-01
|  | Evaluate architect and design for admission system |  |  | 2014-06-01 | 2014-06-01
|  | Review with Customer: +Static View +Dynamic View +Physical View |  |  | 2014-07-01 | 2014-07-01
|  | mapping physical with dynamic |  |  | 2014-07-01 | 2014-11-01
|  | mapping static with dynamic |  |  | 2014-07-01 | 2014-11-01
|  | Edit Architecture Design |  |  | 2014-07-01 | 13/1/2014
|  | Design Interface |  |  | 2014-07-01 | 13/1/2014
Documents
STAGE 4 | Activities | Evaluate architect and design and interface |  |  | 13/1/2014 | 13/1/2014
|  | Review with Customer: review 3 perspective and Interface +Mapping physical – Dynamic and Static –Discuss Interface design |  |  | 14/1/2014 | 14/1/2014
|  | Edit Architecture Design and Interface |  |  | 14/1/2014 | 20/1/2014
|  | Evaluate architect and design and interface |  |  | 20/1/2014 | 20/1/2014
|  | Review with Customer to Done Stage 3 |  |  | 21/1/2014 | 21/1/2014
|  | Edit Architecture Design and Interface Create sprint backlog |  |  | 22/1/2014 | 25/2/2014
Documents
STAGE 5 | Activities
Documents
STAGE 6 | Activities
Documents
STAGE 7 | Activities
Documents