## List main task
No | Activities
1 | Team Meetings
2 | Reading
3 | Self Prepare
4 | Team Home Work
5 | Team Work
6 | Meetings with Faculty
7 | Meetings with Customer
8 | Training
9 | Research
10 | Review with customer
11 | Review with technical support

## AS-PROJECT
Time Recording Log For: Capstone project |  |  |  |  | Start Date: 08/11/2013 End Date:
Khang Huynh - T104898
Week | Date | Start | Stop | Delta Time | Activity | Description | Artifact | Note
1 | 2013-11-08 | 1:00PM | 2:00PM | 1 | Kick off meeting | Meeting with mentor & customer |  |  | SUMMARY: TIME FOR DOING PROJECT | 14 | HOURS
2 | 2013-11-11 | 1:00PM | 3:30PM | 2.5 | Team meeting | Training ACDM & combine some process |  |  | Time for doing week 1 | 1 | HOURS
| 2013-11-11 | 8:00PM | 10:30PM | 2.5 | Team Home Work | Do initial Measurement Plan document | AS_Measurement_PlanV1.0
| 2013-11-12 | 1:00PM | 3:00PM | 2 | Team Meetings | _Discuss to team rule in team charter _Review project charter, communication plan, Configuration plan, Measurement plan, Weekly report and Timelog _Discuss to process model |  |  | Time for doing week 2 | 13 | HOURS
| 2013-11-12 | 10:00PM | 11:30PM | 1.5 | Research | Java overview | Java Overview
| 2013-11-13 | 9:00AM | 11.00AM | 2 | Research | Spring core
| 2013-11-13 | 1:30PM | 3:30PM | 2 | Team Meetings | Review with team technical issues: Java, Hibernate, Spring, Maven
| 2013-11-13 | 8:00PM | 8:30PM | 0.5 | Research | Android basic |  |  | Time for doing week 3 | 0 | HOURS
| 2013-11-14 | [7 empty] | Time for doing week 4 | 0 | HOURS
| 2013-11-15 | [7 empty] | Time for doing week 5 | 0 | HOURS
3 | 2013-11-18 | [7 empty] | Time for doing week 6 | 0 | HOURS
| 2013-11-19 | [7 empty] | Time for doing week 7 | 0 | HOURS
| 2013-11-20 | [7 empty] | Time for doing week 8 | 0 | HOURS
| 2013-11-21 | [7 empty] | Time for doing week 9 | 0 | HOURS
| 2013-11-22 | [7 empty] | Time for doing week 10 | 0 | HOURS
4 | 2013-11-25 | [7 empty] | Time for doing week 11 | 0 | HOURS
| 2013-11-26 | [7 empty] | Time for doing week 12 | 0 | HOURS
| 2013-11-27 | [7 empty] | Time for doing week 13 | 0 | HOURS
| 2013-11-28 | [7 empty] | Time for doing week 14 | 0 | HOURS
| 2013-11-29 | [7 empty] | Time for doing week 15 | 0 | HOURS
5 | 2013-12-02 | [7 empty] | Time for doing week 16 | 0 | HOURS
| 2013-12-03 | [7 empty] | Time for doing week 17 | 0 | HOURS
| 2013-12-04 | [7 empty] | Time for doing week 18 | 0 | HOURS
| 2013-12-05 | [7 empty] | Time for doing week 19 | 0 | HOURS
| 2013-12-06 | [7 empty] | Time for doing week 20 | 0 | HOURS
6 | 2013-12-09 | [7 empty] | Time for doing week 21 | 0 | HOURS
| 2013-12-10 | [7 empty] | Time for doing week 22 | 0 | HOURS
| 2013-12-11 | [7 empty] | Time for doing week 23 | 0 | HOURS
| 2013-12-12 | [7 empty] | Time for doing week 24 | 0 | HOURS
| 2013-12-13 | [7 empty] | Time for doing week 25 | 0 | HOURS
7 | 2013-12-16 | [7 empty] | Time for doing week 26 | 0 | HOURS
| 2013-12-17 | [7 empty] | Time for doing week 27 | 0 | HOURS
| 2013-12-18 | [7 empty] | Time for doing week 28 | 0 | HOURS
| 2013-12-19 | [7 empty] | Time for doing week 29 | 0 | HOURS
| 2013-12-20 | [7 empty] | Time for doing week 30 | 0 | HOURS
8 | 2013-12-23
2013-12-24
2013-12-25
2013-12-26
2013-12-27
9 | 2013-12-30
2013-12-31
2014-01-01
2014-01-02
2014-01-03
10 | 2014-01-06
2014-01-07
2014-01-08
2014-01-09
2014-01-10
11 | 2014-01-13
2014-01-14
2014-01-15
2014-01-16
2014-01-17
12 | 2014-01-20
2014-01-21
2014-01-22
2014-01-23
2014-01-24
13 | 2014-01-27 |  |  |  | Nghỉ tết
| 2014-01-28 |  |  |  | Nghỉ tết
| 2014-01-29 |  |  |  | Nghỉ tết
| 2014-01-30 |  |  |  | Nghỉ tết
| 2014-01-31 |  |  |  | Nghỉ tết
14 | 2014-02-03 |  |  |  | Nghỉ tết
| 2014-02-04 |  |  |  | Nghỉ tết
| 2014-02-05 |  |  |  | Nghỉ tết
| 2014-02-06 |  |  |  | Nghỉ tết
| 2014-02-07 |  |  |  | Nghỉ tết
15 | 2014-02-10
2014-02-11
2014-02-12
2014-02-13
2014-02-14
16 | 2014-02-17
2014-02-18
2014-02-19
2014-02-20
2014-02-21
17 | 2014-02-24
2014-02-25
2014-02-26
2014-02-27
2014-02-28
18 | 2014-03-03
2014-03-04
2014-03-05
2014-03-06
2014-03-07
19 | 2014-03-10
2014-03-11
2014-03-12
2014-03-13
2014-03-14
20 | 2014-03-17
2014-03-18
2014-03-19
2014-03-20
2014-03-21
21 | 2014-03-24
2014-03-25
2014-03-26
2014-03-27
2014-03-28
22 | 2014-03-31
2014-04-01
2014-04-02
2014-04-03
2014-04-04
23 | 2014-04-07
2014-04-08
2014-04-09
2014-04-10
2014-04-11
24 | 2014-04-14
2014-04-15
2014-04-16
2014-04-17
2014-04-18
25 | 2014-04-21
2014-04-22
2014-04-23
2014-04-24
2014-04-25
26 | 2014-04-28
2014-04-29
2014-04-30
2014-05-01
2014-05-02
27 | 2014-05-05
2014-05-06
2014-05-07
2014-05-08
2014-05-09
28 | 2014-05-12
2014-05-13
2014-05-14
2014-05-15
2014-05-16
29 | 2014-05-19
2014-05-20
2014-05-21
2014-05-22
2014-05-23
30 | 2014-05-26
2014-05-27
2014-05-28
2014-05-29
2014-05-30
2014-05-31
2014-06-01
2014-06-02
2014-06-03
2014-06-04
2014-06-05
2014-06-06
2014-06-07
2014-06-08
2014-06-09
2014-06-10
2014-06-11
2014-06-12
2014-06-13
2014-06-14
2014-06-15
2014-06-16
2014-06-17
2014-06-18
2014-06-19
2014-06-20
2014-06-21
2014-06-22
2014-06-23
2014-06-24
2014-06-25
2014-06-26
2014-06-27
2014-06-28
2014-06-29
2014-06-30
2014-07-01
2014-07-02
2014-07-03
2014-07-04