## risk management
|  | Step 1 : Risk Identification |  |  |  |  | Step 2 : Risk analysis |  |  |  | Step 3 : Response Planing |  | Step 4 : Risk management
Risk ID | List of poissible risk | Trigger | Raised By | Date Raises | Risk Category | Probability | Impact | Priority Score | Mitigation methods | Risk strategy | Response plan | Owner | Status | Note
1 | Time is not enough for project development | The remaining time for project is not enough to implement remaining tasks in plan | Ngo Quang Huy | 2013-02-12 | Time | 0.086667 | 0.13667 | 0.011844 |  |  |  |  | Triggered
2 | Communication between project team and stakeholder (mentor and customer) is not good | Mentor doesn’t know current progress of project Customer misjudge team’s ability | Ngo Quang Huy | 2013-02-12 | Resource | 0.066667 | 0.10167 | 0.0067778 |  |  |  |  | Triggered
3 | Estimation is not well | We usually working over or behind schedule ( >10 task everyweek ) | Ngo Quang Huy | 2013-02-12 | Estimating | 0.086 | 0.11167 | 0.0096033 |  |  |  |  | Triggered
4 | Many defects in product after release | Defects > 10 | Ngo Quang Huy | 2013-02-12 |  | 0.096667 | 0.13333 | 0.012889 |  |  |  |  | Triggered
5 | Don't complete the full functionality required | A few members lose trust in the group | Ngo Quang Huy | 2013-02-12 | Performance | 0.086667 | 0.12667 | 0.010978 |  |  |  |  | Triggered
6 | Morale of the team was down | Too difficult to do or manage time is unresonable | Ngo Quang Huy | 2013-02-12 | Resource | 0.1 | 0.12 | 0.012 |  |  |  |  | Triggered
7 | The goal of stakeholders are different | Not understand about the ability and ambitious of stakeholders | Ngo Quang Huy | 2013-02-12 | Scope/Requirement | 0.055 | 0.135 | 0.007425 |  |  |  |  | Triggered
8 | Not enough knowledge about programming | Not be able to programing in java and android | Ngo Quang Huy | 2013-02-12 | Skills | 0.086667 | 0.113 | 0.0097933 |  |  |  |  | Triggered
9 | Difficult to communicate with customer | Can't establish meeting with customer regularly becasuse customer is too busy | Ngo Quang Huy | 2013-02-12 | Comunication | 0.051667 | 0.11333 | 0.0058556 |  |  |  |  | Triggered
10 | Team member's laptop is decayed | To announce from team member | Ngo Quang Huy | 2013-02-12 | Resource | 0.06 | 0.10633 | 0.00638 |  |  |  |  | Triggered
11 | A lots defect in architecture phase | Member lack of experience use to ACDM and design architecture | Ta Ngoc Thien Phu | 2013-04-12 |  | 0.096667 | 0.11333 | 0.010956 |  |  |  |  | Triggered
12 | Progress of architecture phase is slow | Not clearly understand to using ACDM, a lots defect is defined | Ta Ngoc Thien Phu | 2013-04-12 |  | 0.10333 | 0.10667 | 0.011022 |  |  |  |  | Triggered
13 | Lack of meeting place | no room to meeting | Ta Ngoc Thien Phu | 2013-04-12 | Resource | 0.135 | 0.08 | 0.0108 |  |  |  |  | Triggered
14 | lack of experience to manage project | Member lack of experience use to manage project on time and meet expectation | Ta Ngoc Thien Phu | 2013-04-12 | Skills | 0.096667 | 0.11967 | 0.011568 |  |  |  |  | Triggered
15 | Lack of skills about test tool | Member lack of experience use tool to test phase | Nguyen Phan Xuan Huy | 2013-04-12 | Technology | 0.083333 | 0.076667 | 0.0063889 |  |  |  |  | Triggered
16 | Communicate about tester and developer | Can't understand between tester and developer | Nguyen Phan Xuan Huy | 2013-04-12 | Comunication | 0.056667 | 0.063333 | 0.0035889 |  |  |  |  | Triggered
17 | test case pass not enough |  | Nguyen Phan Xuan Huy | 2013-04-12 | Controlling | 0.10667 | 0.086667 | 0.0092444
18 | Team members have to focus on semester (I,II) | members of team no focus on capstone project because they must prepare for final subjects | Huynh Trong Khang | 2013-04-12 | Time | 0.12 | 0.09 | 0.0108 |  |  |  |  | Triggered
19 | Occurring conflict between team members | members can't understand together | Huynh Trong Khang | 2013-04-12 | Comunication | 0.11333 | 0.12167 | 0.013789 |  |  |  |  | Triggered
20 | Team members working not complete, working on time deadline |  | Huynh Trong Khang | 2013-04-12 | Performance | 0.12 | 0.12 | 0.0144
21 | Team members have illness, need a few days to rest |  | Huynh Trong Khang | 2013-04-12 | Resource | 0.09 | 0.08 | 0.0072
22 | Identify the scope unclear of project |  | Huynh Trong Khang | 2013-04-12 | Scope/Requirement | 0.086667 | 0.12833 | 0.011122
23 | Concentrate too much to elicit depth of detail requirement stage | focus too deep on high level requirement | Huynh Trong Khang | 2013-04-12 | Scope | 0.093333 | 0.083333 | 0.0077778 |  |  |  |  | Triggered
24 | Exceeded time for requirement phase |  | Huynh Trong Khang | 2013-04-12 | Time | 0.1 | 0.08 | 0.008
| avoid | go away far from that risk
| mitigate | use some method to control that risk
| accept | live with that risk
| identified | define risk
| analys complete | risk was analys
| planning complete | planning for control risk
| triggered | descrie risk
| resolved | risk wae mitgate

## risk priority (probability)
ID | Châu | Đạo | Q.Huy | X.Huy | Khang | Phú
1 | 50 | 40 | 60 |  | 50 | 60
2 | 50 | 40 | 40 |  | 30 | 40
3 | 68 | 60 | 40 |  | 50 | 40
4 | 70 | 40 | 60 |  | 60 | 60
5 | 80 | 30 | 50 |  | 50 | 50
6 | 80 | 60 | 50 |  | 60 | 50
7 | 25 | 30 | 40 |  | 30 | 40
8 | 60 | 50 | 50 |  | 50 | 50
9 | 5 | 30 | 45 |  | 30 | 45
10 | 10 | 40 | 30 |  | 70 | 30
11 | 20 | 50 | 80 |  | 60 | 80
12 | 10 | 80 | 85 |  | 50 | 85
13 | 85 | 80 | 80 |  | 80 | 80
14 | 80 | 60 | 60 |  | 30 | 60
15 | 30 | 50 | 70 |  | 30 | 70
16 | 30 | 30 | 40 |  | 30 | 40
17 | 50 | 50 | 80 |  | 60 | 80
18 | 20 | 70 | 90 |  | 90 | 90
19 | 70 | 60 | 70 |  | 70 | 70
20 | 60 | 60 | 80 |  | 80 | 80
21 | 20 | 60 | 70 |  | 50 | 70
22 | 40 | 60 | 65 |  | 30 | 65
23 | 50 | 50 | 60 |  | 60 | 60
24 | 60 | 60 | 70 |  | 40 | 70

## risk priority (impact)
ID | Châu | Đạo | Q.Huy | X.Huy | Khang | Phú
1 | 90 | 80 | 80 |  | 80 | 80
2 | 75 | 50 | 60 |  | 60 | 60
3 | 85 | 70 | 60 |  | 60 | 60
4 | 80 | 80 | 80 |  | 80 | 80
5 | 70 | 80 | 70 |  | 70 | 90
6 | 90 | 60 | 70 |  | 70 | 70
7 | 95 | 80 | 70 |  | 70 | 90
8 | 89 | 50 | 70 |  | 70 | 60
9 | 55 | 70 | 70 |  | 70 | 75
10 | 69 | 50 | 70 |  | 70 | 60
11 | 40 | 70 | 80 |  | 80 | 70
12 | 30 | 80 | 70 |  | 70 | 70
13 | 20 | 40 | 60 |  | 60 | 60
14 | 99 | 60 | 70 |  | 70 | 60
15 | 50 | 50 | 30 |  | 30 | 70
16 | 40 | 40 | 30 |  | 30 | 50
17 | 50 | 50 | 50 |  | 50 | 60
18 | 20 | 50 | 70 |  | 70 | 60
19 | 75 | 70 | 70 |  | 70 | 80
20 | 70 | 70 | 70 |  | 70 | 80
21 | 30 | 50 | 50 |  | 50 | 60
22 | 75 | 70 | 80 |  | 80 | 80
23 | 50 | 50 | 50 |  | 50 | 50
24 | 50 | 50 | 40 |  | 40 | 60