## List main task
No | Activities
1 | Team Meetings
2 | Reading
3 | Self Prepare
4 | Team Home Work
5 | Team Work
6 | Meetings with Faculty
7 | Meetings with Customer
8 | Training
9 | Research
10 | Review with customer
11 | Review with technical support

## SEP-PROJECT
Time Recording Log For: Admission project
Le Ngoc Chau - T103573
[7 empty] | Minimum: 5 hours/day 25 hours/week (5hours * 5 days) 700 hours/30 weeks (25 hours * 28 weeks) | Maximum: 24 hours/day 168 hours/week (24hours * 7 days) 4704 hours/30 weeks (168 hours * 28 weeks)
Week | Date | Start | Stop | Delta Time | Total time of day | Activity | Description | Artifact | Note
1 | 2013-11-07 | 13:20 | 14:30 | 1.16 | 1.24 | Team meeting | - Repair for kick off meeting - Devide team work for team member - Define role in project |  |  | SUMMARY: TIME FOR DOING PROJECT | 106.233 | HOURS
|  | 14:30 | 14:35 | 0.08 |  | Team Home Work | - Update timelog
| 2013-11-08 | 14:00 | 15:10 | 1.16 | 1.74 | Kick off meeting | - Discuss about communication plan between customer and team - Discuss about system concept |  |  | Time for doing week 1 | 2.98 | HOURS
|  | 15:10 | 15:40 | 0.5 |  | Meetings with Faculty | - Discus about weekly report meeting
|  | 3.40 PM | 15:45 | 0.08 |  | Team Home Work | - Update timelog
2 | 2013-11-12 | 13:45 | 15:00 | 2.25 | 2.33 | Team Meetings | - Review Team charter - Review Communication plan - Review Configuration plan - Review Measurement plan | - AS_PM_TeamCharter.docx version 1.0 - AS_PM _ConfigurationPlan.docx version 1.0 - AS_PM_CommunicationPlan.docx version 1.0 - AS_PM_MeasurementPlan.docx version 1.0 |  | Time for doing week 2 | 13.293 | HOURS
|  | 15:00 | 15:05 | 0.08 |  | Team Home Work | - Update timelog
| 2013-11-13 | 13:30 | 15:30 | 2 | 3 | Team Meetings | - Review Maven, Spring, Hibernate, Java | - Java Overview + Spring.docx - Training.pptx
|  | 22:00 | 23:00 | 1 |  | Team Home Work | - Create weekly report powerpoint - Update timelog | - AS_DeadlineTeam_Week2.pptx |  | Time for doing week 3 | 28.56 | HOURS
| 2013-11-14 | 20:00 | 20:45 | 0.75 | 2.08 | Team Work | - Update document's name - Update weekly report powerpoint | - AS_DeadlineTeam_Week2.pptx |  | Time for doing week 4 | 28.33 | HOURS
|  | 9:00 | 10:15 | 1.25 |  | Meetings with Faculty | Present work that team completed in this week 2 | - AS_DeadlineTeam_Week2.pptx
|  | 10:15 | 10:20 | 0.08 |  | Team Home Work | - Update timelog
| 2013-11-15 | 13:00 | 14:05 | 1.083 | 5.883 | Team Meetings | - Ngo Quang Huy present about Risk management plan - Nguyen Phan Xuan Huy present about spring framwork | - AS_PM_RiskManagementPlan.docx version 1.0 - Folder Spring Framwork |  | Time for doing week 5 | 21.82 | HOURS
|  | 22:00 | 12:20 | 2.33 |  | Team Home Work | - Update template: + Change management plan + Communication plan + Configuration management plan + Timelog for team + Measurement plan + Project charter + Risk management plan + Team charter + Individual time log + Weekly report | - Template: + AS_DeadlineTeam_Week#_template.pptx +AS_PM_ChangeManagementPlan_template.docx +AS_PM_CommunicationPlan_template.docx +AS_PM_ConfigurationPlan_template.docx +AS_PM_DeadlineTeam_TimeLog_template.xls +AS_MeasurementPlan_template.docx +AS_PM_Meeting_Minutes_ddmmyy_#_template.docx +AS_PM_ProjectCharter_template.docx +AS_PM_RiskManagementPlan_template.docx +AS_PM_TeamCharter_template.docx +AS_PM_TimeLog_DeadlineTeam_Name_template.xls +AS_PM_WeeklReport_template.xls +AS_PM_WeeklReport_individualtemplate.xls |  | Time for doing week 6 | 11.25 | HOURS
| 2013-11-16 | 8:05 | 9:00 | 0.55 | 2.47 | Team Home Work | - Update Team charter - Update Configuration management plan - Update Measurement plan | - Team charter version 1.2 - Configuration management plan version 1.1 - Measurement plan version 1.1 |  | Time for doing week 7 | 0 | HOURS
|  | 20:00 | 22:20 | 1.92 |  | Team Home Work | - Update template for goal - question - metrics of Measurement plan - Update timlog | - Measurement plan version 1.1
3 | 2013-11-19 | 8:00 | 10:30 | 2 | 3.08 | Team Home Work | - Update time log template |  |  | Time for doing week 9 | 0 | HOURS
|  | 13:30 | 14:30 | 1 |  | Team Meetings | - Review Change management plan - Review Scrum modal and ACDM - Review Test management plan
|  | 14:30 | 14:35 | 0.08 |  | Team Home Work | - Update timelog
| 2013-11-20 | 13:30 | 17:30 | 4 | 4.08 | Team Work | - Review Change management plan - Review Requirement plan - Review Architecture plan - Review Change log template - Review Master plan - Review Scrum model and ACDM |  |  | Time for doing week 10 | 0 | HOURS
|  | 17:30 | 17:35 | 0.08 |  | Team Home Work | - Update timelog
| 2013-11-21 | 8:00 | 9:00 | 1 | 11.15 | Team Work | - Review weekly report 3 | - AS_DeadlineTeam_Week3.pptx |  | Time for doing week 11 | 0 | HOURS
|  | 9:00 | 10:10 | 1.16 |  | Meetings with Faculty | - Present about work that assigned in week3 - Present about Change management plan - Present about ACDM and Scrum model - Present about Requirement plan
|  | 10:10 | 11:30 | 1.33 |  | Team Meetings | - Devide work for week 4
|  | 13:30 | 15:00 | 1.5 |  | Research | - Research about Stage 6 and role Supporter in ACDM | Stage 6 + Sup.docx
|  | 15:00 | 17:10 | 2.16 |  | Team Meetings | - Integrate the work of member about ACDM - Devide team work for team member | ACDM.xlsx DevideTeamWork1.docx DevideTeamWork2.docx
|  | 20:00 | 23:59 | 4 |  | Reading | - Read ACDM book - Update timelog
| 2013-11-22 | 13:30 | 14:45 | 1.25 | 5 | Team Meetings | - Review Scrum model - Review Scrum role and responsibility - Review how to map ACDM into Scrum - Devide team work for team member | DevideTeamWork3.docx |  | Time for doing week 12 | 0 | HOURS
|  | 15:30 | 16:30 | 1 |  | Team Work | - Update devide team work for team member - Review test process - Update team evaluation | DevideTeamWork3.docx
|  | 21:45 | 12:30 | 2.75 |  | Reading | - Reading about ACDM - Update timelog
| 2013-11-23 | 13:00 | 13:45 | 0.25 | 5.25 | Team Meetings | - Review process, document, template
|  | 13:45 | 14:45 | 1 |  | Team Work | - Update process document, description stage 6 in ACDM | - Model.vsdx - Stage6.docx - AS_PM_ProjectPlan.docx
|  | 20:00 | 12:00 | 4 |  | Team Home Work | - Create SRM guide, SPM guide, Daily Meeting guide, Scrum iteration guide - Update timelog | - AS_PM_DailyScrumGuide.docx - AS_PM_SprintIterationGuide.docx - AS_PM_SprintPlanningMeetingGuide.docx - AS_PM_SprintReviewMeetingGuide.doc
4 | 2013-11-26 | 19:45 | 21:00 | 2.25 | 7 | Team Work | - Review process |  |  | Time for doing week 13 | 0 | HOURS
|  | 21:00 | 23:30 | 2.5 |  | Meetings with Faculty | - Reivew process - Review Communication plan - Review Change management plan - Review Risk management plan - Review Measurement plan - Review timelog template, daily report - Review weekly report - Review requirement plan - Review Operation Requirement - Review Architecture plan - Architectural drivers template - Architecture design document template - Review test plan, test case template, test report template |  |  | Time for doing week 14 | 0 | HOURS
|  | 13:30 | 14:30 | 1 |  | Team Meetings | - Devide team work that repair for meeting with customer
|  | 14:45 | 16:00 | 1.25 |  | Team Work | - Update process - Update timelog
| 2013-11-27 | 13:30 | 15:50 | 2.33 | 5.08 | Team Meetings | - Repair question for meeting with customer |  |  | Time for doing week 15 | 0 | HOURS
|  | 22:00 | 12:45 | 2.75 |  | Reading
| 2013-11-28 | 8:00 | 9:15 | 1.25 | 5.75 | Team Work | - Review admission system development process - Review question that repaired for meeting with customer |  |  | Time for doing week 16 | 0 | HOURS
|  | 9:15 | 11:00 | 1.75 |  | Meetings with Customer | - Get requirement about admission system
|  | 13:30 | 16:15 | 2.75 |  | Team Meetings | - Discuss about functions that supported by prouct owners
| 2013-11-29 | 13:30 | 17:00 | 3.5 | 6.25 | Team Meetings | - Discuss about functions that supported by prouct owners |  |  | Time for doing week 17 | 0 | HOURS
|  | 22:00 | 12:45 | 2.75 |  | Team Home Work | - Review meeting minutes and review admission system development process.
| 2013-11-30 | 7:15 | 8:30 | 1.25 | 4.25 | Team Home Work | - Update meeting minutes
|  | 9:00 | 0:00 | 3 |  | Team Home Work | - Update meeting minutes - Update timelog
5 | 2013-12-02 | 8:00 | 9:00 | 1 | 1 | Team Home Work | - Define entities and documentation - Update timelog | - Functional and QA.docx - Entity.docx |  | Time for doing week 18 | 0 | HOURS
| 2013-12-03 | 8:00 | 9:00 | 1 | 5.5 | Team Work | - Review entity |  |  | Time for doing week 19 | 0 | HOURS
|  | 9:00 | 10:30 | 1.5 |  | Meetings with Customer | - Review entities and how to documentation
|  | 10:30 | 11:00 | 0.5 |  | Team Meetings | - Discuss about document
|  | 13:30 | 15:30 | 2.5 |  | Training | -Training about Java and Sprint framework + Setup nessecsary tools + Understand DI and AOP in Spring framework + Demo Hello world with Spring - Update timelog
| 2013-12-04 | 9:00 | 12:00AM | 3 | 7.5 | Team Work | - Update Entities and project plan | - Entity - C.docx |  | Time for doing week 20 | 0 | HOURS
|  | 13:30 | 18:00 | 4.5 |  | Team Meetings | - Review list risk, measurement plan - Review master plan, master design plan - Reivew project plan - Review entities
| 2013-12-05 | 3:00 | 6:00 | 3 | 7.82 | Team Home Work | - Define weekly report - Update project plan - Update timelog |  |  | Time for doing week 21 | 0 | HOURS
|  | 8:00 | 9:10AM | 1.16 |  | Team Work | - Update timelog for team
|  | 9:10AM | 10:40AM | 1.5 |  | Meetings with Faculty | - Review List risk, measurement plan - Review master plan, master design plan - Review project plan - Review sprint backlog template
|  | 10:40AM | 11:30AM | 0.66 |  | Team Meetings | - Devide team work - Update entities
|  | 16:30 | 6:00PM | 1.5 |  | Team Work | - Update timelog for team - Update timelog
6 | 2013-12-10 | 8:00 | 9:00AM | 1 | 6 | Team work | - Review use case and quality attribute |  |  | Time for doing week 24 | 0 | HOURS
|  | 9:00AM | 11:30AM | 2.5 |  | Training | - Training about spring framework
|  | 1:30PM | 4:00PM | 2.5 |  | Training | - Training about connect database
| 2013-12-12 | 8:00AM | 9:00AM | 1 | 4 | Team Work | - Review project plan - Timelog |  |  | Time for doing week 26 | 0 | HOURS
|  | 9:00AM | 11:00AM | 2 |  | Meetings with Faculty | - Review project plan, Risk list, plan for next week
|  | 11:00AM | 12:00AM | 1 |  | Team Meetings | - Discuss about team work
| 2013-12-13 | 5:00AM | 6:00AM | 1 | 1.25 | Reading | - Reading about project plan and process |  |  | Time for doing week 27 | 0 | HOURS
|  | 8:15AM | 8:30AM | 0.25 |  | Team Work | - Update timelog
7 | 2013-12-16 |  |  |  | 0 |  |  |  |  | Time for doing week 28 | 0 | HOURS
| 2013-12-17 |  |  |  | 0 |  |  |  |  | Time for doing week 29 | 0 | HOURS
| 2013-12-18 |  |  |  | 0 |  |  |  |  | Time for doing week 30 | 0 | HOURS
| 2013-12-19 |  |  |  | 0
| 2013-12-20 |  |  |  | 0
8 | 2013-12-23 |  |  |  | 0
| 2013-12-24 |  |  |  | 0
| 2013-12-25 |  |  |  | 0
| 2013-12-26 |  |  |  | 0
| 2013-12-27 |  |  |  | 0
9 | 2013-12-30 |  |  |  | 0
| 2013-12-31 |  |  |  | 0
| 2014-01-01 |  |  |  | 0
| 2014-01-02 |  |  |  | 0
| 2014-01-03 |  |  |  | 0
10 | 2014-01-06 |  |  |  | 0
| 2014-01-07 |  |  |  | 0
| 2014-01-08 |  |  |  | 0
| 2014-01-09 |  |  |  | 0
| 2014-01-10 |  |  |  | 0
11 | 2014-01-13 |  |  |  | 0
| 2014-01-14 |  |  |  | 0
| 2014-01-15 |  |  |  | 0
| 2014-01-16 |  |  |  | 0
| 2014-01-17 |  |  |  | 0
12 | 2014-01-20 |  |  |  | 0
| 2014-01-21 |  |  |  | 0
| 2014-01-22 |  |  |  | 0
| 2014-01-23 |  |  |  | 0
| 2014-01-24 |  |  |  | 0
13 | 2014-01-27 |  |  |  | 0 | Nghỉ tết
| 2014-01-28 |  |  |  | 0 | Nghỉ tết
| 2014-01-29 |  |  |  | 0 | Nghỉ tết
| 2014-01-30 |  |  |  | 0 | Nghỉ tết
| 2014-01-31 |  |  |  | 0 | Nghỉ tết
14 | 2014-02-03 |  |  |  | 0 | Nghỉ tết
| 2014-02-04 |  |  |  | 0 | Nghỉ tết
| 2014-02-05 |  |  |  | 0 | Nghỉ tết
| 2014-02-06 |  |  |  | 0 | Nghỉ tết
| 2014-02-07 |  |  |  | 0 | Nghỉ tết
15 | 2014-02-10 |  |  |  | 0
| 2014-02-11 |  |  |  | 0
| 2014-02-12 |  |  |  | 0
| 2014-02-13 |  |  |  | 0
| 2014-02-14 |  |  |  | 0
16 | 2014-02-17 |  |  |  | 0
| 2014-02-18 |  |  |  | 0
| 2014-02-19 |  |  |  | 0
| 2014-02-20 |  |  |  | 0
| 2014-02-21 |  |  |  | 0
17 | 2014-02-24 |  |  |  | 0
| 2014-02-25 |  |  |  | 0
| 2014-02-26 |  |  |  | 0
| 2014-02-27 |  |  |  | 0
| 2014-02-28 |  |  |  | 0
18 | 2014-03-03 |  |  |  | 0
| 2014-03-04 |  |  |  | 0
| 2014-03-05 |  |  |  | 0
| 2014-03-06 |  |  |  | 0
| 2014-03-07 |  |  |  | 0
19 | 2014-03-10 |  |  |  | 0
| 2014-03-11 |  |  |  | 0
| 2014-03-12 |  |  |  | 0
| 2014-03-13 |  |  |  | 0
| 2014-03-14 |  |  |  | 0
20 | 2014-03-17 |  |  |  | 0
| 2014-03-18 |  |  |  | 0
| 2014-03-19 |  |  |  | 0
| 2014-03-20 |  |  |  | 0
| 2014-03-21 |  |  |  | 0
21 | 2014-03-24 |  |  |  | 0
| 2014-03-25 |  |  |  | 0
| 2014-03-26 |  |  |  | 0
| 2014-03-27 |  |  |  | 0
| 2014-03-28 |  |  |  | 0
22 | 2014-03-31 |  |  |  | 0
| 2014-04-01 |  |  |  | 0
| 2014-04-02 |  |  |  | 0
| 2014-04-03 |  |  |  | 0
| 2014-04-04 |  |  |  | 0
23 | 2014-04-07 |  |  |  | 0
| 2014-04-08 |  |  |  | 0
| 2014-04-09 |  |  |  | 0
| 2014-04-10 |  |  |  | 0
| 2014-04-11 |  |  |  | 0
24 | 2014-04-14 |  |  |  | 0
| 2014-04-15 |  |  |  | 0
| 2014-04-16 |  |  |  | 0
| 2014-04-17 |  |  |  | 0
| 2014-04-18 |  |  |  | 0
25 | 2014-04-21 |  |  |  | 0
| 2014-04-22 |  |  |  | 0
| 2014-04-23 |  |  |  | 0
| 2014-04-24 |  |  |  | 0
| 2014-04-25 |  |  |  | 0
26 | 2014-04-28 |  |  |  | 0
| 2014-04-29 |  |  |  | 0
| 2014-04-30 |  |  |  | 0
| 2014-05-01 |  |  |  | 0
| 2014-05-02 |  |  |  | 0
27 | 2014-05-05 |  |  |  | 0
| 2014-05-06 |  |  |  | 0
| 2014-05-07 |  |  |  | 0
| 2014-05-08 |  |  |  | 0
| 2014-05-09 |  |  |  | 0
28 | 2014-05-12 |  |  |  | 0
| 2014-05-13 |  |  |  | 0
| 2014-05-14 |  |  |  | 0
| 2014-05-15 |  |  |  | 0
| 2014-05-16 |  |  |  | 0
29 | 2014-05-19 |  |  |  | 0
| 2014-05-20 |  |  |  | 0
| 2014-05-21 |  |  |  | 0
| 2014-05-22 |  |  |  | 0
| 2014-05-23 |  |  |  | 0
30 | 2014-05-26 |  |  |  | 0
| 2014-05-27 |  |  |  | 0
| 2014-05-28 |  |  |  | 0
| 2014-05-29 |  |  |  | 0
| 2014-05-30 |  |  |  | 0