## risk management
|  | Step 1 : Risk Identification |  |  |  |  | Step 2 : Risk analysis |  |  |  | Step 3 : Response Planing |  | Step 4 : Risk management
Risk ID | List of poissible risk | Trigger | Raised By | Date Raises | Risk Category | Probability | Impact | Priority Score | Mitigation methods | Risk strategy | Response plan | Owner | Status | Note
1 | Requirements are misunderstood | No have a specific plan No meet customer regularly to review product backlog & architectural drivers | Ngo Quang Huy | 2013-02-12 | requirement | 0.66667 | 0.86667 | 0.57778
2 | Time is not enough for project development | The remaining time for project is not enough to implement remaining tasks in plan | Ngo Quang Huy | 2013-02-12 | Time | 0.27333 | 0.86667 | 0.23689
3 | Communication between project team and stakeholder (mentor and customer) is not good | Mentor doesn’t know current progress of project Customer misjudge team’s ability | Ngo Quang Huy | 2013-02-12 | Resource
4 | Estimation is not well | We usually working over or behind schedule ( >10 task everyweek ) | Ngo Quang Huy | 2013-02-12 | Estimating
5 | Many defects in product after release | Defects > 10 | Ngo Quang Huy | 2013-02-12
6 | Don't complete the full functionality required | A few members lose trust in the group | Ngo Quang Huy | 2013-02-12 | Performance
7 | Morale of the team was down | Too difficult to do or manage time is unresonable | Ngo Quang Huy | 2013-02-12 | Resource
8 | The goal of stakeholders are different | Not understand about the ability and ambitious of stakeholders | Ngo Quang Huy | 2013-02-12 | Scope/Requirement
10 | Not enough knowledge about programming | Not be able to programing in java and android | Ngo Quang Huy | 2013-02-12 | Skills
11 | Difficult to communicate with customer | Can't establish meeting with customer regularly becasuse customer is too busy | Ngo Quang Huy | 2013-02-12 | Comunication
12 | Team member's laptop is decayed | To announce from team member | Ngo Quang Huy | 2013-02-12 | Resource
13 | A lots defect in architecture phase | Member lack of experience use to ACDM and design architecture | Ta Ngoc Thien Phu | 2013-04-12
14 | Progress of architecture phase is slow | Not clearly understand to using ACDM, a lots defect is defined | Ta Ngoc Thien Phu | 2013-04-12
15 | Lack of meeting place | no room to meeting | Ta Ngoc Thien Phu | 2013-04-12 | Resource
16 | lack of experience to manage project | Member lack of experience use to manage project on time and meet expectation | Ta Ngoc Thien Phu | 2013-04-12 | Skills
17 | Lack of skills about test tool |  | Nguyen Phan Xuan Huy | 2013-04-12 | Technology
18 | Communicate about tester and developer |  | Nguyen Phan Xuan Huy | 2013-04-12 | Comunication
19 | pass k du testcase |  | Nguyen Phan Xuan Huy | 2013-04-12 | Controlling
20 | Team members have to focus on semester (I,II) |  | Huynh Trong Khang | 2013-04-12 | Time
21 | Occurring conflict between team members |  | Huynh Trong Khang | 2013-04-12 | Comunication
22 | Team members working not complete, working on time deadline |  | Huynh Trong Khang | 2013-04-12 | Performance
23 | Team members have illness, need a few days to rest |  | Huynh Trong Khang | 2013-04-12 | Resource
24 | Identify the scope unclear of project |  | Huynh Trong Khang | 2013-04-12 | Scope/Requirement
25 | Concentrate too much to elicit depth of detail requirement stage |  | Huynh Trong Khang | 2013-04-12 | Scope
26 | Exceeded time for requirement phase |  | Huynh Trong Khang | 2013-04-12 | Time
| avoid | go away far from that risk
| mitigate | use some method to control that risk
| accept | live with that risk