## Sheet1
RISK ID | LIST RISK | PROBABILITY | IMPACT | mitigate method
1 | Time is not enough for project development | 40 | 80 | 0.32
2 | Communication between project team and stakeholder (mentor and customer) is not good | 50 | 50 | 0.25
3 | Estimation is not well | 60 | 70 | 0.42
4 | Many defects in product after release | 30 | 60 | 0.18
5 | Don't complete the full functionality required | 50 | 50 | 0.25
6 | Morale of the team was down | 50 | 80 | 0.4
7 | The goal of stakeholders are different | 20 | 80 | 0.16
8 | Not enough knowledge about programming | 20 | 40 | 0.08
9 | Difficult to communicate with customer | 20 | 60 | 0.12
10 | Team member's laptop is decayed | 25 | 30 | 0.075
11 | A lots defect in architecture phase | 70 | 65 | 0.455
12 | Progress of architecture phase is slow | 80 | 70 | 0.56
13 | Lack of meeting place | 10 | 10 | 0.01
14 | lack of experience to manage project | 30 | 50 | 0.15
15 | Lack of skills about test tool | 30 | 30 | 0.09
16 | Communicate about tester and developer | 55 | 50 | 0.275
17 | test case pass not enough | 60 | 50 | 0.3
18 | Team members have to focus on semester (I,II) | 40 | 50 | 0.2
19 | Occurring conflict between team members | 20 | 30 | 0.06
20 | Team members working not complete, working on time deadline | 50 | 70 | 0.35
21 | Team members have illness, need a few days to rest | 10 | 30 | 0.03
22 | Identify the scope unclear of project | 10 | 80 | 0.08
23 | Concentrate too much to elicit depth of detail requirement stage | 30 | 40 | 0.12
24 | Exceeded time for requirement phase | 40 | 30 | 0.12