## Revision history
Document Reviewer Information
Reviewer Name | Review Attendance (R/S) | Comments
R/S: Required or Suggested participants or functions for the document review meeting
Document Approver Information
Approver Name | Approver Function | Comments
Document Revision History
Date | Revision | Status | Change Summary | Revised by | Version
|  | on going |  | Ngo Quang Huy | 1
|  | on going |  | Ngo Quang Huy | 2

## Master plan
ADMISSION SYSTEM PROJECT
| ID | PHASE | TASK NAME | START | FINISH | ACTUAL FINISH | RESOURCES NAME | STATUS
| 1 | Project management | project organization and team structuring | 2013-07-11 | 2013-07-11 | 2013-07-11 | Deadline team | DONE
| 2 |  | create project plan | 2013-07-11 | 25/11/2013 | 25/11/2013 | Le Ngoc Chau | DONE
| 3 |  | create master plan | 2013-07-11 | 25/11/2013 |  | Ngo Quang Huy | GOING
| 4 |  | kick-off meeting of team | 2013-07-11 | 2013-07-11 | 2013-07-11 | Deadline team | DONE
|  |  | kick-off meeting with mentor | 2013-08-11 | 2013-08-11 | 2013-08-11 | Deadline team | DONE
| 5 |  | Create risk management plan | 2013-07-11 | 25/11/2013 | 15/11/2013 | Ngo Quang Huy | DONE
| 6 |  | create change management plan | 2013-07-11 | 25/11/2013 | 19/11/2013 | Khau Thanh dao | DONE
| 7 |  | create test management plan | 2013-07-11 | 25/11/2013 | 19/11/2013 | Nguyen Phan Xuan huy | DONE
| 8 |  | create communication | 2013-07-11 | 25/11/2013 | 15/11/2013 | Le Ngoc Chau | DONE
| 9 |  | create configuration document | 2013-07-11 | 25/11/2013 | 15/11/2013 | Ta Ngoc Thien Phu | DONE
| 10 |  | create measurement plan | 2013-07-11 | 25/11/2013 | 15/11/2013 | Huynh Trong Khang | DONE
| 11 |  | create team charter | 2013-07-11 | 25/11/2013 | 15/11/2013 | Le Ngoc Chau | DONE
| 12 |  | create timelog | 2013-07-11 | 25/11/2013 | 19/11/2013 | Le Ngoc Chau | DONE
| 13 | Requirement | develop requirement plan | 18/11/2013 | 27/11/2013 | 21/11/2013 | Huynh Trong Khang | DONE
| 14 |  | prepare question list to gather requirement | 26/11/2013 | 27/11/2013 | 27/11/2013 | Deadline team | DONE
| 15 |  | communicate with customer to gather requirement | 28/11/2013 | 28/11/2013 | 28/11/2013 | Deadline team | DONE
| 16 |  | create operational requirement documents | 26/11/2013 | 26/11/2013 | 26/11/2013 | Huynh Trong Khang | DONE
| 17 |  | create product backlog | 2013-12-11 | 22/12/2013 |  | Huynh Trong Khang
| 18 |  | create architect driver specification | 2013-12-11 | 22/12/2013 |  | Huynh Trong Khang
| 19 |  | trainning spring core | 2013-03-12 | 19/01/2014 |  | Deadline team | GOING
| 20 |  | identify entities of product | 28/11/2013 | 2013-04-12 |  | Deadline team
| 21 |  | identify functional requirement | 28/11/2013 | 2013-04-12 |  | Deadline team
| 22 |  | identify quality attribute | 28/11/2013 | 2013-04-12 |  | Deadline team
| 23 |  | develop usecase for "soan tin" | 2013-05-12 | 2013-11-12 |  | Deadline team
| 24 |  | develop usecase for "danh muc" | 2013-05-12 | 2013-11-12 |  | Deadline team
| 25 |  | develop usecase for "hoi dap" | 2013-05-12 | 2013-11-12 |  | Deadline team
| 26 |  | develop usecase for "hoi dap" for android | 2013-05-12 | 2013-11-12 |  | Deadline team
| 27 |  | identify vision and scope project | 2013-12-12 | 2013-12-12 |  | Deadline team
| 28 |  | develop GUI for " soan tin" |  |  |  | Deadline team
| 29 |  | develop GUI for "danh muc" |  |  |  | Deadline team
| 30 |  | develop GUI for "hoi dap" |  |  |  | Deadline team
| 31 |  | develop GUI for "hoi dap for android" |  |  |  | Deadline team
| 32 |  | baseline requirement | 30/12/2013 | 30/12/2013 |  | Deadline team
| 33 | Architect & Design | create architural plan | 18/11/2013 | 27/11/2013 | 21/11/2013 | Ta Ngoc Thien Phu
| 34 |  | system context | 31/12/2013 | 31/12/2013 |  | Deadline team
| 35 |  | Develop overal physical view for admission system (high level) | 2014-01-01 | 2013-04-01
| 36 |  | Develop overal static view for admission system (high level) | 2014-01-01 | 2013-04-01
| 37 |  | Develop overal dynamic view for admission system (high level) | 2014-01-01 | 2013-04-01
| 38 |  | mapping physical with dynamic | 2014-05-01 | 2013-09-01
| 39 |  | mapping static with dynamic | 2014-05-01 | 2013-09-01
| 40 |  | design database | 2014-10-01 | 2014-11-01
| 41 |  | Evaluate architect and design for admission system | 2014-12-01 | 14/1/2014 |  | Deadline team
review sớm hơn | 42 |  | review architect and design with Mr.Quang | 15/1/2014 | 17/1/2014 |  | Deadline team
| 43 |  | Create sprint backlog | 18/1/2014 | 19/1/2014 |  | Deadline team
| 44 | Scrum Sprints | detail design for sprint # | 20/01/2013
| 45 |  | create database
| 46 |  | implement componant of sprint #
| 47 |  | implement unit test
| 48 |  | implement itegration test
| 49 |  | fix bug
| 50 |  | prepare story for sprint #
| 51 |  | release sprint #