## List main task
No | Activities
1 | Team Meetings
2 | Reading
3 | Self Prepare
4 | Team Home Work
5 | Team Work
6 | Meetings with Faculty
7 | Meetings with Customer
8 | Training
9 | Research
10 | Review with customer
11 | Review with technical support

## SEP-PROJECT
Time Recording Log For: Admission project | [6 empty] | Start Date: 08/11/2013 End Date:
Khau Thanh Dao - T105026
[8 empty] | Minimum: 5 hours/day 25 hours/week (5hours * 5 days) 700 hours/30 weeks (25 hours * 28 weeks) | Maximum: 24 hours/day 168 hours/week (24hours * 7 days) 4704 hours/30 weeks (168 hours * 28 weeks)
Week | Date | Start | Stop | Delta Time | Total time of day | Plan | Activity | Description | Artifact | Note
1 | 2013-11-07 | 13:20 | 14:30 | 1.16 | 1.16 |  | Team meeting | - Repair for kick off meeting - Devide team work for team member - Define role in project |  |  | SUMMARY: TIME FOR DOING PROJECT | 68.38 | HOURS
| 2013-11-08 | 14:00 | 15:10 | 1.16 | 1.66 |  | Kick off meeting | - Discuss about communication plan between customer and team - Discuss about system concept |  |  | Time for doing week 1 | 2.82 | HOURS
|  | 15:10 | 15:40 | 0.5 |  |  | Meetings with Faculty | - Discus about weekly report meeting
2 | 2013-11-11 | 14:00 | 15:30 | 1.5 | 1.5 |  | Training | -Training ACDM |  |  | Time for doing week 2 | 12.5 | HOURS
|  | 22:00 | 23:30 | 1.5 | 1.5 |  | Research | -Research Hibernate,Maven | - Java Overview + Spring.docx - Training.pptx
| 2013-11-12 | 13:45 | 15:00 | 2.25 | 2.25 |  | Team Meetings | - Review Team charter - Review Communication plan - Review Configuration plan - Review Measurement plan | - AS_PM_TeamCharter.docx version 1.0 - AS_PM _ConfigurationPlan.docx version 1.0 - AS_PM_CommunicationPlan.docx version 1.0 - AS_PM_MeasurementPlan.docx version 1.0
| 2013-11-13 | 13:30 | 15:30 | 2 | 3 |  | Team Meetings | -Training spring, maven,hibernate - Update template | Training Document
|  | 22:00 | 23:00 | 1 |  |  | Team Home Work | -Do change management plan -Update template | AS_PM_ChangemanagementPlan |  | Time for doing week 3 | 21.9 | HOURS
| 2013-11-14 | 8:00 | 9:00 | 1 | 2.25 |  | Team Home Work | -Do change management plan | AS_PM_ChangemanagementPlan |  | Time for doing week 4 | 20.16 | HOURS
|  | 9:00 | 10:15 | 1.25 |  |  | Meetings with Faculty | Present work that team completed in this week 2 | - AS_DeadlineTeam_Week2.pptx
| 2013-11-15 | 13:00 | 14:00 | 1 | 2 |  | Team Meetings
|  | 20:00 | 21:00 | 1 |  |  | Team Home Work | Do Master Plan | AS_PM_MasterPlan |  | Time for doing week 5 | 11 | HOURS
3 | 2013-11-18 | 15:00 | 16:00 | 1 | 3 |  | Team Home Work | Master Plan | AS_PM_MasterPlan |  | Time for doing week 8 | 0 | HOURS
|  | 20:00 | 22:00 | 2 |  |  | Research | Reseach technical
| 2013-11-19 | 13:30 | 14:30 | 1 | 2.5 |  | Team Meetings |  |  |  | Time for doing week 9 | 0 | HOURS
|  | 21:00 | 22:30 | 1.5 |  |  | Team Home Work | -Do change management plan + Master Plan | AS_PM_MasterPlan AS_PM_ChangeManagementPlan
| 2013-11-20 | 13:30 | 17:00 | 3.5 | 3.5 |  | Team Work | - Do Change management plan - Review Change log template - Do Master plan |  |  | Time for doing week 10 | 0 | HOURS
| 2013-11-21 | 9:00 | 10:10 | 1.16 | 7.65 |  | Meetings with Faculty | - Present about Change management plan |  |  | Time for doing week 11 | 0 | HOURS
|  | 10:10 | 11:30 | 1.33 |  |  | Team Meetings
|  | 13:30 | 14:30 | 1 |  |  | Team Home Work | - Research about Stage 5 and role CS in ACDM
|  | 15:00 | 17:10 | 2.16 |  |  | Team Meetings | - Integrate the work of member about ACDM - Devide team work for team member
|  | 21:00 | 23:00 | 2 |  |  | Team Home Work | - Research tool for control Scrum and Sprint
| 2013-11-22 | 13:30 | 14:45 | 1.25 | 5.25 |  | Team Meetings | - Review Scrum model - Review Scrum role and responsibility - Review how to map ACDM into Scrum - Devide team work for team member |  |  | Time for doing week 12 | 0 | HOURS
|  | 15:30 | 16:30 | 1 |  |  | Team Work | - Update change menagement Plan - Update Change Request Form & Log
|  | 20:00 | 23:00 | 3 |  |  | Team Home Work | - Update change Form & Log - Research High level and low level design - Define defect process
4 | 2013-11-23 | 13:00 | 13:45 | 0.25 | 1.25 |  | Team Meetings | - Review process, document, template
|  | 13:45 | 14:45 | 1 |  |  | Team Work | - Update process document, description stage 5 in ACDM | - Stage5.docx
| 2013-11-25 | 10:30PM | 11:30PM | 1 | 1 |  | Team Home Work | - Update change Form & Log - Research High level and low level design - Define defect process - Update chang management plan |  |  | Time for doing week 13 | 0 | HOURS
| 2013-11-26 | 8.00AM | 9:00AM | 1 | 6.5 |  | Team Home Work | Teamsefl Review
|  | 9:00AM | 11:30PM | 2.5 |  |  | Meetings with Faculty | Review task works
|  | 1.30PM | 2:30PM | 1 |  |  | Team Meetings | Devide work task about Stage 1 elicite
|  | 2:45PM | 4:45PM | 2 |  |  | Team Home Work | brainstorm question for system
| 2013-11-27 | 1:30PM | 3:50PM | 2.33 | 3.33 |  | Team Meetings | brainstorm some question for future system |  |  | Time for doing week 14 | 0 | HOURS
|  | 10:30PM | 11:30PM | 1 |  |  | Team Home Work | brainstorm some question for future system |  |  | Time for doing week 15 | 0 | HOURS
| 2013-11-28 | 8:00AM | 9:15AM | 1.33 | 5.83 |  | Team Home Work | Review question have prepared for system
|  | 9:15AM | 11:00AM | 1.75 |  |  | Meetings with Customer | Collect architect drivers raw and develop user stories
|  | 1:30PM | 4:15PM | 2.75 |  |  | Team Meetings | Analyse architect drivers raw "Bảng tin" and "Danh mục" Draw activity diagrams business process |  |  | Time for doing week 16 | 0 | HOURS
| 2013-11-29 | 1:30PM | 17:00 | 3.5 | 3.5 |  | Team Meetings |  |  |  | Time for doing week 17 | 0 | HOURS
5 | 2013-12-03 | 9.00AM | 10.30AM | 1.5 | 6.5 |  | Meetings with Customer | Discuss entities and collection document + Rework entities + Implement analysis document <Archi Driver specification> |  |  | Time for doing week 19 | 0 | HOURS
|  | 10:30AM | 11:00AM | 0.5 |  |  | Team Meatings | - Discuss about document
|  | 1:30PM | 5:00PM | 3.5 |  |  | Training | First Training Java + Spring with Mr. Thanh + Setup nessecsary tools + Understand DI and AOP in Spring framework + Demo Hello world with Spring
|  | 10:00PM | 11:00PM | 1 |  |  | Team Home Work | Update entities, func,QA for team members
| 2013-12-04 | 1:30PM | 6:00PM | 4.5 | 4.5 |  | Team Mettings |  |  |  | Time for doing week 20 | 0 | HOURS
| 2013-12-05 | 8:00 | 9:10AM | 1.16 | 4.82 |  | Team Work | - Update timelog for team
| 2013-12-05 | 9:10AM | 10:40AM | 1.5 |  |  | Meetings with Faculty | - Review List risk, measurement plan - Review master plan, master design plan - Review project plan - Review sprint backlog template
| 2013-12-05 | 10:40AM | 11:30AM | 0.66 |  |  | Team Meetings | - Devide team work - Update entities
| 2013-12-05 | 16:30 | 6:00PM | 1.5 |  |  | Team Work | - Update timelog for team
6 | 2013-12-09 | 1:30PM | 6:-00PM | 4.5 | 5.5 |  | Team Meetings | - Collection and update driver specification document + Usecase diagram + Quality Attribute - Pioritize risk - Update requirement plan - schedule
| 2013-12-09 | 10:00PM | 11:00PM | 1 |  |  | Team Home Work | Update + Use case "Danh muc" |  |  | Time for doing week 23 | 0 | HOURS
| 2013-12-10 | 1:30 | 4:00PM | 2.5 | 2.5 |  | Training | Training spring core + MySQL + Insert/Update/Delete |  |  | Time for doing week 24 | 0 | HOURS
| 2013-12-12 | 11:00AM | 12:00PM | 1 | 4 |  | Team Meetings | Meeting about internal way of works
|  | 2:00PM | 5:00PM | 3 |  |  | Meetings with Customer | Review architecturals drivers specification |  |  | Time for doing week 26 | 0 | HOURS
| 2013-12-13 | 2:00PM | 5:00PM | 3 | 3 |  | Team Work | Update use case diagram "Danh muc" module Draw interface "Danh muc" module |  |  | Time for doing week 27 | 0 | HOURS
7 | 2013-12-16 | 2:00PM | 5:00PM | 3 | 3 | 5 | Team Work | Research Java with team |  |  | Time for doing week 28 | 0 | HOURS
| 2013-12-17 | 8:00AM | 10:00AM | 2 | 4 | 5 | Team Home Work |  |  |  | Time for doing week 29 | 0 | HOURS
|  | 1:30PM | 3:30PM | 2 |  |  | Training | Training validation with spring in Java |  |  | Time for doing week 30 | 0 | HOURS
| 2013-12-19 |  |  |  | 0 | 5
| 2013-12-20 |  |  |  | 0 | 5
8 | 2013-12-21 |  |  |  | 0 | 5
| 2013-12-22 |  |  |  | 0 | 5
| 2013-12-23 |  |  |  | 0 | 5
| 2013-12-24 |  |  |  | 0 | 5
| 2013-12-25 |  |  |  | 0 | 5
| 2013-12-26 |  |  |  | 0 | 5
| 2013-12-27 |  |  |  | 0 | 5
9 | 2013-12-28 |  |  |  | 0 | 5
| 2013-12-29 |  |  |  | 0 | 5
| 2013-12-30 |  |  |  | 0 | 5
| 2013-12-31 |  |  |  | 0 | 5
| 2014-01-01 |  |  |  | 0 | 5
| 2014-01-02 |  |  |  | 0 | 5
| 2014-01-03 |  |  |  | 0 | 5
10 | 2014-01-04 |  |  |  | 0 | 5
| 2014-01-05 |  |  |  | 0 | 5
| 2014-01-06 |  |  |  | 0 | 5
| 2014-01-07 |  |  |  | 0 | 3
| 2014-01-08 |  |  |  | 0 | 3
| 2014-01-09 |  |  |  | 0 | 5
| 2014-01-10 |  |  |  | 0 | 5
11 | 2014-01-11 |  |  |  | 0 | 8
| 2014-01-12 |  |  |  | 0 | 8
| 2014-01-13 |  |  |  | 0 | 8
| 2014-01-14 |  |  |  | 0 | 8
| 2014-01-15 |  |  |  | 0 | 8
| 2014-01-16 |  |  |  | 0 | 8
| 2014-01-17 |  |  |  | 0 | 8
12 | 2014-01-18 |  |  |  | 0 | 8
| 2014-01-19 |  |  |  | 0 | 8
| 2014-01-20 |  |  |  | 0 | 8
| 2014-01-21 |  |  |  | 0 | 8
| 2014-01-22 |  |  |  | 0 | 8
| 2014-01-23 |  |  |  | 0 | 8
| 2014-01-24 |  |  |  | 0 | 8
13 | 2014-01-25 |  |  |  | 0 |  | Nghỉ tết
| 2014-01-26 |  |  |  | 0 |  | Nghỉ tết
| 2014-01-27 |  |  |  | 0 |  | Nghỉ tết
| 2014-01-28 |  |  |  | 0 |  | Nghỉ tết
| 2014-01-29 |  |  |  | 0 |  | Nghỉ tết
| 2014-01-30 |  |  |  | 0 |  | Nghỉ tết
| 2014-01-31 |  |  |  | 0 |  | Nghỉ tết
14 | 2014-02-01 |  |  |  | 0 |  | Nghỉ tết
| 2014-02-02 |  |  |  | 0 |  | Nghỉ tết
| 2014-02-03 |  |  |  | 0 |  | Nghỉ tết
| 2014-02-04 |  |  |  | 0 |  | Nghỉ tết
| 2014-02-05 |  |  |  | 0 |  | Nghỉ tết
| 2014-02-06 |  |  |  | 0 |  | Nghỉ tết
| 2014-02-07 |  |  |  | 0 |  | Nghỉ tết
15 | 2014-02-08 |  |  |  | 0 | 8
| 2014-02-09 |  |  |  | 0 | 8
| 2014-02-10 |  |  |  | 0 | 8
| 2014-02-11 |  |  |  | 0 | 8
| 2014-02-12 |  |  |  | 0 | 8
| 2014-02-13 |  |  |  | 0 | 8
| 2014-02-14 |  |  |  | 0 | 8
16 | 2014-02-15 |  |  |  | 0 | 8
| 2014-02-16 |  |  |  | 0 | 8
| 2014-02-17 |  |  |  | 0 | 8
| 2014-02-18 |  |  |  | 0 | 8
| 2014-02-19 |  |  |  | 0 | 8
| 2014-02-20 |  |  |  | 0 | 8
| 2014-02-21 |  |  |  | 0 | 8
17 | 2014-02-22 |  |  |  | 0 | 8
| 2014-02-23 |  |  |  | 0 | 8
| 2014-02-24 |  |  |  | 0 | 8
| 2014-02-25 |  |  |  | 0 | 8
| 2014-02-26 |  |  |  | 0 | 8
| 2014-02-27 |  |  |  | 0 | 8
| 2014-02-28 |  |  |  | 0 | 8
18 | 2014-03-01 |  |  |  | 0 | 8
| 2014-03-02 |  |  |  | 0 | 8
| 2014-03-03 |  |  |  | 0 | 8
| 2014-03-04 |  |  |  | 0 | 8
| 2014-03-05 |  |  |  | 0 | 8
| 2014-03-06 |  |  |  | 0 | 8
| 2014-03-07 |  |  |  | 0 | 8
19 | 2014-03-08 |  |  |  | 0 | 8
| 2014-03-09 |  |  |  | 0 | 8
| 2014-03-10 |  |  |  | 0 | 8
| 2014-03-11 |  |  |  | 0 | 8
| 2014-03-12 |  |  |  | 0 | 8
| 2014-03-13 |  |  |  | 0 | 8
| 2014-03-14 |  |  |  | 0 | 8
20 | 2014-03-15 |  |  |  | 0 | 8
| 2014-03-16 |  |  |  | 0 | 8
| 2014-03-17 |  |  |  | 0 | 8
| 2014-03-18 |  |  |  | 0 | 8
| 2014-03-19 |  |  |  | 0 | 8
| 2014-03-20 |  |  |  | 0 | 8
| 2014-03-21 |  |  |  | 0 | 8
21 | 2014-03-22 |  |  |  | 0 | 8
| 2014-03-23 |  |  |  | 0 | 8
| 2014-03-24 |  |  |  | 0 | 8
| 2014-03-25 |  |  |  | 0 | 8
| 2014-03-26 |  |  |  | 0 | 8
| 2014-03-27 |  |  |  | 0 | 8
| 2014-03-28 |  |  |  | 0 | 8
22 | 2014-03-29 |  |  |  | 0 | 8
| 2014-03-30 |  |  |  | 0 | 8
| 2014-03-31 |  |  |  | 0 | 8
| 2014-04-01 |  |  |  | 0 | 8
| 2014-04-02 |  |  |  | 0 | 8
| 2014-04-03 |  |  |  | 0 | 8
| 2014-04-04 |  |  |  | 0 | 8
23 | 2014-04-05 |  |  |  | 0 | 8
| 2014-04-06 |  |  |  | 0 | 8
| 2014-04-07 |  |  |  | 0 | 8
| 2014-04-08 |  |  |  | 0 | 8
| 2014-04-09 |  |  |  | 0 | 8
| 2014-04-10 |  |  |  | 0 | 8
| 2014-04-11 |  |  |  | 0 | 8
24 | 2014-04-12 |  |  |  | 0 | 8
| 2014-04-13 |  |  |  | 0 | 8
| 2014-04-14 |  |  |  | 0 | 8
| 2014-04-15 |  |  |  | 0 | 8
| 2014-04-16 |  |  |  | 0 | 8
| 2014-04-17 |  |  |  | 0 | 8
| 2014-04-18 |  |  |  | 0 | 8
25 | 2014-04-19 |  |  |  | 0 | 8
| 2014-04-20 |  |  |  | 0 | 8
| 2014-04-21 |  |  |  | 0 | 8
| 2014-04-22 |  |  |  | 0 | 8
| 2014-04-23 |  |  |  | 0 | 8
| 2014-04-24 |  |  |  | 0 | 8
| 2014-04-25 |  |  |  | 0 | 8
26 | 2014-04-26 |  |  |  | 0 | 8
| 2014-04-27 |  |  |  | 0 | 8
| 2014-04-28 |  |  |  | 0 | 8
| 2014-04-29 |  |  |  | 0 | 8
| 2014-04-30 |  |  |  | 0 | 8
| 2014-05-01 |  |  |  | 0 | 8
| 2014-05-02 |  |  |  | 0 | 8
27 | 2014-05-03 |  |  |  | 0 | 8
| 2014-05-04 |  |  |  | 0 | 8
| 2014-05-05 |  |  |  | 0 | 8
| 2014-05-06 |  |  |  | 0 | 8
| 2014-05-07 |  |  |  | 0 | 8
| 2014-05-08 |  |  |  | 0 | 8
| 2014-05-09 |  |  |  | 0 | 8
28 | 2014-05-10 |  |  |  | 0 | 8
| 2014-05-11 |  |  |  | 0 | 8
| 2014-05-12 |  |  |  | 0 | 8
| 2014-05-13 |  |  |  | 0 | 8
| 2014-05-14 |  |  |  | 0 | 8
| 2014-05-15 |  |  |  | 0 | 8
| 2014-05-16 |  |  |  | 0 | 8
29 | 2014-05-17 |  |  |  | 0 | 8
| 2014-05-18 |  |  |  | 0 | 8
| 2014-05-19 |  |  |  | 0 | 8
| 2014-05-20 |  |  |  | 0 | 8
| 2014-05-21 |  |  |  | 0 | 8
| 2014-05-22 |  |  |  | 0 | 8
| 2014-05-23 |  |  |  | 0 | 8
30 | 2014-05-24 |  |  |  | 0 | 8
| 2014-05-25 |  |  |  | 0 | 8
| 2014-05-26 |  |  |  | 0 | 8
| 2014-05-27 |  |  |  | 0 | 8
| 2014-05-28 |  |  |  | 0 | 8
| 2014-05-29 |  |  |  | 0 | 8
| 2014-05-30 |  |  |  | 0 | 8