## Revision history
Document Reviewer Information
Reviewer Name | Review Attendance (R/S) | Comments
R/S: Required or Suggested participants or functions for the document review meeting
Document Approver Information
Approver Name | Approver Function | Comments
Document Revision History
Date | Revision | Status | Change Summary | Revised by | Version
|  | on going |  | Ngo Quang Huy | 1
|  | on going |  | Ngo Quang Huy | 2

## Master plan
ADMISSION SYSTEM PROJECT
ID | PHASE | TASK NAME | START | FINISH | ACTUAL FINISH | RESOURCES NAME | STATUS
1 | Project management | project organization and team structuring | 2013-07-11 | 2013-07-11 |  | Deadline team | DONE
2 |  | create project plan | 2013-07-11 | 25/11/2013 |  | Le Ngoc Chau
3 |  | create master plan | 2013-07-11 | 25/11/2013 |  | Ngo Quang Huy | DONE
4 |  | kick-off meeting of team | 2013-07-11 | 25/11/2013 |  | Deadline team | DONE
|  | kick-off meeting with mentor | 2013-08-11 | 2013-08-11 |  | Deadline team | DONE
5 |  | Create risk management plan | 2013-07-11 | 25/11/2013 |  | Ngo Quang Huy | DONE
6 |  | create change management plan | 2013-07-11 | 25/11/2013 |  | Khau Thanh dao | DONE
7 |  | create test management plan | 2013-07-11 | 25/11/2013 |  | Nguyen Phan Xuan huy | DONE
8 |  | create communication | 2013-07-11 | 25/11/2013 |  | Le Ngoc Chau | DONE
9 |  | create configuration document | 2013-07-11 | 25/11/2013 |  | Ta Ngoc Thien Phu | DONE
10 |  | create measurement plan | 2013-07-11 | 25/11/2013 |  | Huynh Trong Khang | DONE
11 |  | create team charter | 2013-07-11 | 25/11/2013 |  | Le Ngoc Chau | DONE
12 |  | create timelog | 2013-07-11 | 25/11/2013 |  | Le Ngoc Chau | DONE
13 | Requirement | develop requirement plan | 18/11/2013 | 27/11/2013 |  | Huynh Trong Khang
14 |  | prepare question list to gather requirement | 26/11/2013 | 27/11/2013 |  | Deadline team
15 |  | communicate with customer to gather requirement | 28/11/2013 | 28/11/2013 |  | Deadline team
16 |  | create operational requirement documents
17 |  | create product backlog
18 |  | create architect driver specification
19 |  | trainning spring core | 2013-03-12 |  |  | Deadline team
20 |  | identify vision and scope project
21 |  | identify functional requirement
22 |  | identify quality attribute
23 |  | develop usecase for "soan tin"
24 |  | develop usecase for "danh muc"
25 |  | develop usecase for "hoi dap"
26 |  | develop usecase for "hoi dap" for android
27 |  | develop GUI for " soan tin"
28 |  | develop GUI for "danh muc"
29 |  | develop GUI for "hoi dap"
30 |  | develop GUI for "hoi dap for android"
31 |  | baseline requirement | 30/12/2013 | 30/12/2013
32 | Architect & Design | Develop overal physical view for admission system (high level) | 31/12/2013
33 |  | Develop overal static view for admission system (high level)
34 |  | Develop overal dynamic view for admission system (high level)
35 |  | Evaluate architect and design for admission system
36 |  | review architect and design with Mr.Quang
37 |  | Create sprint backlog
38 |  | design database
system context
mapping physical with dynamic
mapping static with dynamic
39 | Sprint 1 (Sprint scrum) | detail design for sprint 1 | 20/01/2013
40 |  | create database
41 |  | implement componant of sprint 1
42 |  | implement unit test
43 |  | fix bug
44 |  | prepare story for sprint 2
45 |  | release sprint 1
46 | Sprint 2 | detail design for sprint 2
47 |  | create database
48 |  | implement componant of sprint 2
49 |  | implement unit test
50 |  | implement integration test between sprint 1 & 2
51 |  | fix bug
52 |  | prepare users tories for sprint 3
53 |  | release sprint 2
54 | Sprint 3 | detail design for sprint 3
55 |  | create database
56 |  | implement componant of sprint 3
57 |  | implement unit test
58 |  | implement integration test between sprint 1,2 &3
59 |  | fix bug
60 |  | prepare story for sprint 4
61 |  | release sprint 3
62 | Sprint 4 | detail design for sprint 3
63 |  | create database
64 |  | implement componant of sprint 3
65 |  | implement unit test
66 |  | implement integration test between sprint 1,2 &3
67 |  | fix bug
68 |  | prepare story for sprint 4
69 |  | release sprint 4