## Team member
Team member list
Project: Admission system - DeadlineTeam - Mentor: Mr. Bui Minh Phung
Project Risk Manager:
No | Name
1 | Le Ngoc Chau
2 | Khau Thanh Dao
3 | Ngo Quang Huy
4 | Nguyen Phan Xuan Huy
5 | Huynh Trong Khang
6 | Ta Ngoc Thien Phu

## Le Ngoc Chau
Risk priority list
Project: Admission system - DeadlineTeam - Mentor: Mr. Bui Minh Phung
Member: Le Ngoc Chau
RISK ID | LIST RISK | PROBABILITY | IMPACT | MITIGATE METHOD
1 | Time is not enough for project development | 50 | 90
2 | Communication between project team and stakeholder (mentor and customer) is not good | 50 | 75
3 | Estimation is not well | 68 | 85
4 | Many defects in product after release | 70 | 80
5 | Don't complete the full functionality required | 80 | 70
6 | Morale of the team was down | 80 | 90
7 | The goal of stakeholders are different | 25 | 95
8 | Not enough knowledge about programming | 60 | 89
9 | Difficult to communicate with customer | 5 | 55
10 | Team member's laptop is decayed | 10 | 69
11 | A lots defect in architecture phase | 20 | 40
12 | Progress of architecture phase is slow | 10 | 30
13 | Lack of meeting place | 85 | 20
14 | lack of experience to manage project | 80 | 99
15 | Lack of skills about test tool | 30 | 50
16 | Communicate about tester and developer | 30 | 40
17 | test case pass not enough | 50 | 50
18 | Team members have to focus on semester (I,II) | 20 | 20
19 | Occurring conflict between team members | 70 | 75
20 | Team members working not complete, working on time deadline | 60 | 70
21 | Team members have illness, need a few days to rest | 20 | 30
22 | Identify the scope unclear of project | 40 | 75
23 | Concentrate too much to elicit depth of detail requirement stage | 50 | 50
24 | Exceeded time for requirement phase | 60 | 50

## Khau Thanh Dao
Risk priority list
Project: Admission system - DeadlineTeam - Mentor: Mr. Bui Minh Phung
Member: Khau Thanh Dao
RISK ID | LIST RISK | PROBABILITY | IMPACT | MITIGATE METHOD
1 | Time is not enough for project development | 40 | 80
2 | Communication between project team and stakeholder (mentor and customer) is not good | 40 | 50
3 | Estimation is not well | 60 | 70
4 | Many defects in product after release | 40 | 80
5 | Don't complete the full functionality required | 30 | 80
6 | Morale of the team was down | 60 | 60
7 | The goal of stakeholders are different | 30 | 80
8 | Not enough knowledge about programming | 50 | 50
9 | Difficult to communicate with customer | 30 | 70
10 | Team member's laptop is decayed | 40 | 50
11 | A lots defect in architecture phase | 50 | 70
12 | Progress of architecture phase is slow | 80 | 80
13 | Lack of meeting place | 80 | 40
14 | lack of experience to manage project | 60 | 60
15 | Lack of skills about test tool | 50 | 50
16 | Communicate about tester and developer | 30 | 40
17 | test case pass not enough | 50 | 50
18 | Team members have to focus on semester (I,II) | 70 | 50
19 | Occurring conflict between team members | 60 | 70
20 | Team members working not complete, working on time deadline | 60 | 70
21 | Team members have illness, need a few days to rest | 60 | 50
22 | Identify the scope unclear of project | 60 | 70
23 | Concentrate too much to elicit depth of detail requirement stage | 50 | 50
24 | Exceeded time for requirement phase | 60 | 50

## Ngo Quang Huy
Risk priority list
Project: Admission system - DeadlineTeam - Mentor: Mr. Bui Minh Phung
Member: Ngo Quang Huy
RISK ID | LIST RISK | PROBABILITY | IMPACT | MITIGATE METHOD
1 | Time is not enough for project development | 40 | 80
2 | Communication between project team and stakeholder (mentor and customer) is not good | 40 | 50
3 | Estimation is not well | 60 | 70
4 | Many defects in product after release | 40 | 80
5 | Don't complete the full functionality required | 30 | 80
6 | Morale of the team was down | 60 | 60
7 | The goal of stakeholders are different | 30 | 80
8 | Not enough knowledge about programming | 50 | 50
9 | Difficult to communicate with customer | 30 | 70
10 | Team member's laptop is decayed | 40 | 50
11 | A lots defect in architecture phase | 50 | 70
12 | Progress of architecture phase is slow | 80 | 80
13 | Lack of meeting place | 80 | 40
14 | lack of experience to manage project | 60 | 60
15 | Lack of skills about test tool | 50 | 50
16 | Communicate about tester and developer | 30 | 40
17 | test case pass not enough | 50 | 50
18 | Team members have to focus on semester (I,II) | 70 | 50
19 | Occurring conflict between team members | 60 | 70
20 | Team members working not complete, working on time deadline | 60 | 70
21 | Team members have illness, need a few days to rest | 60 | 50
22 | Identify the scope unclear of project | 60 | 70
23 | Concentrate too much to elicit depth of detail requirement stage | 50 | 50
24 | Exceeded time for requirement phase | 60 | 50

## Nguyen Phan Xuan Huy
Risk priority list
Project: Admission system - DeadlineTeam - Mentor: Mr. Bui Minh Phung
Member: Nguyen Phan Xuan Huy
RISK ID | LIST RISK | PROBABILITY | IMPACT | MITIGATE METHOD
1 | Time is not enough for project development | 40 | 80
2 | Communication between project team and stakeholder (mentor and customer) is not good | 50 | 50
3 | Estimation is not well | 60 | 70
4 | Many defects in product after release | 30 | 60
5 | Don't complete the full functionality required | 50 | 50
6 | Morale of the team was down | 50 | 80
7 | The goal of stakeholders are different | 20 | 80
8 | Not enough knowledge about programming | 20 | 40
9 | Difficult to communicate with customer | 20 | 60
10 | Team member's laptop is decayed | 25 | 30
11 | A lots defect in architecture phase | 70 | 65
12 | Progress of architecture phase is slow | 80 | 70
13 | Lack of meeting place | 10 | 10
14 | lack of experience to manage project | 30 | 50
15 | Lack of skills about test tool | 30 | 30
16 | Communicate about tester and developer | 55 | 50
17 | test case pass not enough | 60 | 50
18 | Team members have to focus on semester (I,II) | 40 | 50
19 | Occurring conflict between team members | 20 | 30
20 | Team members working not complete, working on time deadline | 50 | 70
21 | Team members have illness, need a few days to rest | 10 | 30
22 | Identify the scope unclear of project | 10 | 80
23 | Concentrate too much to elicit depth of detail requirement stage | 30 | 40
24 | Exceeded time for requirement phase | 40 | 30

## Huynh Trong Khang
Risk priority list
Project: Admission system - DeadlineTeam - Mentor: Mr. Bui Minh Phung
Member: Huynh Trong Khang
RISK ID | LIST RISK | PROBABILITY | IMPACT | MITIGATE METHOD
1 | Time is not enough for project development | 50 | 80
2 | Communication between project team and stakeholder (mentor and customer) is not good | 30 | 60
3 | Estimation is not well | 50 | 60
4 | Many defects in product after release | 60 | 80
5 | Don't complete the full functionality required | 50 | 70
6 | Morale of the team was down | 60 | 70
7 | The goal of stakeholders are different | 30 | 70
8 | Not enough knowledge about programming | 50 | 70
9 | Difficult to communicate with customer | 30 | 70
10 | Team member's laptop is decayed | 70 | 70
11 | A lots defect in architecture phase | 60 | 80
12 | Progress of architecture phase is slow | 50 | 70
13 | Lack of meeting place | 80 | 60
14 | lack of experience to manage project | 30 | 70
15 | Lack of skills about test tool | 30 | 30
16 | Communicate about tester and developer | 30 | 30
17 | test case pass not enough | 60 | 50
18 | Team members have to focus on semester (I,II) | 90 | 70
19 | Occurring conflict between team members | 70 | 70
20 | Team members working not complete, working on time deadline | 80 | 70
21 | Team members have illness, need a few days to rest | 50 | 50
22 | Identify the scope unclear of project | 30 | 80
23 | Concentrate too much to elicit depth of detail requirement stage | 60 | 50
24 | Exceeded time for requirement phase | 40 | 40

## Ta Ngoc Thien Phu
Risk priority list
Project: Admission system - DeadlineTeam - Mentor: Mr. Bui Minh Phung
Member: Ta Ngoc Thien Phu
RISK ID | LIST RISK | PROBABILITY | IMPACT | MITIGATE METHOD
1 | Time is not enough for project development | 60 | 80 | Increase work hours Discuss with customer to decrease scope of project
2 | Communication between project team and stakeholder (mentor and customer) is not good | 40 | 60 | Improve communication plan
3 | Estimation is not well | 40 | 60 | Use other estimation method
4 | Many defects in product after release | 60 | 80
5 | Don't complete the full functionality required | 50 | 90 | Negotiate with customers about the functionality that is not complete
6 | Morale of the team was down | 50 | 70 | Motivate team member
7 | The goal of stakeholders are different | 40 | 90
8 | Not enough knowledge about programming | 50 | 60 | Trainning for all member every week
9 | Difficult to communicate with customer | 45 | 75 | Improve communication plan
10 | Team member's laptop is decayed | 30 | 60
11 | A lots defect in architecture phase | 80 | 70 | planning time that spent fix architecture
12 | Progress of architecture phase is slow | 85 | 70 | Increase work hours
13 | Lack of meeting place | 80 | 60
14 | lack of experience to manage project | 60 | 60 | Consultation of the teachers
15 | Lack of skills about test tool | 70 | 70
16 | Communicate about tester and developer | 40 | 50
17 | test case pass not enough | 80 | 60
18 | Team members have to focus on semester (I,II) | 90 | 60 | Planning work time between capstone and semester
19 | Occurring conflict between team members | 70 | 80 | Improve communication plan
20 | Team members working not complete, working on time deadline | 80 | 80 | Sanction base on the law of group
21 | Team members have illness, need a few days to rest | 70 | 60 | Transfer tasks to another member
22 | Identify the scope unclear of project | 65 | 80 | Working with customer to re-define scope of project
23 | Concentrate too much to elicit depth of detail requirement stage | 60 | 50
24 | Exceeded time for requirement phase | 70 | 60

## Risk management list
Risk management list
Project: Admission system - DeadlineTeam - Mentor: Mr. Bui Minh Phung
Project Risk Manager:
Step 1 : Risk Identification | [5 empty] | Step 2 : Risk analysis |  |  |  | Step 3 : Response Planing |  |  | Step 4 : Risk management
Risk ID | List of poissible risk | Trigger | Raised By | Date Raises | Risk Category | Probability | Impact | Priority Score | Mitigation methods | Risk strategy | Response plan | Owner | Status | Note
1 | Time is not enough for project development | The remaining time for project is not enough to implement remaining tasks in plan | Ngo Quang Huy | 2013-02-12 | Time | 0.5 | 0.81667 | 0.40833 | Increase work hours Discuss with customer to decrease scope of project | Mitigate | Report status and progress of project with mentor and customer with rational reasons. Focus on completing necessary documents Negotiate with customer about scope of product |  | Resolved
2 | Communication between project team and stakeholder (mentor and customer) is not good | Mentor doesn’t know current progress of project Customer misjudge team’s ability | Ngo Quang Huy | 2013-02-12 | Resource | 0.41667 | 0.59167 | 0.24653 | Improve communication plan |  | Announce to stakeholders instantly when team face with difficult |  | Planning complete
3 | Estimation is not well | We usually working over or behind schedule ( >10 task everyweek) | Ngo Quang Huy | 2013-02-12 | Estimating | 0.53 | 0.675 | 0.35775 | Apply estimate's process. Implement to re-estimate and update regular plan | Accept | Make the meeting for re-estimation Refer idea of experts |  | Planning complete
4 | Many defects in product after release | Defects > 10 | Ngo Quang Huy | 2013-02-12 | technology | 0.53333 | 0.76667 | 0.40889 | Tightly managed testing phase. Have reports about defects | Mitigate | .Make more effort for testing .Give module for customer using after each interation relase for collect feedback from customers continuous |  | Planning complete
5 | Don't complete the full functionality required | A few members not focus on the project | Ngo Quang Huy | 2013-02-12 | Performance | 0.51667 | 0.71667 | 0.37028 | Do the requirments phase carefully to avoid missing functionality due to missing requirements or do wrong | Mitigate | + Manage time reasonable to avoid delay progress, no time to complete the remaining fuctions + For the function that too hard too complete, Ess team can negotiate with customer to mitigate it or accept it and living with it (it depend on ESS Team's capacity) |  | Planning complete
6 | Morale of the team was down | Too difficult to do or manage time is unresonable | Ngo Quang Huy | 2013-02-12 | Resource | 0.58333 | 0.73333 | 0.42778 | spend time to relax | Avoid | Leader is responsible for track and understand the thought and aspirations of each member during Ecosystem project. -Organize regular meetings for team members raise their thoughts and their aspirations to recapitulate all problems that team member encoutered during project and from that, propose solutions reasonable to solve that problems - Plans to reduce work pressure for team members (team building) |  | Planning complete
7 | The goal of stakeholders are different | Not understand about the ability and ambitious of stakeholders | Ngo Quang Huy | 2013-02-12 | Scope/Requirement | 0.30833 | 0.80833 | 0.24924 | Define clear scope and initial goad with stakeholders. | Mitigate | Meet regularly with stakeholders to prevent the incorrect target. Present clearly perspective and direction of the project team with stakeholders. |  | Planning complete
8 | Not enough knowledge about programming | Not be able to programing in java and android | Ngo Quang Huy | 2013-02-12 | Skills | 0.46667 | 0.63167 | 0.29478 | Join in training class of Mr.Thanh | Accept | trainning per week about programming. |  | Planning complete
9 | Difficult to communicate with customer | Can't establish meeting with customer regularly becasuse customer is too busy | Ngo Quang Huy | 2013-02-12 | Comunication | 0.29167 | 0.66667 | 0.19444 | Establish the weekly meeting with customer |  | Utilize provided marterial to collect requirement and verify with customer. |  | Planning complete
10 | Team member's laptop is decayed | To announce from team member | Ngo Quang Huy | 2013-02-12 | Resource | 0.34167 | 0.58167 | 0.19874 |  | Accept | Borrow the school's laptop to continue the work or working in pair. |  | Planning complete
11 | A lots defect in architecture phase | Member lack of experience use to ACDM and design architecture | Ta Ngoc Thien Phu | 2013-04-12 | performance | 0.6 | 0.675 | 0.405 | planning time that spent fix architecture | Mitigate |  |  | Analysis complete
12 | Progress of architecture phase is slow | Not clearly understand to using ACDM, a lots defect is defined | Ta Ngoc Thien Phu | 2013-04-12 | performance | 0.65 | 0.65 | 0.4225 | Increase work hours | Accept |  |  | Analysis complete
13 | Lack of meeting place | no room to meeting | Ta Ngoc Thien Phu | 2013-04-12 | Resource | 0.69167 | 0.41667 | 0.28819 | go to another place | Accept |  |  | Resolved
14 | lack of experience to manage project | Member lack of experience use to manage project on time and meet expectation | Ta Ngoc Thien Phu | 2013-04-12 | Skills | 0.53333 | 0.68167 | 0.36356 | consultation of the teachers | Mitigate |  |  | Analysis complete
15 | Lack of skills about test tool | Member lack of experience use tool to test phase | Nguyen Phan Xuan Huy | 2013-04-12 | Technology | 0.46667 | 0.43333 | 0.20222 | increase time to learn and research test tool |  |  |  | Analysis complete
16 | Communicate about tester and developer | Can't understand between tester and developer | Nguyen Phan Xuan Huy | 2013-04-12 | Comunication | 0.375 | 0.4 | 0.15 | report progress daily | Avoid |  |  | Resolved
17 | test case pass not enough |  | Nguyen Phan Xuan Huy | 2013-04-12 | Controlling | 0.63333 | 0.51667 | 0.32722 | implement unit test on componant of function | Avoid |  |  | Analysis complete
18 | Team members have to focus on semester (I,II) | members of team no focus on capstone project because they must prepare for final subjects | Huynh Trong Khang | 2013-04-12 | Time | 0.66667 | 0.53333 | 0.35556 | planning work time between capstone and semester | Accept | reduce homework on capstone project. |  | Resolved
19 | Occurring conflict between team members | members can't understand together | Huynh Trong Khang | 2013-04-12 | Comunication | 0.6 | 0.65833 | 0.395 | Improve communication plan | Avoid |  |  | Resolved
20 | Team members working not complete, working on time deadline |  | Huynh Trong Khang | 2013-04-12 | Performance | 0.68333 | 0.71667 | 0.48972 | sanction base on the law of group | Mitigate |  |  | Analysis complete
21 | Lack of team members | Team members have illness, need a few days to rest… | Huynh Trong Khang | 2013-04-12 | Resource | 0.46667 | 0.45 | 0.21 | transfer tasks to another member | Accept |  |  | Analysis complete
22 | Identify the scope unclear of project |  | Huynh Trong Khang | 2013-04-12 | Scope/Requirement | 0.45 | 0.775 | 0.34875 | Working with customer to re-define scope of project | Avoid |  |  | Analysis complete
23 | Concentrate too much to elicit depth of detail requirement stage | focus too deep on high level requirement | Huynh Trong Khang | 2013-04-12 | Scope | 0.51667 | 0.48333 | 0.24972 | review with product owner weekly | Avoid |  |  | Resolved
Risk strategy | Avoid | Go away too far from that risk
| Mitigate | Use some method to control that risk
| Accept | Live with that risk
Transfer
Status | Identified | Define risk
| Analys complete | Risk was analys
| Planning complete | Planning for control risk
| Triggered | Describe risk
| Resolved | Risk was mitgate

## Recorded
Risk recorded
Project: Admission system - DeadlineTeam - Mentor: Mr. Bui Minh Phung
Project Risk Manager:
ID | Week | Risk | Plan/Methods
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
21 | 16 | Lack of team members | Transfer tasks to another member
8 | 17 | Not enough knowledge about programming | Increase trainning per week about programming.
3 | 17 | Estimation is not well | Refer idea of experts
18
14 | 19 | Lack of experience to manage project | Consultation of the teachers
20

## risk priority (probability) (hidden)
ID | Châu | Đạo | Q.Huy | X.Huy | Khang | Phú
1 | 50 | 40 | 60 | 40 | 50 | 60
2 | 50 | 40 | 40 | 50 | 30 | 40
3 | 68 | 60 | 40 | 60 | 50 | 40
4 | 70 | 40 | 60 | 30 | 60 | 60
5 | 80 | 30 | 50 | 50 | 50 | 50
6 | 80 | 60 | 50 | 50 | 60 | 50
7 | 25 | 30 | 40 | 20 | 30 | 40
8 | 60 | 50 | 50 | 20 | 50 | 50
9 | 5 | 30 | 45 | 20 | 30 | 45
10 | 10 | 40 | 30 | 25 | 70 | 30
11 | 20 | 50 | 80 | 70 | 60 | 80
12 | 10 | 80 | 85 | 80 | 50 | 85
13 | 85 | 80 | 80 | 10 | 80 | 80
14 | 80 | 60 | 60 | 30 | 30 | 60
15 | 30 | 50 | 70 | 30 | 30 | 70
16 | 30 | 30 | 40 | 55 | 30 | 40
17 | 50 | 50 | 80 | 60 | 60 | 80
18 | 20 | 70 | 90 | 40 | 90 | 90
19 | 70 | 60 | 70 | 20 | 70 | 70
20 | 60 | 60 | 80 | 50 | 80 | 80
21 | 20 | 60 | 70 | 10 | 50 | 70
22 | 40 | 60 | 65 | 10 | 30 | 65
23 | 50 | 50 | 60 | 30 | 60 | 60
24 | 60 | 60 | 70 | 40 | 40 | 70

## risk priority (impact) (hidden)
ID | Châu | Đạo | Q.Huy | X.Huy | Khang | Phú
1 | 90 | 80 | 80 | 80 | 80 | 80
2 | 75 | 50 | 60 | 50 | 60 | 60
3 | 85 | 70 | 60 | 70 | 60 | 60
4 | 80 | 80 | 80 | 60 | 80 | 80
5 | 70 | 80 | 70 | 50 | 70 | 90
6 | 90 | 60 | 70 | 80 | 70 | 70
7 | 95 | 80 | 70 | 80 | 70 | 90
8 | 89 | 50 | 70 | 40 | 70 | 60
9 | 55 | 70 | 70 | 60 | 70 | 75
10 | 69 | 50 | 70 | 30 | 70 | 60
11 | 40 | 70 | 80 | 65 | 80 | 70
12 | 30 | 80 | 70 | 70 | 70 | 70
13 | 20 | 40 | 60 | 10 | 60 | 60
14 | 99 | 60 | 70 | 50 | 70 | 60
15 | 50 | 50 | 30 | 30 | 30 | 70
16 | 40 | 40 | 30 | 50 | 30 | 50
17 | 50 | 50 | 50 | 50 | 50 | 60
18 | 20 | 50 | 70 | 50 | 70 | 60
19 | 75 | 70 | 70 | 30 | 70 | 80
20 | 70 | 70 | 70 | 70 | 70 | 80
21 | 30 | 50 | 50 | 30 | 50 | 60
22 | 75 | 70 | 80 | 80 | 80 | 80
23 | 50 | 50 | 50 | 40 | 50 | 50
24 | 50 | 50 | 40 | 30 | 40 | 60