## List main task
No | Activities
1 | Team Meetings
2 | Reading
3 | Self Prepare
4 | Team Home Work
5 | Team Work
6 | Meetings with Faculty
7 | Meetings with Customer
8 | Training
9 | Research
10 | Review with customer
11 | Review with technical support

## AS-PROJECT
Time Recording Log For: Capstone project | [5 empty] | Start Date: 08/11/2013 End Date:
Ta Ngoc Thien Phu - T101184
[8 empty] | Minimum: 5 hours/day 25 hours/week (5hours * 5 days) 700 hours/30 weeks (25 hours * 28 weeks) | Maximum: 24 hours/day 168 hours/week (24hours * 7 days) 4704 hours/30 weeks (168 hours * 28 weeks)
Week | Date | Start | Stop | Delta Time | Total time of day | Plan | Activity | Description | Artifact | Note
1 | 2013-11-08 | 1:00PM | 2:00PM | 1 | 1 | 1 | Kick off meeting |  |  |  | SUMMARY: TIME FOR DOING PROJECT | 392.66 | HOURS
2 | 2013-11-11 | 2:00PM | 3:30PM | 1.5 | 3 | 5 | Trainning | Quang Nguyen trainning ACDM |  |  | Time for doing week 1 | 1 | HOURS
| 2013-11-11 | 7:00PM | 8:30PM | 1.5 |  |  | Team Home Work | Define configuration management document and write meeting minutes of trainning ACDM |  |  | Time for doing week 2 | 12.3 | HOURS
| 2013-11-12 | 1:00PM | 3:00PM | 2 | 4 | 5 | Team meeting | _Discuss to team rule in team charter _Review project charter, communication plan, Configuration plan, Measurement plan, Weekly report and Timelog _Discuss to process model |  |  | Time for doing week 3 | 28.55 | HOURS
| 2013-11-12 | 9:00PM | 11:00PM | 2 |  |  | Team Home Work | _Review each stage in ACDM and role of ACDM _Update template configuration management document |  |  | Time for doing week 4 | 28.41 | HOURS
| 2013-11-13 | 1:30PM | 3:30PM | 2 | 2 | 5 | Team meeting | _Khang and Dao introduce about java spring core that they researched _Dao introduce about Maven and Hibernet _Khang introduce about Java 6 and Spring 3 |  |  | Time for doing week 5 | 21.16 | HOURS
| 2013-11-14 | 8:00AM | 9:00AM | 1 | 2.25 | 5 | Team work | Review development process of team |  |  | Time for doing week 6 | 23.91 | HOURS
|  | 9:00AM | 10:15AM | 1.25 |  |  | Meetings with Faculty | Present work that team completed in this week |  |  | Time for doing week 7 | 27.33 | HOURS
| 2013-11-15 | 1:00PM | 2:05PM | 1.05 | 1.05 | 2 | Team meeting | Present about Scrum model, Risk management, Huy presnet spring framework |  |  | Time for doing week 8 | 26.25 | HOURS
3 | 2013-11-16 | 9:30PM | 10:30PM | 1 | 1 | 1 | Team Home Work | Research Srum model |  |  | Time for doing week 9 | 20 | HOURS
| 2013-11-17 | 7:30PM | 10:30PM | 3 | 3 | 2 | Team Home Work | Research Srum model (cont) Integrate ACDM to Scrum |  |  | Time for doing week 10 | 29.5 | HOURS
| 2013-11-18 | 9:00PM | 10:00PM | 1 | 1 | 2 | Team Home Work | Review Srcum that integrated ACDM |  |  | Time for doing week 11 | 35.25 | HOURS
| 2013-11-19 | 1:30PM | 2:30PM | 1 | 4.65 | 6 | Team meeting | 1/Present: -Change management document -Process of team -Test management document 2/Review time log |  |  | Time for doing week 12 | 19.5 | HOURS
|  | 4:30PM | 6:00PM | 1.5 |  |  | Team Home Work | Define architecture plan document Write meeting minutes | AS_AD_Architecture Plan.doxc |  | Time for doing week 13 | 0 | HOURS
|  | 9:00PM | 1:15PM | 2.15 |  |  | Team Home Work | Define team process document (use Scrum Model combine ACDM) | AS_PM_Deadline Team Process.doxc |  | Time for doing week 14 | 0 | HOURS
| 2013-11-20 | 1:30PM | 5:30PM | 4 | 4 | 5 | Team Home Work | Phu, Khang, Dao, Chau discuss about Scrum model combine ACDM Update architeture plan document and deadline team process document | AS_AD_Architecture Plan.doxc AS_PM_Deadline Team Process.doxc |  | Time for doing week 15 | 14.5 | HOURS
| 2013-11-21 | 8:00AM | 9:00AM | 1 | 9.65 | 10 | Team work | Prepare architecture plan and deadline team process to report with mentor | AS_AD_Architecture Plan.doxc AS_PM_Deadline Team Process.doxc |  | Time for doing week 16 | 24 | HOURS
|  | 9:00AM | 10:10AM | 1.16 |  |  | Meetings with Faculty | Report: -Change plan document -Requirement plan document -Architecture plan document -Master plan -Issue that team are meeting -Plan for next week |  |  | Time for doing week 17 | 27.5 | HOURS
|  | 10:10AM | 11:30AM | 1.33 |  |  | Team meeting | Divide ACDM task for each member |  |  | Time for doing week 18 | 39.5 | HOURS
|  | 1:30PM | 3:00PM | 1.5 |  |  | Team Home Work | Research chief architect role of ACDM and Stage 3 of ACDM |  |  | Time for doing week 19 | 14 | HOURS
|  | 3:00PM | 5:10PM | 2.16 |  |  | Team meeting | Report to research result |  |  | Time for doing week 20 | 0 | HOURS
|  | 9:00PM | 11:30PM | 2.5 |  |  | Team Home Work | Mapping ACDM to Scrum Model Mapping role of ACDM to role of Scrum Update Deadline Team process | AS_PM_Deadline Team Process.doxc |  | Time for doing week 21 | 0 | HOURS
| 2013-11-22 | 1:30PM | 2:45PM | 1.25 | 5.25 | 2 | Team meeting | Report research result about Scrum Divide task about Scrum continuous | AS_PM_Deadline Team Process.doxc |  | Time for doing week 22 | 0 | HOURS
|  | 3:00PM | 4:30PM | 1.5 |  |  | Team Home Work | Drawing Scrum model that have use ACDM Description for Scrum model | AS_PM_Deadline Team Process.doxc |  | Time for doing week 23 | 0 | HOURS
|  | 8:30PM | 11:00PM | 2.5 |  |  | Team Home Work | Update Deadline team process document Update Architect Plan | AS_AD_Architecture Plan.doxc AS_PM_Deadline Team Process.doxc |  | Time for doing week 24 | 0 | HOURS
4 | 2013-11-23 | 1:10PM | 34:48 | 0.25 | 1.25 | 0 | Team meeting | Discuss about Scrum model that is draw by IDEF0 Divide task about Scrum continuous |  |  | Time for doing week 25 | 0 | HOURS
|  | 10:30PM | 11:30PM | 1 |  |  | Team Home Work | Define table that show description of phase 3 ACDM, inculde Name Steps, image of Process, description Write Meeting Minutes | AS_AD_Architecture Plan.doxc |  | Time for doing week 26 | 0 | HOURS
| 2013-11-24 | 8:00AM | 12:00PM | 4 | 4 | 0 | Trainning | Trainning Java at Nhat Nghe Center |  |  | Time for doing week 27 | 0 | HOURS
| 2013-11-25 | 2:00PM | 4:00PM | 2 | 2 | 3 | Team Home Work | Update Architecture Plan |  |  | Time for doing week 28 | 0 | HOURS
| 2013-11-26 | 9:00AM | 11:30PM | 2.5 | 5 | 5 | Meetings with Faculty | Report content that team will do it on the week before |  |  | Time for doing week 29 | 0 | HOURS
|  | 1:30PM | 2:30PM | 1 |  |  | Team meeting | Overview RE phase, divide module for each member to reaserch and give question for this module that members is assigned |  |  | Time for doing week 30 | 0 | HOURS
|  | 9:30PM | 11:90PM | 1.5 |  |  | Team Home Work | Brainstroming and give question that related to module Question & Anwser
| 2013-11-27 | 12:30PM | 1:30PM | 1 | 3.33 | 5 | Team Home Work | Write meeting minustes
|  | 1:30PM | 3:50PM | 2.33 |  |  | Team meeting | Discuss about question that is used to ask customer in each module Discuss Scrum model with Mrs.Hong
| 2013-11-28 | 8:00AM | 9:15AM | 1.33 | 8.33 | 7 | Team Home Work | Review question have prepared for system
|  | 9:15AM | 11:00AM | 1.75 |  |  | Meetings with Customer | Collect raw architect drivers and develop user stories
|  | 1:30PM | 4:15PM | 2.75 |  |  | Team Meetings | Analyse architect drivers
|  | 9:00PM | 11:30PM | 2.5 |  |  | Team Home Work | Write meeting minustes Draw Activity digram of Functional Tim Kiem and Chuyen Tin
| 2013-11-29 | 1:30PM | 5:00PM | 3.5 | 4.5 | 5 | Team meeting | Discuss and draw activity diagram of module Ban Tin, Hoi-Dap Design interface of system Divide task Update time log
|  | 10:30PM | 11:30PM | 1 |  |  | Team Home Work | Write meeting minustes Update time log
5 | 2013-12-01 | 12:30PM | 4:00PM | 3.5 | 5 | 0 | Team Home Work | Write Functional, Quality Attribute and Entity of Module Soan Tin
|  | 7:00PM | 8:30PM | 1.5 |  |  | Team Home Work | Update Functional, Quality Attribute and Entity of Module Soan Tin Update timlog
| 2013-12-03 | 9:00AM | 10:30AM | 1.5 | 9.5 | 10 | Meetings with Customer | Discuss entities and collection document + Rework entities + Implement analysis document <Archi Driver specification>
|  | 10:30AM | 11:00AM | 0.5 |  |  | Team Meetings | Discuss about document
|  | 1:30PM | 5:00PM | 3.5 |  |  | Trainning | First Training Java + Spring with Mr. Thanh + Setup nessecsary tools + Understand DI and AOP in Spring framework + Demo Hello world with Spring
|  | 6:30PM | 10:30PM | 4 |  |  | Team Home Work | Update Entities Write Use case Update architecture plan document Update timelog
| 2013-12-04 | 1:30PM | 6:00PM | 4.5 | 4.5 | 5 | Team Meeting | Review documents: -Master plan -Risk management -Measuremet management -Process -Entities Update timelog
| 2013-12-05 | 9:10AM | 10:40AM | 1.5 | 2.16 | 5 | Meetings with Faculty | - Review List risk, measurement plan - Review master plan, master design plan - Review project plan - Review sprint backlog template
| 2013-12-05 | 10:40AM | 11:30AM | 0.66 |  |  | Team Meetings | - Devide team work - Update entities
6 | 2013-12-07 | 10:30PM | 12:00PM | 1.5 | 1.5 | 5 | Team Home Work | Write meeting minutes 4/12/2013 and 5/12/2013 | Meeting_Minutes_041213.doc Meeting_Minutes_051213.doc
| 2013-12-08 | 2:30PM | 3:30PM | 1 | 4.5 | 0 | Team Home Work | Priority and solution for risk list
|  | 7:30PM | 11:00PM | 3.5 |  |  | Team Home Work | Fix and update use case, quality attribute Create Architecture Schedule Create template Detail Design Document Draw use case diagram | AS_PM_Architecture Plan.docx AS_AD_Detail Design.docx
| 2013-12-09 | 1:30PM | 6:-00PM | 4.5 | 4.5 | 5 | Team Work | Draw Usecase diagram Update Use case description Update Quality Attribute | AS_RE_ArchitectureDriverSpecification-VN-version.docx
| 2013-12-10 | 9:00AM | 11:30AM | 2.5 | 5 | 5 | Trainning | Tranning HTML + CSS
|  | 1:30PM | 4:00AM | 2.5 |  |  | Trainning | Training spring core + MySQL + Insert/Update/Delete
| 2013-12-12 | 9:00AM | 11:00AM | 2 | 5.41 | 5 | Meetings with Faculty | - Review project plan, Risk list, plan for next week
| 2013-12-12 | 11:00AM | 11:45AM | 0.75 |  |  | Team Meetings | - Discuss about team work
| 2013-12-12 | 2:00PM | 4:40PM | 2.66 |  |  | Meetings with Customer
| 2013-12-13 | 2:00PM | 5:00PM | 3 | 3 | 5 | Team Work | Update use case diagram SoanTin module Draw interface of SoanTin module
7 | 2013-12-14 | 1:30PM | 5:00PM | 3.5 | 3.5 | 5 | Trainning | Trainning Java: Connect database and login
| 2013-12-15 | 2:00PM | 3:00PM | 1 | 2.5 | 0 | Team Home Work | Update QA + Entity of SoanTin module
| 2013-12-15 | 7:30PM | 9:00PM | 1.5 |  |  | Team Home Work | Update use case diagram + use case description of SoanTin module update timelog
| 2013-12-16 | 2:00PM | 5:00PM | 3 | 3 | 5 | Team Work | Research Java with team
| 2013-12-17 | 1:30PM | 3:30PM | 2 | 2 | 5.5 | Training | Training validation with spring in Java
| 2013-12-18 | 1:30PM | 4:00PM | 2.5 | 5.5 | 5 | Team Meetings | Review documents for mentor meetings at 19/12
| 2013-12-18 | 7:00PM | 10::00 PM | 3 |  |  | Team Home Work | Update Entity, Use case diagram Soan Tin | AS_RE_ArchitectureDriverSpecification-VN-version-0.6
| 2013-12-19 | 8:00AM | 9:00AM | 1 | 7.83 | 5 | Team Work | - Review usecase, entities | - AS_RE_ArchitectureDriverSpecification-VN-version.docx
|  | 9:10AM | 10:30AM | 1.33 |  |  | Meetings with Faculty | - Review project plan - Reivew requirement plan
|  | 10:30AM | 12:00AM | 1.5 |  |  | Team Meetings | - Devide work for next week - Review use case, entities | - AS_RE_ArchitectureDriverSpecification-VN-version.docx
|  | 2:00PM | 4:30PM | 2.5 |  |  | Meetings with Customer | - Review Entity
|  | 9:30PM | 11:00PM | 1.5 |  |  | Team Home Work | Write meeting minutes 19/12/2013 Update timelog
| 2013-12-20 | 9:00PM | 12:00PM | 3 | 3 | 4.5 | Team Home Work | Edit entity + use case Soan Tin
8 | 2013-12-23 | 9:00AM | 11:30AM | 2.5 | 4 | 5 | Training | Java: configuation and validator a form
|  | 9:30PM | 11:00PM | 1.5 |  |  | Team Home Work | Edit entity hoi dap follow Customer comments
| 2013-12-24 | 8:00AM | 9:00AM | 1 | 7.5 | 5.5 | Team Work | Prepare document for meeting with customer
|  | 9:00AM | 11:00AM | 2 |  |  | Meetings with Customer | Review Entity + Use Case + Quality Attribute
|  | 1:30PM | 3:30PM | 2 |  |  | Trainning | Review Ex02 of last week
|  | 9:00PM | 11:30PM | 2.5 |  |  | Team Home Work | Edit Quality Attribute Update time log
| 2013-12-25 | 10:30PM | 11:00PM | 0.5 | 4 | 5 | Team Home Work | Update timelog
|  | 1:30PM | 5:00PM | 3.5 |  |  | Team Work | Update Team evaluate Update Individual evaluate Update Team Timelog
| 2013-12-26 | 9:15AM | 10:00AM | 0.75 | 4.75 | 5 | Meetings with Faculty
|  | 2:00PM | 5:00PM | 3 |  |  | Team Home Work | Research Static View
|  | 10:00PM | 11:00PM | 1 |  |  | Team Home Work | Update timelog, write meetings minutes
| 2013-12-27 | 2:00PM | 5:00PM | 3 | 6 | 4.5 | Team Home Work | Research Static View
|  | 7:00PM | 10:00PM | 3 |  |  | Team Home Work
9 | 2013-12-28 | 2:00PM | 4:30PM | 2.5 | 5 | 5 | Team Home Work | Research Physical View
|  | 9:30PM | 12:00PM | 2.5 |  |  | Team Home Work
| 2013-12-29 | 1:30PM | 6:00PM | 4.5 | 6.5 | 5 | Team Home Work | Research Dynamic View
|  | 9:00PM | 11:00PM | 2 |  |  | Team Home Work | Review Static View + Physical View
| 2013-12-30 | 1:30PM | 3:00PM | 1.5 | 1.5 | 1 | Team Meetings | Review Static View + Physical View + Dynamic View Divide task for each members
| 2013-12-31 | 9:00PM | 11:45PM | 2.75 | 4.25 | 5.5 | Meetings with Customer | Review Use Case + QA
|  | 1:30PM | 3:00PM | 1.5 |  |  | Trainning | Trainning Lucene update timelog
| 2014-01-02 | 9:15AM | 10:00PM | 0.75 | 2.75 | 5 | Meetings with Faculty
| 2014-01-02 | 9:30PM | 11:30PM | 2 |  |  | Team Home Work | Design Decompose Style
| 2014-01-03 |  |  |  |  | 5
10 | 2014-01-04 |  |  |  |  | 5
| 2014-01-05 | 8:00PM | 11:00PM | 3 | 3 |  | Team Home Work | Update Decompose Style Review Physical Review Static - Layer Style
| 2014-01-06 | 8:00AM | 9:30AM | 1.5 | 7 |  | Team Work | Review Physical View, Dynamic View and Static View
|  | 2:00PM | 5:00PM | 3 |  |  | Team Home Work | Update Decompose Style, combine Decompose Style and Layer Style
|  | 8:00PM | 10:30PM | 2.5 |  |  | Team Home Work | Update Decompose Style, combine Decompose Style and Layer Style
| 2014-01-07 | 9:00AM | 11:30AM | 2.5 | 5.5 | 5 | Team Meetings | Review work assignment of each member: physical, layer style, datamodel, system context
|  | 1:30PM | 3:00PM | 1.5 |  |  | Team Meetings
|  | 10:30PM | 11:59PM | 1.5 |  |  | Team Home Work | Update Decompose Style Update timelog
| 2014-01-08 | 8:30AM | 12:00PM | 3.5 | 5 | 5 | Team Meetings | Review work assignment of each member: physical, layer style, datamodel, system context
|  | 9:30PM | 11:00PM | 1.5 |  |  | Team Home Work | Update Dynamic View Update timelog
| 2014-01-09 | 8:00AM | 9:00AM | 1 | 6.5 | 5 | Team Work | Review some document to review with mentor
|  | 9:00AM | 11:00AM | 2 |  |  | Meetings with Faculty | Report week 10 and present some views in architect
|  | 2:00PM | 4:00PM | 2 |  |  | Meetings with Customer | Review and update three view in high level
|  | 9:30PM | 11:00PM | 1.5 |  |  | Team Home Work | Update C&C View - công cụ soạn tin
| 2014-01-10 | 9:30PM | 12:00AM | 2.5 | 2.5 | 5 | Team Home Work | Update Architecture Document
11 | 2014-01-11
| 2014-01-12 | 8:00PM | 11:00PM | 3 | 3 |  | Team Home Work | Edit architect document
| 2014-01-13 | 8:00AM | 10:00AM | 2 | 7.5 | 5 | Team Home Work | Research C&C view and Static View im Document of Mr.Quang
|  | 1:30PM | 4:00PM | 2.5 |  |  | Team Work | Discuss about architect document
|  | 8:00PM | 11:00PM | 3 |  |  | Team Home Work | Research C&C view and Static View im Document of Mr.Quang
| 2014-01-14 | 8:30AM | 11:30AM | 3 | 9 | 7 | Team Meetings | Research android: widget, activity and input/output stream
|  | 1:30PM | 4:30PM | 3 |  |  | Team Meetings | Review and update c&c view
|  | 8:00PM | 11:00PM | 3 |  |  | Team Home Work | Update archutect document
| 2014-01-15 | 9:00AM | 10:00AM | 1 | 3.75 | 7 | Meetings with Customer | Discuss about C&C View
|  | 10:00AM | 12:00AM | 2 |  |  | Team Meetings | Rework, draw C&C view
|  | 5:00PM | 5:45PM | 0.75 |  |  | Team Home Work | Update timelog and evaluation team
| 2014-01-16 | 8:00AM | 9:00AM | 1 | 6 | 6 | Team Work | Prepare document
|  | 9:00AM | 11:00AM | 2 |  |  | Meetings with Faculty | Report pre-week and present architectural elements
|  | 7:30PM | 10:30AM | 3 |  |  | Team Home Work | Design C&C View
| 2014-01-17 | 2:00PM | 5:00AM | 3 | 6 | 5 | Team Home Work | Edit architecture design
|  | 7:30PM | 10:30AM | 3 |  |  | Team Home Work | Design Interface
12 | 2014-01-18 | 8:30AM | 10:30AM | 2 | 6.5 | 5 | Team Home Work | Edit arhitecture design and Interface
|  | 2:30PM | 4:30PM | 2 |  |  | Team Home Work | Edit Static View
|  | 7:30PM | 10:00PM | 2.5 |  |  | Team Home Work | Edit Interface
2014-01-19
| 2014-01-20 | 7:30PM | 11:00PM | 3.5 | 3.5 | 5 | Team Home Work | Edit arhitecture design and Interface
| 2014-01-21 | 9:00 | 12:00 | 3 | 5.5 | 7 | Meeting with Customer | - Review Architect design
|  | 12:00 | 12:30 | 0.5 |  |  | Team Meetings | - Divide team works
|  | 21:00 | 23:00 | 2 |  |  | Team Home Work | Update C&C View + Static View and Interface
| 2014-01-22 | 19:00 | 23:00 | 4 | 4 | 7 | Team Home Work | Edit arhitecture design and Interface Update timelog
| 2014-01-23 |  |  |  |  | 6
| 2014-01-24 |  |  |  |  | 5
13 | 2014-01-25 |  |  |  |  | 5
| 2014-01-27 | [5 empty] | Nghỉ tết
| 2014-01-28 | [5 empty] | Nghỉ tết
| 2014-01-29 | [5 empty] | Nghỉ tết
| 2014-01-30 | [5 empty] | Nghỉ tết
| 2014-01-31 | [5 empty] | Nghỉ tết
14 | 2014-02-01 | [5 empty] | Nghỉ tết
2014-02-02
2014-02-03
| 2014-02-04 | [5 empty] | Nghỉ tết
| 2014-02-05 | [5 empty] | Nghỉ tết
| 2014-02-06 | [5 empty] | Nghỉ tết
| 2014-02-07 | [5 empty] | Nghỉ tết
15 | 2014-02-08 |  |  |  |  | 5
2014-02-09
2014-02-10
| 2014-02-11 | 14:00 | 16:00 | 2 | 6 | 7 | Meeting with Customer | - Review architect design
|  | 16:00 | 5:00PM | 1 |  |  | Team Meeting | Dicuss architectural issues and assign task works for members
|  | 19:00 | 10:00PM | 3 |  |  | Team Home Work | Edit C&C view, static view
| 2014-02-12 | 19:00 | 10:30PM | 3.5 | 3.5 | 7 | Team Home Work | Update timelog re-design C&C view, static view
| 2014-02-13 | 21:00 | 10:30PM | 1.5 | 1.5 | 6 | Team Home Work | Update architecture design
| 2014-02-14 | 20:30 | 12:00PM | 3.5 | 3.5 | 5 | Team Home Work | Update architecture design
16 | 2014-02-15 |  |  |  |  | 5
| 2014-02-16 |  |  |  |  | 5
| 2014-02-17 | 19:00 | 23:00 | 4 | 4 |  | Team Home Work | Update architecture design
| 2014-02-18 | 14:00 | 16:00 | 2 | 2 |  | Meetings with Customer | review architecture design and interface design
| 2014-02-19 | 8:00 | 11:00 | 3 | 6 | 6 | Team Meetings | review C&C view, static view, interface design
|  | 11:30 | 12:30 | 1 |  |  | Team Work | Update timelog and evaluation team
|  | 13:30 | 15:30 | 2 |  |  | Team Home Work | Update architecture design and write interface
| 2014-02-20 | 9:30AM | 10:30AM | 1 | 6 | 7 | Meetings with Faculty | Report week 15
|  | 2:00PM | 4:00PM | 2 |  |  | Meetings with Customer | Review architecture design document
|  | 7:00PM | 10:30PM | 3 |  |  | Team Home Work | Update architecture design
| 2014-02-21 | 9:00AM | 12:00PM | 3 | 6 | 8 | Team Work | Design Interface
|  | 1:00PM | 4:00PM | 3 |  |  | Team Work | Design Interface
17 | 2014-02-22 | 7:00PM | 11:00PM | 4 | 4 | 5 | Team Home Work | Research css and convert psd to html Dap web application and login page
2014-02-23
| 2014-02-24 | 8:00AM | 12:00PM | 4 | 4 |  | Team Work | Design User Interface page 1
| 2014-02-25 | 8:00AM | 12:00PM | 4 | 7 | 8 | Team Work | Design User Interface page 2
|  | 1:00PM | 4:00PM | 3 |  |  | Team Work | Design User Interface page 2
| 2014-02-26 | 8:30AM | 12:00PM | 3.5 | 3.5 | 6 | Team Work | Update timelog, research ajax design User Interface
| 2014-02-27 | 8:00AM | 9:00AM | 1 | 6 | 7 | Team Work | prepare for Meetings with Faculty
|  | 9:00AM | 10:00AM | 1 |  |  | Meetings with Faculty | Report week 17
|  | 10:00AM | 12:00PM | 2 |  |  | Team Meetings | Review and assign task works for team members
|  | 9:00PM | 11:00PM | 2 |  |  | Team Home Work | detail design: description each interface
| 2014-02-28 | 7:00PM | 10:00PM | 3 | 3 | 7 | Team Home Work | detail design: update
18 | 2014-03-01 |  |  |  |  | 5
2014-03-02
| 2014-03-03 | 8:30AM | 11:30AM | 3 | 7 | 8 | Research | create daatabase
|  | 9:00PM | 1:00AM | 4 |  |  | Team Home Work | coding load QuestionList
| 2014-03-04 | 8:00AM | 12:00PM | 4 | 7 | 8 | Team Work | coding load QuestionList
|  | 1:00PM | 4:00PM | 3 |  |  | Team Meetings | coding load QuestionList
| 2014-03-05 | 8:00AM | 12:00PM | 4 | 10 | 8 | Team Work | coding load QuestionList
|  | 1:00PM | 4:00PM | 3 |  |  | Team Work | coding load QuestionList update timelog
|  | 7:00PM | 10:00PM | 3 |  |  | Team Home Work | coding load QuestionList
| 2014-03-06 | 8:00AM | 9:00AM | 1 | 6.5 | 7 | Team Meetings | daily meeting - report progress of members and review individuals task works to prepare present mentor
|  | 9:00AM | 10:30AM | 1.5 |  |  | Meetings with Faculty | Report week 17
|  | 10:30AM | 12:00PM | 0.5 |  |  | Team Meetings | Review sub-tasks and assign task works
|  | 1:00PM | 2:00PM | 1 |  |  | Team Meetings | Review question to ask customer
|  | 2:00PM | 4:00PM | 2 |  |  | Meetings with Customer | Show user interface and get business rules
|  | 4:00PM | 4:30PM | 0.5 |  |  | Team Meetings | Assign task works for memebers
| 2014-03-07 | 8:00AM | 12:00PM | 4 | 9 | 7 | Team Work | Coding "Load question list to form"
|  | 1:00PM | 6:00PM | 5 |  |  | Team Work | Coding "Load question list to form"
19 | 2014-03-08 | 8:00AM | 12:00PM | 4 | 4 | 5 | Team Work | Coding "Load question list to form"
| 2014-03-09 | 8:00PM | 11:00PM | 3 | 3 |  | Team Home Work | research coding "search data"
| 2014-03-10 | 8:00AM | 12:00PM | 4 | 7 |  | Team Work | Coding "search data"
|  | 1:00PM | 4:00PM | 3 |  |  | Team Work | Coding "search data"
| 2014-03-11 |  |  |  |  | 8
| 2014-03-12 |  |  |  |  | 6
| 2014-03-13 |  |  |  |  | 7
| 2014-03-14 |  |  |  |  | 7
20 | 2014-03-15 |  |  |  |  | 5
2014-03-16
2014-03-17
| 2014-03-18 |  |  |  |  | 8
| 2014-03-19 |  |  |  |  | 6
| 2014-03-20 |  |  |  |  | 7
| 2014-03-21 |  |  |  |  | 7
21 | 2014-03-22 |  |  |  |  | 5
2014-03-23
2014-03-24
| 2014-03-25 |  |  |  |  | 8
| 2014-03-26 |  |  |  |  | 6
| 2014-03-27 |  |  |  |  | 7
| 2014-03-28 |  |  |  |  | 7
22 | 2014-03-29 |  |  |  |  | 5
2014-03-30
2014-03-31
| 2014-04-01 |  |  |  |  | 8
| 2014-04-02 |  |  |  |  | 6
| 2014-04-03 |  |  |  |  | 7
| 2014-04-04 |  |  |  |  | 7
23 | 2014-04-05 |  |  |  |  | 5
2014-04-06
2014-04-07
| 2014-04-08 |  |  |  |  | 8
| 2014-04-09 |  |  |  |  | 6
| 2014-04-10 |  |  |  |  | 7
| 2014-04-11 |  |  |  |  | 7
24 | 2014-04-12 |  |  |  |  | 5
2014-04-13
2014-04-14
| 2014-04-15 |  |  |  |  | 8
| 2014-04-16 |  |  |  |  | 6
| 2014-04-17 |  |  |  |  | 7
| 2014-04-18 |  |  |  |  | 7
25 | 2014-04-19 |  |  |  |  | 5
2014-04-20
2014-04-21
| 2014-04-22 |  |  |  |  | 8
| 2014-04-23 |  |  |  |  | 6
| 2014-04-24 |  |  |  |  | 7
| 2014-04-25 |  |  |  |  | 7
26 | 2014-04-26 |  |  |  |  | 5
2014-04-27
2014-04-28
| 2014-04-29 |  |  |  |  | 8
| 2014-04-30 |  |  |  |  | 6
| 2014-05-01 |  |  |  |  | 7
| 2014-05-02 |  |  |  |  | 7
27 | 2014-05-03 |  |  |  |  | 5
2014-05-04
2014-05-05
| 2014-05-06 |  |  |  |  | 8
| 2014-05-07 |  |  |  |  | 6
| 2014-05-08 |  |  |  |  | 7
| 2014-05-09 |  |  |  |  | 7
28 | 2014-05-10 |  |  |  |  | 5
2014-05-11
2014-05-12
| 2014-05-13 |  |  |  |  | 8
| 2014-05-14 |  |  |  |  | 6
| 2014-05-15 |  |  |  |  | 7
| 2014-05-16 |  |  |  |  | 7
29 | 2014-05-17 |  |  |  |  | 5
2014-05-18
2014-05-19
| 2014-05-20 |  |  |  |  | 8
| 2014-05-21 |  |  |  |  | 6
| 2014-05-22 |  |  |  |  | 7
| 2014-05-23 |  |  |  |  | 7
30 | 2014-05-24 |  |  |  |  | 5
2014-05-25
2014-05-26
| 2014-05-27 |  |  |  |  | 8
| 2014-05-28 |  |  |  |  | 6
| 2014-05-29 |  |  |  |  | 7
| 2014-05-30 |  |  |  |  | 7