## LeNgocChau
Admission System Project
Report date: 29/5/2014 |  |  | Phase: Daily report sprint 4
Reporter: Le Ngoc Chau
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Implement - Create question in DDS (android app) | Medium | 2014-06-05 | 2014-06-05 | Done |  | Le Ngoc Chau
2 | Web service - DMS receive question from DDS (android app) | Medium | 2014-06-05 | 2014-06-05 | Done |  | Le Ngoc Chau
3
4
Plan for next days
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## KhauThanhDao
Admission System Project
Report date: 29/5/2014 |  |  | Phase: Daily report sprint 4
Reporter: Khau Thanh Dao
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Web service - Search in DDS (android app) | Medium | 2014-05-05 | 2014-05-05 | Done |  | Khau Thanh Dao
2 | Deploy - DDS (android app) | High | 2014-06-05 | 2014-06-05 | On-going |  | Khau Thanh Dao
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## NgoQuangHuy
Admission System Project
Report date: 29/5/2014 |  |  | Phase: Daily report sprint 4
Reporter: Ngo Quang Huy
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Detail design for DDS (android app) | High | 2014-06-05 | 2014-06-05 | Done |  | Ngo Quang Huy
2
3
4
6
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1

## NguyenPhanXuanHuy
Admission System Project
Report date: 29/5/2014 |  |  | Phase: Daily report sprint 4
Reporter: Nguyen Phan Xuan Huy
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Implement - Update dictionary in DDS (android app) | Medium | 2014-05-05 | 2014-05-05 | Done |  | Nguyen Phan Xuan Huy
2
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## HuynhTrongKhang
Admission System Project
Report date: 29/5/2014 |  |  | Phase: Daily report sprint 4
Reporter: Huynh Trong Khang
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Implement - View detail question in DDS (android app) | Medium | 2014-05-05 | 2014-05-05 | Done |  | Huynh Trong Khang
2 | Get more business rule for DDS (android app) | High | 2014-06-05 | 2014-06-05 | On-going |  | Huynh Trong Khang
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1 | Android virtual sometime being crash
The most significance knowledge gained last week
# | Description
1
2
3

## TaNgocThienPhu
Admission System Project
Report date: 29/5/2014 |  |  | Phase: Daily report sprint 4
Reporter: Ta Ngoc Thien Phu
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Web service - Sent list question to DDS (android app) | Medium | 2014-06-05 | 2014-06-05 | Done |  | Ta Ngoc Thien Phu
2
3
4
Plan for next days
# | Tasks |  | Start date | Remark |  |  | Owner
1
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Team member
No | Team member
1 | Le Ngoc Chau
2 | Khau Thanh Dao
3 | Ngo Quang Huy
4 | Nguyen Phan Xuan Huy
5 | Huynh Trong Khang
6 | Ta Ngoc Thien Phu