## Team member
Chau Le
Dao Khau
Huy Ngo
Huy Nguyen
Khang Huynh
Phu Ta

## Chau Le
Admission System Project
Report date: 7/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Dao Khau
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Code interface for dictionary | Medium | 2014-05-03 | 2014-06-03 | Done
2
3
4
Plan for next days
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Code interface for change password |  | 2014-07-03
2 | Code interface for view profile |  | 2014-07-03
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1 | understand how to use ckeditor
2
3

## Dao Khau
Admission System Project
Report date: 7/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Dao Khau
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Code interface for menu | Medium | 2014-05-03 | 2014-06-03 | Done
2 | Research tiles template | High | 2014-05-03 | 2014-07-03 | Done
3
4
Plan for next days
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Code interface with ckeditor |  | 2014-07-03
2 | Integrate inteface |  | 2014-07-03
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1 | understand how to use ckeditor
2
3

## Huy Ngo
Admission System Project
Report date: 7/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Huy Ngo
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Code interface for danh sach cau hoi chua tra loi | Medium | 2014-07-03 | 2014-07-03 | On-going
2
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Code interface for danh sach cau hoi chua tra loi |  | 2014-11-03
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Huy Nguyen
Admission System Project
Report date: 7/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Huy Nguyen
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Researh testcase template | Medium | 2014-07-03 | 2014-07-03 | On-going
2
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Code interface for danh sach cau hoi chua tra loi |  | 2014-11-03
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1
2
3

## Khang Huynh
Admission System Project
Report date: 7/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Dao Khau
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Implement login | Medium | 2014-05-03 | 2014-05-03 | Done
2 | Update dictionary-list interface | Medium | 2014-05-03 | 2014-05-03 | Done
3 | Update login, register, menu interface | Medium | 2014-06-03 | 2014-06-03 | Done
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Create business rule for Dictionary management on web application |  | 2014-07-03
2 | Create pagination, checkbox, security code |  | 2014-07-03
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Done |  | Owner
1 |  |  |  |  | Done
The most significance knowledge gained last week
# | Description
1
2
3

## Phu Ta
Admission System Project
Report date: 7/3/2014 |  |  | Phase: Daily report sprint 1
Reporter: Phu Ta
Green
Task status
# | Tasks | Priority | Start date | Actual date | Status | Remark | Owner
1 | Research load list-question from db | Medium | 2014-05-03 | 2014-06-03 | Done
2 | Coding load list-question from db | High | 2014-06-03 | 2014-07-03 | On-going
3
4
Plan for next week
# | Tasks |  | Start date | Remark |  |  | Owner
1 | Coding load list-question from db |  | 2014-07-03
2
3
4
5
Risk/ Action
# | Risk name |  |  | Action
1
2
Issue/ Action
# | Issue name |  |  | Closing date | Action |  | Owner
1
The most significance knowledge gained last week
# | Description
1 | understand how to use ckeditor
2
3